## EDC all
Status | edc_id | project_name | total_units | build_year | bbl | Borough Code | Block | Lot | comments_on_phasing | Question for EDC
EDC provided May 2018 | 1 | Bedford-Union Armory | 415 | 2025 | Not needed, have shapefile
EDC provided May 2018 | 2 | 126 St Bus Depot | 730 | 2022 | Not needed, have shapefile
EDC provided May 2018 | 3 | Spofford Campus Redevelopment LSGD | 777 | 2025 | Not needed, have shapefile |  |  |  | Three phases of construction to be completed by 2024, first residential by 2020
EDC provided May 2018 | 4 | Bronx Point | 1045 | 2023 | Not needed, have shapefile |  |  |  | Two phases, the first 600 (Bronx Point) in 2022
EDC provided May 2018 | 5 | Stapleton Phase I | 329 | 2020 | Not needed, have shapefile |  |  |  | Property has been transferred to a private owner awaiting financing. | What is total units (built/under construction/projected)?
EDC provided May 2018 | 6 | Stapleton Phase II | 485 | 2023 | Not needed, have shapefile |  |  |  | ULURP complete, procurement of developer and CEQR update to update program pending | Is this now Stapleton North/South? Are there changes to timing and unit counts?
EDC provided May 2018 | 7 | Stapleton Phase III | 624 | 2027 | Not needed, have shapefile |  |  |  | ULURP complete, procurement of developer pending. Update of CEQR included in Bay Street Rezonign EIS | Is this now Stapleton North/South? Are there changes to timing and unit counts?
EDC to add | 8 | Coney West (Parcel A) | 508 | 2035 | 3070710100;3070710123
EDC to add | 9 | Coney West (Parcels E & F) | 1353 | 2036 | 3070730101 |  |  |  | Much longer time horizon
EDC to add | 10 | Coney West (Parcel C1) | 135 | 2025 | 3070720001 |  |  |  | C1 - under construction, 135 units. C2 - anticipated closing Oct 2017, 216 units. C3 - closing tentatively planned for 2019, 145 units. C4 - closing tentatively planned for 2020, 100-160 units. D - closing TBD, 300-400 units
EDC to add | 11 | Coney West (Parcel C2) | 220 | 2025 | 3070720002 |  |  |  | C1 - under construction, 135 units. C2 - anticipated closing Oct 2017, 216 units. C3 - closing tentatively planned for 2019, 145 units. C4 - closing tentatively planned for 2020, 100-160 units. D - closing TBD, 300-400 units
EDC to add | 12 | Coney West (Parcel C3) | 145 | 2035 | 3070720003 |  |  |  | C1 - under construction, 135 units. C2 - anticipated closing Oct 2017, 216 units. C3 - closing tentatively planned for 2019, 145 units. C4 - closing tentatively planned for 2020, 100-160 units. D - closing TBD, 300-400 units
EDC to add | 13 | Coney West (Parcel C4) | 160 | 2035 | 3070720004 |  |  |  | C1 - under construction, 135 units. C2 - anticipated closing Oct 2017, 216 units. C3 - closing tentatively planned for 2019, 145 units. C4 - closing tentatively planned for 2020, 100-160 units. D - closing TBD, 300-400 units
EDC to add | 14 | Coney West (Parcel D) | 400 | 2036 | 3070720006 |  |  |  | C1 - under construction, 135 units. C2 - anticipated closing Oct 2017, 216 units. C3 - closing tentatively planned for 2019, 145 units. C4 - closing tentatively planned for 2020, 100-160 units. D - closing TBD, 300-400 units
EDC to add | 15 | Coney North (Parcel N1) | 446 | 2025 | 3070600019 |  |  |  | N1 - closed June 2018, 446 units. N2 - anticipated closing June 2019, 373 units. N3 - anticipated closing June 2020, 259 units
EDC to add | 16 | Coney North (Parcel N2) | 373 | 2035 |  | 3 | 7061 |  | N1 - closed June 2018, 446 units. N2 - anticipated closing June 2019, 373 units. N3 - anticipated closing June 2020, 259 units
EDC to add | 17 | Coney North (Parcel N3) | 259 | 2025 |  | 3 | 7062 |  | N1 - closed June 2018, 446 units. N2 - anticipated closing June 2019, 373 units. N3 - anticipated closing June 2020, 259 units
EDC to add |  | Amazon/formerly Anable Basin and LICIC | 710 |  | Not needed, have from HPD |  |  |  |  | We heard there would be a residential component to Amazon still, can you please confirm/add info?
HPD provided Jan 2019 |  | Beach 21st Street - EDC |  |  | Not needed, have from HPD |  |  |  |  | HPD listed this as a future RFP. Can you confirm, and fill out units and build year?
HPD provided Jan 2019 |  | Spofford RFEI (EDC) |  |  | Not needed, have from HPD |  |  |  |  | HPD listed this as a future RFP. Can you confirm, and fill out units and build year?
HPD provided Jan 2019 |  | Slaughterhouse - EDC |  |  | Not needed, have from HPD |  |  |  |  | HPD listed this as a future RFP. Can you confirm, and fill out units and build year?
HPD provided Jan 2019 |  | Beach 21st Street - EDC |  |  | Not needed, have from HPD |  |  |  |  | HPD listed this as a future RFP. Can you confirm, and fill out units and build year?
HPD provided Jan 2019 |  | Lower Concourse North RFEI - EDC |  |  | Not needed, have from HPD |  |  |  |  | HPD listed this as a future RFP. Can you confirm, and fill out units and build year?
HPD provided Jan 2019 |  | 11-24 Jackson Ave (EDC) |  |  | Not needed, have from HPD |  |  |  |  | HPD listed this as a future RFP. Can you confirm, and fill out units and build year?
HPD provided Jan 2019 |  | 11-24 Jackson Ave (EDC) |  |  | Not needed, have from HPD |  |  |  |  | HPD listed this as a future RFP. Can you confirm, and fill out units and build year?
Anything else you'd like to add to this list?