## Carto Import v2
Action if not found in pipeline | BBLs if not in pipeline or planner inputs | Omit from Public Sites Relevant Projects | Project found in | Project name | Second project name | Third project name | Total units | History/Status | Unique project ID | Project ID | Boro | Lead | Project | ZAP Project ID | ZAP Project ID 2 | ZAP Project ID 3 | ZAP Project ID 4 | City Planning Comments | Aff. Units | CM | Developer | Program | Current Agency | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May |  | Jun | Jul | Aug
|  |  | DCP | 63 Stockholm Street - Bushwick Alliance |  | TRUE | 20 |  | Current 1 | 1 | Bk | HPD | Bushwick Alliance | P2017K0417 |  |  |  |  | 20 | Reynoso & Espinal | Riseboro, St. Nicks | NCP |  | Sep: Certify; Oct: 1; Nov: 2; Dec: 3; Jan: 4; Feb: 5; Mar: Approve
|  |  | HPD RFP | Beach 21st Street - EDC |  | TRUE | 224 |  | Current 2 | 2 | Q | EDC/DM | Beach 21st | No ZAP ID |  |  |  |  | 224 | Richards | Community Builders |  |  | Oct: 4; Nov: 5; Dec: 6; Jan: 7; Dec: 1; Jan: 2; Feb: 3; Mar: Approve
|  |  | HPD RFP | NYCHA Betances VI |  | TRUE | 101 |  | Current 3 | 3 | Bx | NYCHA | Betances VI | P2018X0138 |  |  |  |  | 101 | Ayala | Lemle & Wolff, The Bridge, Alembic | ELLA |  | Oct: Certify; Nov: 1; Dec: 2; Jan: 3; Feb: 4; Mar: Approve
|  |  | HPD RFP | MWBE Site B - 1921 Atlantic Ave |  | TRUE | 235 |  | Current 4 | 4 | Bk | HPD | 1921 Atlantic Ave (MWBE Site B) | P2017K0429 |  |  |  |  | 183 | Ampry-Samuel | Dabar/Thorobird | Mix and Match | [17 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | HPD RFP | Mott-Elizabeth Streets |  | TRUE | 121 |  | Current 5 | 5 | M | HPD | Elizabeth-Mott (Haven Green) | P2018M0251 |  |  |  |  | 121 | Chin | Pennrose, RiseBoro, Habitat, | SARA | HPD | [16 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | Neighborhood Study | Jersey Street Garage |  |  | 220 |  | Current 6 | 6 | SI | HPD | Jersey Street Garage | P2016R0149 |  |  |  |  | 108 | Rose | TBD | TBD | DSNY | [14 empty] | Cert TBD |  | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | DCP | Brook 156 |  | TRUE | 55 |  | Current 7 | 7 | BX | HPD | Brook 156 | P2018X0210 |  |  |  | Brook 156 | 54 | Salamanca | Phipps | ELLA | [18 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | DCP | Brownsville North - Ocean Hill NCP Cluster |  | TRUE | 32 |  | Current 8 | 8 | Bk | HPD | Brownsville North/Ocean Hill | P2017K0368 |  |  |  |  | 32 | Ampry-Samuel | EBC+ Mlappin+Marcal Group | NCP | [18 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | DCP | 201-207 7th Avenue Dispo |  | TRUE | 26 |  | Current 9 | 9 | M | HPD | 7th Avenue TIL/ANCP | P2015M0223 |  |  |  |  | 26 | Johnson | AAFE | TBD | [19 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
Pull from future ZAP |  |  | ZAP | ENY North NCP (UDAAP) |  | TRUE | 79 |  | Current 10 | 10 | Bk | HPD | East New York North | P2018K0116 |  |  |  |  | 41 | Espinal | EBC | NCP | [20 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | HPD RFP | MWBE Site D - 359 E. 157th Street / 784 Courtlandt Avenue |  | TRUE | 20 |  | Current 11 | 11 | Bx | HPD | 784 Courtlandt Ave (MWBE Site D) | P2018X0203 |  |  |  |  | 20 | Salamanca | Infinite Horizons | NCP | [20 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | EDC | Bronx Point |  | TRUE | 1045 |  | Current 12 | 12 | Bx | EDC/DM | Bronx Point UDAAP + Certification | P2018X0177 |  |  |  |  | 800 | Ayala |  |  |  | 4 | 5 | 6 | Approve | [14 empty] | Certify | 1 |  | Certify | 1 | 2 | Approve
|  |  | HPD RFP | Slaughterhouse - EDC |  | FALSE | 230 |  | Current 13 | 13 | M | EDC/DM | 495 Eleventh (fka Slaughterhouse) | P2017M0358 |  |  |  |  | 250 | Johnson | Radson | MIH | NYPD, HPD, DCP | [19 empty] | Certify |  | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | DCP | 776-780 Myrtle Avenue (UDAAP) |  | FALSE | 50 |  | Current 14 | 14 | BK | HPD | 776-780 Myrtle | 2018K0468 |  |  |  |  | 59 | Cornegy | IMPACCT BK | Supportive | HPD | [21 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | HPD | BROWNSVILLE SOUTH |  | TRUE | 42 |  | Current 15 | 15 | Bk | HPD | Brownsville South | P2018K0064 |  |  |  |  | 42 | Barron | Alembic+JMR | NCP | [22 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | HPD | ROCHESTER SUYDAM |  | TRUE | 76 |  | Current 16 | 16 | Bk | HPD | Rochester-Suydam | 2019K0234 |  |  |  |  | 76 | Cornegy & Ampry-Samuel | Jobe/Fulcrum/Briarwood | Open Door | [22 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | DCP | NMEIII West 140th and West 150th |  | FALSE | 61 |  | Current 17 | 17 | M | HPD | NME III | P2017M0377 |  |  |  |  | 67 | Perkins | HCCI, Exact, Prestige | Open Door | [15 empty] | Cert TBD | [6 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | HPD RFP | MWBE Site C - 1510-1524 Broadway |  | TRUE | 107 | Regarding the disagreement disagreement between HPD and DCP about whether an acquisition action for a future MTA elevator is necessary (HPD believes one is; DCP does not), HPD is planning to move forward with the acquisition action included. We have not received a draft application yet | Current 18 | 18 | Bk | HPD | 1510-1524 Broadway (MWBE Site C) | P2017K0284 |  |  |  |  | 103 | Ampry-Samuel | Macquesten | ELLA | [23 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | DCP | 515 Blake Avenue (HA,ZM,ZR,ZS) |  | FALSE | 361 |  | Current 19 | 19 | BK | HPD | 515 Blake | P2018K0333 |  |  |  |  | 556 | Barron | HELP | Supportive/ELLA | DHS/HELP (reverter) | [22 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | DCP | Melrose NIHOP 1 | Melrose NIHOP 2 | FALSE | 71 |  | Current 20 | 20 | BX | HPD | Melrose NIHOP | P2018X0086 |  |  |  |  | 75 | Salamanca | MHANY | Open Door | [23 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | HPD RFP | NYCHA Wyckoff |  | TRUE | 500 |  | Current 21 | 21 | Bk | NYCHA | NYCHA 50/50 - Wyckoff | P2018K0295 |  |  |  |  | 250 | Levin | Arker/Two Trees | ELLA | [27 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | HPD RFP | LIC Waterfront Mixed-Use Development |  | TRUE | Missing |  | Current 22 | 22 | Q | EDC/DM | LIC - Waterfront + DOT site (TBD) | No ZAP ID (Amazon location) |  |  |  |  | 287 | Van Bramer | TF Cornerstone | MIH | DOT, DOE | [19 empty] | Certify |  |  | Cert TBD
|  |  | EDC | Stapleton Phase III |  | TRUE | 624 |  | Current 23 | 23 | SI | DCP | Bay St / Stapleton III / 55 Stuyvesant | P2016R0149 | [5 empty] | Rose | [6 empty] | Certify | 1 | 2 | [8 empty] | Cert TBD | [7 empty] | Cert TBD
|  |  | DCP | 266 West 96th Street |  | TRUE | 170 |  | Current 24 | 24 | M | HPD | 266 West 96 | 2018M0467 |  |  |  |  | 67 | Rosenthal | Fetner | Inclusionary | [23 empty] | Cert TBD
|  |  | DCP | DeKalb Commons (NCP-NIHOP) (UDAAP) |  | TRUE | 85 |  | Current 25 | 25 | Bk | HPD | DeKalb Commons (Bed Stuy I & II NCP) | P2017K0364 |  |  |  | 84 | 85 | St. Nicks | ELLA | ELLA | [15 empty] | Cert TBD |  |  |  | Certify | 1 |  |  | Cert TBD
|  |  | DCP | Columbia Street Waterfront UDAAP |  | TRUE | 13 |  | Current 26 | 26 | Bk | HPD | Columbia Street | P2016K0437 |  |  |  |  | 13 | Lander | Columbia St. Partners | Open Door | [15 empty] | Cert TBD | [7 empty] | Cert TBD
Ignore due to low unit count of clusters (https://www1.nyc.gov/site/hpd/about/press-releases/2018/02/02-13b-18.page) |  | 1 | [6 empty] | Current 27 | 27 | M | HPD | East Harlem NCP | 2018M0390 |  |  |  |  | 75 | Ayala | Ascendent Neighborhood (formerly Lott) | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
|  |  | HPD RFP | Brownsville Site A - Rockaway Avenue/Chester Street |  | FALSE | 230 |  | Current 28 | 28 | Bk | HPD | Brownsville - Site A | No ZAP ID |  |  |  |  | 250 | Ampry-Samuel |  |  |  |  | Issue | [12 empty] | Cert TBD | [7 empty] | Cert TBD
|  |  | HPD RFP | Brownsville Site B - Christopher/Glenmore Ave |  | TRUE | 230 |  | Current 29 | 29 | Bk | HPD | Brownsville - Site B | 2019K0208 |  |  |  |  | 185 | Espinal |  |  |  |  | Issue | [12 empty] | Cert TBD | [7 empty] | Cert TBD
|  |  | HPD RFP | Brownsville Site C - Livonia Sites |  | TRUE | 420 |  | Current 30 | 30 | Bk | HPD | Brownsville - Site C | No ZAP ID |  |  |  |  | 330 | Barron |  |  |  |  | Issue | [12 empty] | Cert TBD | [7 empty] | Cert TBD
Pull from future ZAP |  |  | ZAP | 1559-1563 Prospect Place, Weeksville NCP UDAAP |  | FALSE |  |  | Current 31 | 31 | BK | HPD | Weeksville (NCP) | 2019K0093 |  |  |  |  | 45 | Ampry-Samuel | SHF & Beechwood | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
|  |  | ZAP | NIHOP and NCP Clusters (Northern Site) | NIHOP and NCP Clusters (Middle, Western, and Southern Sites) | FALSE | 96 |  | Current 32 | 32 | M | HPD | Central Harlem I & II | P2018M0158 | P2018M0159 | P2018M0161 | P2018M0332 |  | 100 | Perkins | Lemor & IRIS | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Ignore due to low unit count of clusters |  | 1 |  |  |  | FALSE |  |  | Current 33 | 33 | BX | HPD | East Tremont (NCP) | No ZAP ID |  |  |  |  | 29 | Salamanca | SUS & Fulcrum | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Ignore due to low unit count of clusters |  | 1 |  |  |  | FALSE |  |  | Current 34 | 34 | BX | HPD | Melrose/Concourse (NCP) | No ZAP ID |  |  |  |  | 32 | Gibson | SHF & Beechwood | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Pull from future ZAP |  |  | ZAP |  |  | FALSE | 29 |  | Current 35 | 35 | BX | HPD | Morrisania/Claremont & Morris Heights/Univ Heights | 2019X0192 | 2019X0246 |  |  |  | 62 | Gibson & Cabrera & King | Neighborhood Infill Partner | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
|  |  | HPD | BED STUY CENTRAL AND NORTH |  | FALSE | 78 |  | Current 36 | 36 | BK | HPD | Bed Stuy Central & North NIHOP | 2018K0517 |  |  |  |  | 79 | Cornegy | Shelter Rock | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Ignore due to low unit count |  | 1 |  |  |  | FALSE |  |  | Current 37 | 37 | BK | HPD | Bed Stuy East & Weeksville | No ZAP ID |  |  |  |  | 69 | Ampry-Samuel | Habitat | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
|  |  | DCP | Brownsville North - Ocean Hill NCP Cluster |  | FALSE | 32 |  | Current 38 | 38 | BK | HPD | Brownsville North and South | P2017K0368 |  |  |  |  | 59 | Ampry-Samuel | FAC & Habitat | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
|  |  | Neighborhood Study | 247 Vermont Street (NIHOP and NCP Clusters) EAST NEW YORK REZONING COMMITMENT |  | TRUE | Missing |  | Current 39 | 39 | BK | HPD | East New York & Brownsville (NIHOP) | No ZAP ID |  |  |  |  | 32 | Espinal | Infinite Horizons & FG-PH | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Ignore due to low unit count |  | 1 |  |  |  | FALSE |  |  | Current 40 | 40 | BK | HPD | East New York South & East (NIHOP & NCP) | No ZAP ID |  |  |  |  | 69 | Barron & Espinal | MHANY & CHLDC | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Ignore due to low unit count |  | 1 |  |  |  | FALSE |  |  | Current 41 | 41 | BK | HPD | East New York South & West (NIHOP & NCP) | No ZAP ID |  |  |  |  | 71 | Barron | Rajoy & PM Architecture | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Ignore due to lower unit count |  | 1 |  |  |  | FALSE |  |  | Current 42 | 42 | QNS | HPD | South Jamaica (NCP) | No ZAP ID |  |  |  |  | 40 | Adams | Infinite Horizons & FG-PH | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Ignore due to lower unit count |  | 1 |  |  |  | FALSE |  |  | Current 43 | 43 | QNS | HPD | South Jamaica (NIHOP) | No ZAP ID |  |  |  |  | 23 | Ulrich & Adams | Briarwood & Fulcrum | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
|  |  | ZAP |  |  | TRUE | 600 |  | Current 44 | 44 | Bk | HPD | Greenpoint Hospital | 2019K0177 |  |  |  |  | 300 | Reynoso |  |  |  |  | Issue | [12 empty] | Cert TBD | [7 empty] | Cert TBD
[6 empty] | FALSE |  |  |  |  | RFP / RFEI Pipeline
Covered by planner input | 1004910016 | 0 |  |  |  | FALSE |  |  | Pipeline 1 | 1 | M | ECF | 131 Sixth Ave | No ZAP ID | [5 empty] | Johnson | [11 empty] | Issue | [6 empty] | Select |  | Select
|  |  | HPD RFP | NYCHA Senior -Bushwick II |  | TRUE | 154 |  | Pipeline 2 | 2 | Bk | NYCHA | Bushwick II Senior First | No ZAP ID |  |  |  |  | 100 | Espinal | [7 empty] | Issue | 1 | 2 | [10 empty] | Select |  |  | Select
|  |  | HPD RFP | NYCHA Senior -Sotomayor |  | TRUE | 200 |  | Pipeline 3 | 3 | Bx | NYCHA | Sotomayor Senior First | No ZAP ID |  |  |  |  | 100 | Diaz | [7 empty] | Issue | 1 | 2 | [10 empty] | Select |  |  | Select
Ignore project -- too early stage |  | 1 |  |  |  | FALSE |  |  | Pipeline 4 | 4 | Bk | EDC/DM | DUMBO Man Bridge Dev Rights | No ZAP ID | [5 empty] | Levin | [6 empty] | Issue | [11 empty] | Select |  |  | Select |  | Select
|  |  | HPD RFP | Grant Avenue (Modular) |  | TRUE | 167 |  | Pipeline 5 | 5 | Bk | HPD | Grant Avenue Muni | No ZAP ID |  |  |  |  | 100 | Espinal | [13 empty] | Issue | [8 empty] | Select | Select
|  |  | HPD RFP | Broadway Triangle - Site A | Broadway Triangle - Site B | TRUE | 387 |  | Pipeline 6 | 6 | Bk | HPD | Broadway Triangle (3 sites) | No ZAP ID |  |  |  |  | 320 | Reynoso | [14 empty] | Issue | [8 empty] | Select
Ignore due to lower unit count |  | 1 | [6 empty] | Pipeline 7 | 7 | Multi | HPD | Big Ideas, Small Lots Design Competiton | No ZAP ID |  |  |  |  | TBD | Various | [19 empty] | Public |  | Issue |  |  |  | Select
Ignore due to unselected site |  | 1 | [6 empty] | Pipeline 8 | 8 | Multi | EDC/DM | Life Sciences HUB RFEI & RFP | No ZAP ID |  |  |  |  | 0 | TBD | [10 empty] | Issue RFEI | [7 empty] | Issue | [7 empty] | Select
Ignore due to unselected site |  | 1 | [6 empty] | Pipeline 9 | 9 | Multi | HPD | ShareNYC (Shared Facilities) | No ZAP ID |  |  |  |  | TBD | Various | [18 empty] | Issue | Issue | [8 empty] | Select
|  |  | HPD RFP | 11-24 Jackson Ave (EDC) |  | FALSE |  |  | Pipeline 10 | 10 | Q | EDC/DM | 11-24 Jackson Ave. | No ZAP ID |  |  |  |  | TBD | Van Bramer | [18 empty] | Select | [10 empty] | Select
|  |  | Neighborhood Study | 97 West 169th Street JEROME REZONING COMMITMENT |  |  | 50 |  | Pipeline 11 | 11 | BX | HPD | Corporal Fischer/97 W. 169th St. | No ZAP ID |  |  |  |  | 65 | Gibson | [11 empty] | Points of Agreement to release in 2018 | [8 empty] | Issue | [8 empty] | Select
|  |  | HPD RFP | NYCHA LaGuardia |  | TRUE | Missing |  | Pipeline 12 | 12 | M | NYCHA | NYCHA - La Guardia | No ZAP ID |  |  |  |  | 180 | Chin | [11 empty] | Issue | [14 empty] | ReIssue |  |  |  | 6 6 6 6 6 6 6 6 5: Select
Covered in planner input |  | 0 | [6 empty] | Pipeline 13 | 13 | Bk | NYCHA | NYCHA - Cooper Park | No ZAP ID |  |  |  |  | 115 | Reynoso | [26 empty] | Issue |  |  |  | 6 6 6 6 6 6 6 6 5: Select
|  |  | Neighborhood Study | (Projected RFP) NYPD 25th Precinct Parking Lot (Site 2) EAST HARLEM REZONING COMMITMENT |  | TRUE | Missing |  | Pipeline 14 | 14 | M | HPD | NYPD 25th Precinct Parking Lot | No ZAP ID |  |  |  |  | 250 | Ayala | [11 empty] | Points of Agreement by Q2 of CY2019 | Points of Agreement by Q2 of CY2019 | [13 empty] | Issue |  |  |  | 6 6 6 6 6 6 6 6 6: Select
|  |  | Neighborhood Study | (Projected RFP) HRA East Harlem Multiâ€Service Center (Site 1) EAST HARLEM REZONING COMMITMENT |  | TRUE | Missing |  | Pipeline 15 | 15 | M | HPD | HRA E. Harlem Multi-Service Center | No ZAP ID |  |  |  |  | 140 | Ayala | [11 empty] | Points of Agreement by Q2 of CY2019 | Points of Agreement by Q2 of CY2019 | [13 empty] | Issue |  |  |  | 6 6 6 6 6 6 6 6 6: Select
Ignore -- multi borough |  | 1 | [6 empty] | Pipeline 16 | 16 | Multi | NYCHA | 50/50 - 2 sites | No ZAP ID |  |  |  |  | TBD | TBD | [27 empty] | Issue |  |  | 6 6 6 6 6 6 6 6 6: Select
Covered in planner input |  | 0 | [6 empty] | Pipeline 17 | 17 | Q | HPD | Astoria DOT Lot (Seniors) | No ZAP ID |  |  |  |  | TBD | Constantinides | [28 empty] | Issue
|  |  | HPD RFP | NYCHA Morrisania Air Rights | NYCHA Sumner Houses; NYCHA Twin Park West; NYCHA Harborview Terrace |  |  |  | Pipeline 18 | 18 | Multi | NYCHA | 100% Affordable - 4 sites | No ZAP ID |  |  |  |  | TBD | TBD | [29 empty] | Issue | [7 empty] | Select
|  |  | Neighborhood Study | 1640-1642 Anthony Avenue JEROME REZONING COMMITMENT |  |  | 50 |  | Pipeline 19 | 19 | Bx | HPD | Anthony Ave ACS Play Lot | No ZAP ID |  |  |  |  | 50 | Gibson | [11 empty] | Points of Agreement by Q3 of CY2019 | Points of Agreement by Q3 of CY2019 | [16 empty] | Issue | [8 empty] | Select
|  |  | Neighborhood Study | Morrisania Diagnostic and Treatment Center Surface Lot JEROME REZONING COMMITMENT |  |  | 100 |  | Pipeline 20 | 20 | Bx | HPD | Morrisania H+H Surface Lot | No ZAP ID |  |  |  |  | 180 | Gibson | [11 empty] | Points of Agreement by Q3 of CY2019 | Points of Agreement by Q3 of CY2019 | [15 empty] | Issue | Issue | [8 empty] | Select
|  |  | EDC | 126 St Bus Depot |  | TRUE | 730 |  | Pipeline 21 | 21 | M | EDC/DM | Bus Depot 126th St-Cultural Operator Only | No ZAP ID |  |  |  |  | 580 | Ayala | [29 empty] | Issue | [8 empty] | Select | Select
Covered in planner input |  | 0 | [6 empty] | Pipeline 22 | 22 | Bk | HPD | Fulton St Sites ( A + B - Seniors) | No ZAP ID |  |  |  |  | 300 | Ampry-Samuel | [30 empty] | 6 6 6 6 6 5 5 5 1: Issue |  |  | Select
KS to calculate assumed unit count | 3011430025 | 0 | [6 empty] | Pipeline 23 | 23 | Bk | HPD | 516 Bergen + ENS Lot (Seniors) | No ZAP ID |  |  |  |  | TBD | Cumbo | [11 empty] | Points of Agreement | Points of Agreement | [17 empty] | 6 6 6 6 6 6 6 6 2: Tentative Issue
Ignore -- multi borough |  | 1 | [6 empty] | Pipeline 24 | 24 | Multi | HPD | MWBE RFP | [5 empty] | TBD | Various | [30 empty] | 6 6 6 6 6 6 6 6 2: Issue
Ignore -- project cancelled |  |  | HPD RFP | NYCHA Harborview Terrace |  | TRUE | Missing |  | Pipeline 25 | 25 | M | NYCHA | Harborview | [5 empty] | 227 | Rosenthal | [11 empty] | Select | Select | [5 empty] | Select
|  |  | ZAP | Sea View Healthy Community |  |  | 500 |  | Pipeline 26 | 26 | SI | EDC | Seaview Healthy Community (TBD) | P2018R0276 |  |  |  |  | 400 | Matteo |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | [9 empty] | Select
|  |  | HPD RFP | NYCHA Senior - Baruch |  | TRUE | Missing |  | Pipeline 27 | 27 | M | NYCHA | Baruch Seniors First (TBD) | No ZAP ID |  |  |  | Baruch Senior First | 100 | Rivera |  |  |  | 6: Issue | 1 | 2 | [10 empty] | Select
KS to calculate | 2025710001 | 0 | [6 empty] | Pipeline 28 | 28 | Bx | HPD | 351 Powers Avenue | No ZAP ID |  |  |  |  | TBD | Ayala | [11 empty] | Points of Agreement to release in 2019 | Points of Agreement to release in 2019
Covered in planner input |  | 0 |  |  |  |  | 1704 |  | Pipeline 29 | 29 | Q | HPD | Hunters Point D+E | No ZAP ID |  |  |  |  | 1020 | Van Bramer | [38 empty] | Select
Ignore, too early stage |  | 1 | [6 empty] | Pipeline 30 | 30 | Bk | HPD | DEP - Myrtle ST | [6 empty] | Cumbo
Ignore -- Project seems to be in early stages |  | 1 | [6 empty] | Pipeline 31 | 31 | BX | HPD | Southern BLVD Acquisition Sites | No ZAP ID |  |  |  |  | TBD | Salamanca
|  |  | EDC | Stapleton Phase III |  | TRUE | 624 |  | Pipeline 32 | 32 | SI | EDC/DM | Stapleton North (TBD) | No ZAP ID | [5 empty] | Rose
|  |  | EDC | Stapleton Phase II |  | FALSE | 485 |  | Pipeline 33 | 33 | SI | EDC/DM | Stapleton South (TBD) | No ZAP ID | [5 empty] | Rose | [37 empty] | Select
Note on N4: Cohen, Jon: HPD had approval in May
Note on N50: Sharon Tepper: Selection moved out
Note on N54: Sharon Tepper: reinserted
Note on N56: Sharon Tepper: Selection moved out
Note on N67: Sharon Tepper: I removed the listing in the Project list above and kept here, since we have not yet released the RFP; also moved out schedule
Note on N72: Sharon Tepper: Selection moved out

## Public Sites
PUBLIC SITES
[11 empty] | Last revised | 2019-03-05
[21 empty] | 2017 | [5 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020
Action if not found in pipeline | BBLs if not in pipeline or planner inputs | Omit from Public Sites Relevant Projects | Project found in | Project name | Second project name | Third project name | Total units | History/Status | Unique project ID | Project ID | Boro | Lead | Project | ZAP Project ID | City Planning Comments | Aff. Units | CM | Developer | Program | Current Agency | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May |  | Jun | Jul | Aug
|  |  | DCP | 63 Stockholm Street - Bushwick Alliance |  | TRUE | 20 |  | Current 1 | 1 | Bk | HPD | Bushwick Alliance | P2017K0417 |  | 20 | Reynoso & Espinal | Riseboro, St. Nicks | NCP |  | 2018 Sep: Certify; 2018 Oct: 1; 2018 Nov: 2; 2018 Dec: 3; 2019 Jan: 4; 2019 Feb: 5; 2019 Mar: Approve
|  |  | HPD RFP | Beach 21st Street - EDC |  | TRUE | 224 |  | Current 2 | 2 | Q | EDC/DM | Beach 21st | No ZAP ID |  | 224 | Richards | Community Builders |  |  | 2017 Oct: 4; 2017 Nov: 5; 2017 Dec: 6; 2018 Jan: 7; 2018 Dec: 1; 2019 Jan: 2; 2019 Feb: 3; 2019 Mar: Approve
|  |  | HPD RFP | NYCHA Betances VI |  | TRUE | 101 |  | Current 3 | 3 | Bx | NYCHA | Betances VI | P2018X0138 |  | 101 | Ayala | Lemle & Wolff, The Bridge, Alembic | ELLA |  | 2018 Oct: Certify; 2018 Nov: 1; 2018 Dec: 2; 2019 Jan: 3; 2019 Feb: 4; 2019 Mar: Approve
|  |  | HPD RFP | MWBE Site B - 1921 Atlantic Ave |  | TRUE | 235 |  | Current 4 | 4 | Bk | HPD | 1921 Atlantic Ave (MWBE Site B) | P2017K0429 |  | 183 | Ampry-Samuel | Dabar/Thorobird | Mix and Match | [17 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | HPD RFP | Mott-Elizabeth Streets |  | TRUE | 121 |  | Current 5 | 5 | M | HPD | Elizabeth-Mott (Haven Green) | P2018M0251 |  | 121 | Chin | Pennrose, RiseBoro, Habitat, | SARA | HPD | [16 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | Neighborhood Study | Jersey Street Garage |  |  | 220 |  | Current 6 | 6 | SI | HPD | Jersey Street Garage | P2016R0149 |  | 108 | Rose | TBD | TBD | DSNY | [14 empty] | Cert TBD |  | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | DCP | Brook 156 |  | TRUE | 55 |  | Current 7 | 7 | BX | HPD | Brook 156 | P2018X0210 | Brook 156 | 54 | Salamanca | Phipps | ELLA | [18 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | DCP | Brownsville North - Ocean Hill NCP Cluster |  | TRUE | 32 |  | Current 8 | 8 | Bk | HPD | Brownsville North/Ocean Hill | P2017K0368 |  | 32 | Ampry-Samuel | EBC+ Mlappin+Marcal Group | NCP | [18 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | DCP | 201-207 7th Avenue Dispo |  | TRUE | 26 |  | Current 9 | 9 | M | HPD | 7th Avenue TIL/ANCP | P2015M0223 |  | 26 | Johnson | AAFE | TBD | [19 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
Pull from future ZAP |  |  | ZAP | ENY North NCP (UDAAP) |  | TRUE | 79 |  | Current 10 | 10 | Bk | HPD | East New York North | P2018K0116 |  | 41 | Espinal | EBC | NCP | [20 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | HPD RFP | MWBE Site D - 359 E. 157th Street / 784 Courtlandt Avenue |  | TRUE | 20 |  | Current 11 | 11 | Bx | HPD | 784 Courtlandt Ave (MWBE Site D) | P2018X0203 |  | 20 | Salamanca | Infinite Horizons | NCP | [20 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | EDC | Bronx Point |  | TRUE | 1045 |  | Current 12 | 12 | Bx | EDC/DM | Bronx Point UDAAP + Certification | P2018X0177 |  | 800 | Ayala |  |  |  | 4 | 5 | 6 | Approve | [14 empty] | Certify | 1 |  | Certify | 1 | 2 | Approve
|  |  | HPD RFP | Slaughterhouse - EDC |  | FALSE | 230 |  | Current 13 | 13 | M | EDC/DM | 495 Eleventh (fka Slaughterhouse) | P2017M0358 |  | 250 | Johnson | Radson | MIH | NYPD, HPD, DCP | [19 empty] | Certify |  | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | DCP | 776-780 Myrtle Avenue (UDAAP) |  | FALSE | 50 |  | Current 14 | 14 | BK | HPD | 776-780 Myrtle | 2018K0468 |  | 59 | Cornegy | IMPACCT BK | Supportive | HPD | [21 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | HPD | BROWNSVILLE SOUTH |  | TRUE | 42 |  | Current 15 | 15 | Bk | HPD | Brownsville South | P2018K0064 |  | 42 | Barron | Alembic+JMR | NCP | [22 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | HPD | ROCHESTER SUYDAM |  | TRUE | 76 |  | Current 16 | 16 | Bk | HPD | Rochester-Suydam | 2019K0234 |  | 76 | Cornegy & Ampry-Samuel | Jobe/Fulcrum/Briarwood | Open Door | [22 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | DCP | NMEIII West 140th and West 150th |  | FALSE | 61 |  | Current 17 | 17 | M | HPD | NME III | P2017M0377 |  | 67 | Perkins | HCCI, Exact, Prestige | Open Door | [15 empty] | Cert TBD | [6 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | HPD RFP | MWBE Site C - 1510-1524 Broadway |  | TRUE | 107 | Regarding the disagreement disagreement between HPD and DCP about whether an acquisition action for a future MTA elevator is necessary (HPD believes one is; DCP does not), HPD is planning to move forward with the acquisition action included. We have not received a draft application yet | Current 18 | 18 | Bk | HPD | 1510-1524 Broadway (MWBE Site C) | P2017K0284 |  | 103 | Ampry-Samuel | Macquesten | ELLA | [23 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | DCP | 515 Blake Avenue (HA,ZM,ZR,ZS) |  | FALSE | 361 |  | Current 19 | 19 | BK | HPD | 515 Blake | P2018K0333 |  | 556 | Barron | HELP | Supportive/ELLA | DHS/HELP (reverter) | [22 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | DCP | Melrose NIHOP 1 | Melrose NIHOP 2 | FALSE | 71 |  | Current 20 | 20 | BX | HPD | Melrose NIHOP | P2018X0086 |  | 75 | Salamanca | MHANY | Open Door | [23 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | HPD RFP | NYCHA Wyckoff |  | TRUE | 500 |  | Current 21 | 21 | Bk | NYCHA | NYCHA 50/50 - Wyckoff | P2018K0295 |  | 250 | Levin | Arker/Two Trees | ELLA | [27 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
|  |  | HPD RFP | LIC Waterfront Mixed-Use Development |  | TRUE | Missing |  | Current 22 | 22 | Q | EDC/DM | LIC - Waterfront + DOT site (TBD) | No ZAP ID (Amazon location) |  | 287 | Van Bramer | TF Cornerstone | MIH | DOT, DOE | [19 empty] | Certify |  |  | Cert TBD
|  |  | EDC | Stapleton Phase III |  | TRUE | 624 |  | Current 23 | 23 | SI | DCP | Bay St / Stapleton III / 55 Stuyvesant | P2016R0149 |  |  | Rose | [6 empty] | Certify | 1 | 2 | [8 empty] | Cert TBD | [7 empty] | Cert TBD
|  |  | DCP | 266 West 96th Street |  | TRUE | 170 |  | Current 24 | 24 | M | HPD | 266 West 96 | 2018M0467 |  | 67 | Rosenthal | Fetner | Inclusionary | [23 empty] | Cert TBD
|  |  | DCP | DeKalb Commons (NCP-NIHOP) (UDAAP) |  | TRUE | 85 |  | Current 25 | 25 | Bk | HPD | DeKalb Commons (Bed Stuy I & II NCP) | P2017K0364 | 84 | 85 | St. Nicks | ELLA | ELLA | [15 empty] | Cert TBD |  |  |  | Certify | 1 |  |  | Cert TBD
|  |  | DCP | Columbia Street Waterfront UDAAP |  | TRUE | 13 |  | Current 26 | 26 | Bk | HPD | Columbia Street | P2016K0437 |  | 13 | Lander | Columbia St. Partners | Open Door | [15 empty] | Cert TBD | [7 empty] | Cert TBD
Ignore due to low unit count of clusters (https://www1.nyc.gov/site/hpd/about/press-releases/2018/02/02-13b-18.page) |  | 1 | [6 empty] | Current 27 | 27 | M | HPD | East Harlem NCP | 2018M0390 |  | 75 | Ayala | Ascendent Neighborhood (formerly Lott) | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
|  |  | HPD RFP | Brownsville Site A - Rockaway Avenue/Chester Street |  | FALSE | 230 |  | Current 28 | 28 | Bk | HPD | Brownsville - Site A | No ZAP ID |  | 250 | Ampry-Samuel |  |  |  |  | Issue | [12 empty] | Cert TBD | [7 empty] | Cert TBD
|  |  | HPD RFP | Brownsville Site B - Christopher/Glenmore Ave |  | TRUE | 230 |  | Current 29 | 29 | Bk | HPD | Brownsville - Site B | 2019K0208 |  | 185 | Espinal |  |  |  |  | Issue | [12 empty] | Cert TBD | [7 empty] | Cert TBD
|  |  | HPD RFP | Brownsville Site C - Livonia Sites |  | TRUE | 420 |  | Current 30 | 30 | Bk | HPD | Brownsville - Site C | No ZAP ID |  | 330 | Barron |  |  |  |  | Issue | [12 empty] | Cert TBD | [7 empty] | Cert TBD
Pull from future ZAP |  |  | ZAP | 1559-1563 Prospect Place, Weeksville NCP UDAAP |  | FALSE |  |  | Current 31 | 31 | BK | HPD | Weeksville (NCP) | 2019K0093 |  | 45 | Ampry-Samuel | SHF & Beechwood | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
|  |  | ZAP | NIHOP and NCP Clusters (Northern Site) | NIHOP and NCP Clusters (Middle, Western, and Southern Sites) | FALSE | 96 |  | Current 32 | 32 | M | HPD | Central Harlem I & II | P2018M0158; P2018M0159; P2018M0161; P2018M0332 |  | 100 | Perkins | Lemor & IRIS | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Ignore due to low unit count of clusters |  | 1 |  |  |  | FALSE |  |  | Current 33 | 33 | BX | HPD | East Tremont (NCP) | No ZAP ID |  | 29 | Salamanca | SUS & Fulcrum | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Ignore due to low unit count of clusters |  | 1 |  |  |  | FALSE |  |  | Current 34 | 34 | BX | HPD | Melrose/Concourse (NCP) | No ZAP ID |  | 32 | Gibson | SHF & Beechwood | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Pull from future ZAP |  |  | ZAP |  |  | FALSE | 29 |  | Current 35 | 35 | BX | HPD | Morrisania/Claremont & Morris Heights/Univ Heights | 2019X0192; 2019X0246 |  | 62 | Gibson & Cabrera & King | Neighborhood Infill Partner | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
|  |  | HPD | BED STUY CENTRAL AND NORTH |  | FALSE | 78 |  | Current 36 | 36 | BK | HPD | Bed Stuy Central & North NIHOP | 2018K0517 |  | 79 | Cornegy | Shelter Rock | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Ignore due to low unit count |  | 1 |  |  |  | FALSE |  |  | Current 37 | 37 | BK | HPD | Bed Stuy East & Weeksville | No ZAP ID |  | 69 | Ampry-Samuel | Habitat | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
|  |  | DCP | Brownsville North - Ocean Hill NCP Cluster |  | FALSE | 32 |  | Current 38 | 38 | BK | HPD | Brownsville North and South | P2017K0368 |  | 59 | Ampry-Samuel | FAC & Habitat | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
|  |  | Neighborhood Study | 247 Vermont Street (NIHOP and NCP Clusters) EAST NEW YORK REZONING COMMITMENT |  | TRUE | Missing |  | Current 39 | 39 | BK | HPD | East New York & Brownsville (NIHOP) | No ZAP ID |  | 32 | Espinal | Infinite Horizons & FG-PH | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Ignore due to low unit count |  | 1 |  |  |  | FALSE |  |  | Current 40 | 40 | BK | HPD | East New York South & East (NIHOP & NCP) | No ZAP ID |  | 69 | Barron & Espinal | MHANY & CHLDC | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Ignore due to low unit count |  | 1 |  |  |  | FALSE |  |  | Current 41 | 41 | BK | HPD | East New York South & West (NIHOP & NCP) | No ZAP ID |  | 71 | Barron | Rajoy & PM Architecture | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Ignore due to lower unit count |  | 1 |  |  |  | FALSE |  |  | Current 42 | 42 | QNS | HPD | South Jamaica (NCP) | No ZAP ID |  | 40 | Adams | Infinite Horizons & FG-PH | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Ignore due to lower unit count |  | 1 |  |  |  | FALSE |  |  | Current 43 | 43 | QNS | HPD | South Jamaica (NIHOP) | No ZAP ID |  | 23 | Ulrich & Adams | Briarwood & Fulcrum | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
|  |  | ZAP |  |  | TRUE | 600 |  | Current 44 | 44 | Bk | HPD | Greenpoint Hospital | 2019K0177 |  | 300 | Reynoso |  |  |  |  | Issue | [12 empty] | Cert TBD | [7 empty] | Cert TBD
[6 empty] | FALSE |  |  |  |  | RFP / RFEI Pipeline
Covered by planner input |  | 0 |  |  |  | FALSE |  |  | Pipeline 1 | 1 | M | ECF | 131 Sixth Ave | No ZAP ID |  |  | Johnson | [11 empty] | Issue | [6 empty] | Select |  | Select
|  |  | HPD RFP | NYCHA Senior -Bushwick II |  | TRUE | 154 |  | Pipeline 2 | 2 | Bk | NYCHA | Bushwick II Senior First | No ZAP ID |  | 100 | Espinal | [7 empty] | Issue | 1 | 2 | [10 empty] | Select |  |  | Select
|  |  | HPD RFP | NYCHA Senior -Sotomayor |  | TRUE | 200 |  | Pipeline 3 | 3 | Bx | NYCHA | Sotomayor Senior First | No ZAP ID |  | 100 | Diaz | [7 empty] | Issue | 1 | 2 | [10 empty] | Select |  |  | Select
Ignore project -- too early stage |  | 1 |  |  |  | FALSE |  |  | Pipeline 4 | 4 | Bk | EDC/DM | DUMBO Man Bridge Dev Rights | No ZAP ID |  |  | Levin | [6 empty] | Issue | [11 empty] | Select |  |  | Select |  | Select
|  |  | HPD RFP | Grant Avenue (Modular) |  | TRUE | 167 |  | Pipeline 5 | 5 | Bk | HPD | Grant Avenue Muni | No ZAP ID |  | 100 | Espinal | [13 empty] | Issue | [8 empty] | Select | Select
|  |  | HPD RFP | Broadway Triangle - Site A | Broadway Triangle - Site B | TRUE | 387 |  | Pipeline 6 | 6 | Bk | HPD | Broadway Triangle (3 sites) | No ZAP ID |  | 320 | Reynoso | [14 empty] | Issue | [8 empty] | Select
Ignore due to lower unit count |  | 1 | [6 empty] | Pipeline 7 | 7 | Multi | HPD | Big Ideas, Small Lots Design Competiton | No ZAP ID |  | TBD | Various | [19 empty] | Public |  | Issue |  |  |  | Select
Ignore due to unselected site |  | 1 | [6 empty] | Pipeline 8 | 8 | Multi | EDC/DM | Life Sciences HUB RFEI & RFP | No ZAP ID |  | 0 | TBD | [10 empty] | Issue RFEI | [7 empty] | Issue | [7 empty] | Select
Ignore due to unselected site |  | 1 | [6 empty] | Pipeline 9 | 9 | Multi | HPD | ShareNYC (Shared Facilities) | No ZAP ID |  | TBD | Various | [18 empty] | Issue | Issue | [8 empty] | Select
|  |  | HPD RFP | 11-24 Jackson Ave (EDC) |  | FALSE |  |  | Pipeline 10 | 10 | Q | EDC/DM | 11-24 Jackson Ave. | No ZAP ID |  | TBD | Van Bramer | [18 empty] | Select | [10 empty] | Select
|  |  | Neighborhood Study | 97 West 169th Street JEROME REZONING COMMITMENT |  |  | 50 |  | Pipeline 11 | 11 | BX | HPD | Corporal Fischer/97 W. 169th St. | No ZAP ID |  | 65 | Gibson | [11 empty] | Points of Agreement to release in 2018 | [8 empty] | Issue | [8 empty] | Select
|  |  | HPD RFP | NYCHA LaGuardia |  | TRUE | Missing |  | Pipeline 12 | 12 | M | NYCHA | NYCHA - La Guardia | No ZAP ID |  | 180 | Chin | [11 empty] | Issue | [14 empty] | ReIssue |  |  |  | 6 6 6 6 6 6 6 6 5: Select
Covered in planner input |  | 0 | [6 empty] | Pipeline 13 | 13 | Bk | NYCHA | NYCHA - Cooper Park | No ZAP ID |  | 115 | Reynoso | [26 empty] | Issue |  |  |  | 6 6 6 6 6 6 6 6 5: Select
|  |  | Neighborhood Study | (Projected RFP) NYPD 25th Precinct Parking Lot (Site 2) EAST HARLEM REZONING COMMITMENT |  | TRUE | Missing |  | Pipeline 14 | 14 | M | HPD | NYPD 25th Precinct Parking Lot | No ZAP ID |  | 250 | Ayala | [11 empty] | Points of Agreement by Q2 of CY2019 | Points of Agreement by Q2 of CY2019 | [13 empty] | Issue |  |  |  | 6 6 6 6 6 6 6 6 6: Select
|  |  | Neighborhood Study | (Projected RFP) HRA East Harlem Multiâ€Service Center (Site 1) EAST HARLEM REZONING COMMITMENT |  | TRUE | Missing |  | Pipeline 15 | 15 | M | HPD | HRA E. Harlem Multi-Service Center | No ZAP ID |  | 140 | Ayala | [11 empty] | Points of Agreement by Q2 of CY2019 | Points of Agreement by Q2 of CY2019 | [13 empty] | Issue |  |  |  | 6 6 6 6 6 6 6 6 6: Select
Ignore -- multi borough |  | 1 | [6 empty] | Pipeline 16 | 16 | Multi | NYCHA | 50/50 - 2 sites | No ZAP ID |  | TBD | TBD | [27 empty] | Issue |  |  | 6 6 6 6 6 6 6 6 6: Select
Covered in planner input |  | 0 | [6 empty] | Pipeline 17 | 17 | Q | HPD | Astoria DOT Lot (Seniors) | No ZAP ID |  | TBD | Constantinides | [28 empty] | Issue
|  |  | HPD RFP | NYCHA Morrisania Air Rights | NYCHA Sumner Houses; NYCHA Twin Park West; NYCHA Harborview Terrace |  |  |  | Pipeline 18 | 18 | Multi | NYCHA | 100% Affordable - 4 sites | No ZAP ID |  | TBD | TBD | [29 empty] | Issue | [7 empty] | Select
|  |  | Neighborhood Study | 1640-1642 Anthony Avenue JEROME REZONING COMMITMENT |  |  | 50 |  | Pipeline 19 | 19 | Bx | HPD | Anthony Ave ACS Play Lot | No ZAP ID |  | 50 | Gibson | [11 empty] | Points of Agreement by Q3 of CY2019 | Points of Agreement by Q3 of CY2019 | [16 empty] | Issue | [8 empty] | Select
|  |  | Neighborhood Study | Morrisania Diagnostic and Treatment Center Surface Lot JEROME REZONING COMMITMENT |  |  | 100 |  | Pipeline 20 | 20 | Bx | HPD | Morrisania H+H Surface Lot | No ZAP ID |  | 180 | Gibson | [11 empty] | Points of Agreement by Q3 of CY2019 | Points of Agreement by Q3 of CY2019 | [15 empty] | Issue | Issue | [8 empty] | Select
|  |  | EDC | 126 St Bus Depot |  | TRUE | 730 |  | Pipeline 21 | 21 | M | EDC/DM | Bus Depot 126th St-Cultural Operator Only | No ZAP ID |  | 580 | Ayala | [29 empty] | Issue | [8 empty] | Select | Select
Covered in planner input |  | 0 | [6 empty] | Pipeline 22 | 22 | Bk | HPD | Fulton St Sites ( A + B - Seniors) | No ZAP ID |  | 300 | Ampry-Samuel | [30 empty] | 6 6 6 6 6 5 5 5 1: Issue |  |  | Select
KS to calculate assumed unit count | 3011430025 | 0 | [6 empty] | Pipeline 23 | 23 | Bk | HPD | 516 Bergen + ENS Lot (Seniors) | No ZAP ID |  | TBD | Cumbo | [11 empty] | Points of Agreement | Points of Agreement | [17 empty] | 6 6 6 6 6 6 6 6 2: Tentative Issue
Ignore -- multi borough |  | 1 | [6 empty] | Pipeline 24 | 24 | Multi | HPD | MWBE RFP |  |  | TBD | Various | [30 empty] | 6 6 6 6 6 6 6 6 2: Issue
Ignore -- project cancelled |  |  | HPD RFP | NYCHA Harborview Terrace |  | TRUE | Missing |  | Pipeline 25 | 25 | M | NYCHA | Harborview |  |  | 227 | Rosenthal | [11 empty] | Select | Select | [5 empty] | Select
Covered in planner input |  | 0 |  |  |  |  | 500 |  | Pipeline 26 | 26 | SI | EDC | Seaview Healthy Community (TBD) | No ZAP ID |  | 400 | Matteo |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | [9 empty] | Select
|  |  | HPD RFP | NYCHA Senior - Baruch |  | TRUE | Missing |  | Pipeline 27 | 27 | M | NYCHA | Baruch Seniors First (TBD) | No ZAP ID | Baruch Senior First | 100 | Rivera |  |  |  | 6: Issue | 1 | 2 | [10 empty] | Select
KS to calculate | 2025710001 | 0 | [6 empty] | Pipeline 28 | 28 | Bx | HPD | 351 Powers Avenue | No ZAP ID |  | TBD | Ayala | [11 empty] | Points of Agreement to release in 2019 | Points of Agreement to release in 2019
Covered in planner input |  | 0 |  |  |  |  | 1704 |  | Pipeline 29 | 29 | Q | HPD | Hunters Point D+E | No ZAP ID |  | 1020 | Van Bramer | [38 empty] | Select
Ignore, too early stage |  | 1 | [6 empty] | Pipeline 30 | 30 | Bk | HPD | DEP - Myrtle ST |  |  |  | Cumbo
Ignore -- Project seems to be in early stages |  | 1 | [6 empty] | Pipeline 31 | 31 | BX | HPD | Southern BLVD Acquisition Sites | No ZAP ID |  | TBD | Salamanca
|  |  | EDC | Stapleton Phase III |  | TRUE | 624 |  | Pipeline 32 | 32 | SI | EDC/DM | Stapleton North (TBD) | No ZAP ID |  |  | Rose
|  |  | EDC | Stapleton Phase II |  | FALSE | 485 |  | Pipeline 33 | 33 | SI | EDC/DM | Stapleton South (TBD) | No ZAP ID |  |  | Rose | [37 empty] | Select
Note on N7: Cohen, Jon: HPD had approval in May
Note on N53: Sharon Tepper: Selection moved out
Note on N57: Sharon Tepper: reinserted
Note on N59: Sharon Tepper: Selection moved out
Note on N70: Sharon Tepper: I removed the listing in the Project list above and kept here, since we have not yet released the RFP; also moved out schedule
Note on N75: Sharon Tepper: Selection moved out

## Carto Import
Unique project ID | Project ID | Boro | Lead | Project | ZAP Project ID | ZAP Project ID 2 | ZAP Project ID 3 | ZAP Project ID 4 | City Planning Comments | Aff. Units | CM | Developer | Program | Current Agency | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May |  | Jun | Jul | Aug
Current 1 | 1 | Bk | HPD | Bushwick Alliance | P2017K0417 |  |  |  |  | 20 | Reynoso & Espinal | Riseboro, St. Nicks | NCP |  | Sep: Certify; Oct: 1; Nov: 2; Dec: 3; Jan: 4; Feb: 5; Mar: Approve
Current 2 | 2 | Q | EDC/DM | Beach 21st | No ZAP ID |  |  |  |  | 224 | Richards | Community Builders |  |  | Oct: 4; Nov: 5; Dec: 6; Jan: 7; Dec: 1; Jan: 2; Feb: 3; Mar: Approve
Current 3 | 3 | Bx | NYCHA | Betances VI | P2018X0138 |  |  |  |  | 101 | Ayala | Lemle & Wolff, The Bridge, Alembic | ELLA |  | Oct: Certify; Nov: 1; Dec: 2; Jan: 3; Feb: 4; Mar: Approve
Current 4 | 4 | Bk | HPD | 1921 Atlantic Ave (MWBE Site B) | P2017K0429 |  |  |  |  | 183 | Ampry-Samuel | Dabar/Thorobird | Mix and Match | [17 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
Current 5 | 5 | M | HPD | Elizabeth-Mott (Haven Green) | P2018M0251 |  |  |  |  | 121 | Chin | Pennrose, RiseBoro, Habitat, | SARA | HPD | [16 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
Current 6 | 6 | SI | HPD | Jersey Street Garage | P2016R0149 |  |  |  |  | 108 | Rose | TBD | TBD | DSNY | [14 empty] | Cert TBD |  | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
Current 7 | 7 | BX | HPD | Brook 156 | P2018X0210 |  |  |  | Brook 156 | 54 | Salamanca | Phipps | ELLA | [18 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
Current 8 | 8 | Bk | HPD | Brownsville North/Ocean Hill | P2017K0368 |  |  |  |  | 32 | Ampry-Samuel | EBC+ Mlappin+Marcal Group | NCP | [18 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
Current 9 | 9 | M | HPD | 7th Avenue TIL/ANCP | P2015M0223 |  |  |  |  | 26 | Johnson | AAFE | TBD | [19 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
Current 10 | 10 | Bk | HPD | East New York North | P2018K0116 |  |  |  |  | 41 | Espinal | EBC | NCP | [20 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
Current 11 | 11 | Bx | HPD | 784 Courtlandt Ave (MWBE Site D) | P2018X0203 |  |  |  |  | 20 | Salamanca | Infinite Horizons | NCP | [20 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
Current 12 | 12 | Bx | EDC/DM | Bronx Point UDAAP + Certification | P2018X0177 |  |  |  |  | 800 | Ayala |  |  |  | 4 | 5 | 6 | Approve | [14 empty] | Certify | 1 |  | Certify | 1 | 2 | Approve
Current 13 | 13 | M | EDC/DM | 495 Eleventh (fka Slaughterhouse) | P2017M0358 |  |  |  |  | 250 | Johnson | Radson | MIH | NYPD, HPD, DCP | [19 empty] | Certify |  | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
Current 14 | 14 | BK | HPD | 776-780 Myrtle | 2018K0468 |  |  |  |  | 59 | Cornegy | IMPACCT BK | Supportive | HPD | [21 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
Current 15 | 15 | Bk | HPD | Brownsville South | P2018K0064 |  |  |  |  | 42 | Barron | Alembic+JMR | NCP | [22 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
Current 16 | 16 | Bk | HPD | Rochester-Suydam | 2019K0234 |  |  |  |  | 76 | Cornegy & Ampry-Samuel | Jobe/Fulcrum/Briarwood | Open Door | [22 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
Current 17 | 17 | M | HPD | NME III | P2017M0377 |  |  |  |  | 67 | Perkins | HCCI, Exact, Prestige | Open Door | [15 empty] | Cert TBD | [6 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
Current 18 | 18 | Bk | HPD | 1510-1524 Broadway (MWBE Site C) | P2017K0284 |  |  |  |  | 103 | Ampry-Samuel | Macquesten | ELLA | [23 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
Current 19 | 19 | BK | HPD | 515 Blake | P2018K0333 |  |  |  |  | 556 | Barron | HELP | Supportive/ELLA | DHS/HELP (reverter) | [22 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
Current 20 | 20 | BX | HPD | Melrose NIHOP | P2018X0086 |  |  |  |  | 75 | Salamanca | MHANY | Open Door | [23 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
Current 21 | 21 | Bk | NYCHA | NYCHA 50/50 - Wyckoff | P2018K0295 |  |  |  |  | 250 | Levin | Arker/Two Trees | ELLA | [27 empty] | Certify | 1 | 2 | 3 | 4 | 5 | 6 | Approve
Current 22 | 22 | Q | EDC/DM | LIC - Waterfront + DOT site (TBD) | No ZAP ID (Amazon location) |  |  |  |  | 287 | Van Bramer | TF Cornerstone | MIH | DOT, DOE | [19 empty] | Certify |  |  | Cert TBD
Current 23 | 23 | SI | DCP | Bay St / Stapleton III / 55 Stuyvesant | P2016R0149 | [5 empty] | Rose | [6 empty] | Certify | 1 | 2 | [8 empty] | Cert TBD | [7 empty] | Cert TBD
Current 24 | 24 | M | HPD | 266 West 96 | 2018M0467 |  |  |  |  | 67 | Rosenthal | Fetner | Inclusionary | [23 empty] | Cert TBD
Current 25 | 25 | Bk | HPD | DeKalb Commons (Bed Stuy I & II NCP) | P2017K0364 |  |  |  | 84 | 85 | St. Nicks | ELLA | ELLA | [15 empty] | Cert TBD |  |  |  | Certify | 1 |  |  | Cert TBD
Current 26 | 26 | Bk | HPD | Columbia Street | P2016K0437 |  |  |  |  | 13 | Lander | Columbia St. Partners | Open Door | [15 empty] | Cert TBD | [7 empty] | Cert TBD
Current 27 | 27 | M | HPD | East Harlem NCP | 2018M0390 |  |  |  |  | 75 | Ayala | Ascendent Neighborhood (formerly Lott) | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Current 28 | 28 | Bk | HPD | Brownsville - Site A | No ZAP ID |  |  |  |  | 250 | Ampry-Samuel |  |  |  |  | Issue | [12 empty] | Cert TBD | [7 empty] | Cert TBD
Current 29 | 29 | Bk | HPD | Brownsville - Site B | 2019K0208 |  |  |  |  | 185 | Espinal |  |  |  |  | Issue | [12 empty] | Cert TBD | [7 empty] | Cert TBD
Current 30 | 30 | Bk | HPD | Brownsville - Site C | No ZAP ID |  |  |  |  | 330 | Barron |  |  |  |  | Issue | [12 empty] | Cert TBD | [7 empty] | Cert TBD
Current 31 | 31 | BK | HPD | Weeksville (NCP) | 2019K0093 |  |  |  |  | 45 | Ampry-Samuel | SHF & Beechwood | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Current 32 | 32 | M | HPD | Central Harlem I & II | P2018M0158 | P2018M0159 | P2018M0161 | P2018M0332 |  | 100 | Perkins | Lemor & IRIS | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Current 33 | 33 | BX | HPD | East Tremont (NCP) | No ZAP ID |  |  |  |  | 29 | Salamanca | SUS & Fulcrum | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Current 34 | 34 | BX | HPD | Melrose/Concourse (NCP) | No ZAP ID |  |  |  |  | 32 | Gibson | SHF & Beechwood | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Current 35 | 35 | BX | HPD | Morrisania/Claremont & Morris Heights/Univ Heights | 2019X0192 | 2019X0246 |  |  |  | 62 | Gibson & Cabrera & King | Neighborhood Infill Partner | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Current 36 | 36 | BK | HPD | Bed Stuy Central & North NIHOP | 2018K0517 |  |  |  |  | 79 | Cornegy | Shelter Rock | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Current 37 | 37 | BK | HPD | Bed Stuy East & Weeksville | No ZAP ID |  |  |  |  | 69 | Ampry-Samuel | Habitat | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Current 38 | 38 | BK | HPD | Brownsville North and South | P2017K0368 |  |  |  |  | 59 | Ampry-Samuel | FAC & Habitat | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Current 39 | 39 | BK | HPD | East New York & Brownsville (NIHOP) | No ZAP ID |  |  |  |  | 32 | Espinal | Infinite Horizons & FG-PH | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Current 40 | 40 | BK | HPD | East New York South & East (NIHOP & NCP) | No ZAP ID |  |  |  |  | 69 | Barron & Espinal | MHANY & CHLDC | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Current 41 | 41 | BK | HPD | East New York South & West (NIHOP & NCP) | No ZAP ID |  |  |  |  | 71 | Barron | Rajoy & PM Architecture | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Current 42 | 42 | QNS | HPD | South Jamaica (NCP) | No ZAP ID |  |  |  |  | 40 | Adams | Infinite Horizons & FG-PH | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Current 43 | 43 | QNS | HPD | South Jamaica (NIHOP) | No ZAP ID |  |  |  |  | 23 | Ulrich & Adams | Briarwood & Fulcrum | [13 empty] | Cert TBD |  |  | Cert TBD | [7 empty] | Cert TBD
Current 44 | 44 | Bk | HPD | Greenpoint Hospital | 2019K0177 |  |  |  |  | 300 | Reynoso |  |  |  |  | Issue | [12 empty] | Cert TBD | [7 empty] | Cert TBD
RFP / RFEI Pipeline
Pipeline 1 | 1 | M | ECF | 131 Sixth Ave | No ZAP ID | [5 empty] | Johnson | [11 empty] | Issue | [6 empty] | Select |  | Select
Pipeline 2 | 2 | Bk | NYCHA | Bushwick II Senior First | No ZAP ID |  |  |  |  | 100 | Espinal | [7 empty] | Issue | 1 | 2 | [10 empty] | Select |  |  | Select
Pipeline 3 | 3 | Bx | NYCHA | Sotomayor Senior First | No ZAP ID |  |  |  |  | 100 | Diaz | [7 empty] | Issue | 1 | 2 | [10 empty] | Select |  |  | Select
Pipeline 4 | 4 | Bk | EDC/DM | DUMBO Man Bridge Dev Rights | No ZAP ID | [5 empty] | Levin | [6 empty] | Issue | [11 empty] | Select |  |  | Select |  | Select
Pipeline 5 | 5 | Bk | HPD | Grant Avenue Muni | No ZAP ID |  |  |  |  | 100 | Espinal | [13 empty] | Issue | [8 empty] | Select | Select
Pipeline 6 | 6 | Bk | HPD | Broadway Triangle (3 sites) | No ZAP ID |  |  |  |  | 320 | Reynoso | [14 empty] | Issue | [8 empty] | Select
Pipeline 7 | 7 | Multi | HPD | Big Ideas, Small Lots Design Competiton | No ZAP ID |  |  |  |  | TBD | Various | [19 empty] | Public |  | Issue |  |  |  | Select
Pipeline 8 | 8 | Multi | EDC/DM | Life Sciences HUB RFEI & RFP | No ZAP ID |  |  |  |  | 0 | TBD | [10 empty] | Issue RFEI | [7 empty] | Issue | [7 empty] | Select
Pipeline 9 | 9 | Multi | HPD | ShareNYC (Shared Facilities) | No ZAP ID |  |  |  |  | TBD | Various | [18 empty] | Issue | Issue | [8 empty] | Select
Pipeline 10 | 10 | Q | EDC/DM | 11-24 Jackson Ave. | No ZAP ID |  |  |  |  | TBD | Van Bramer | [18 empty] | Select | [10 empty] | Select
Pipeline 11 | 11 | BX | HPD | Corporal Fischer/97 W. 169th St. | No ZAP ID |  |  |  |  | 65 | Gibson | [11 empty] | Points of Agreement to release in 2018 | [8 empty] | Issue | [8 empty] | Select
Pipeline 12 | 12 | M | NYCHA | NYCHA - La Guardia | No ZAP ID |  |  |  |  | 180 | Chin | [11 empty] | Issue | [14 empty] | ReIssue |  |  |  | 6 6 6 6 6 6 6 6 5: Select
Pipeline 13 | 13 | Bk | NYCHA | NYCHA - Cooper Park | No ZAP ID |  |  |  |  | 115 | Reynoso | [26 empty] | Issue |  |  |  | 6 6 6 6 6 6 6 6 5: Select
Pipeline 14 | 14 | M | HPD | NYPD 25th Precinct Parking Lot | No ZAP ID |  |  |  |  | 250 | Ayala | [11 empty] | Points of Agreement by Q2 of CY2019 | Points of Agreement by Q2 of CY2019 | [13 empty] | Issue |  |  |  | 6 6 6 6 6 6 6 6 6: Select
Pipeline 15 | 15 | M | HPD | HRA E. Harlem Multi-Service Center | No ZAP ID |  |  |  |  | 140 | Ayala | [11 empty] | Points of Agreement by Q2 of CY2019 | Points of Agreement by Q2 of CY2019 | [13 empty] | Issue |  |  |  | 6 6 6 6 6 6 6 6 6: Select
Pipeline 16 | 16 | Multi | NYCHA | 50/50 - 2 sites | No ZAP ID |  |  |  |  | TBD | TBD | [27 empty] | Issue |  |  | 6 6 6 6 6 6 6 6 6: Select
Pipeline 17 | 17 | Q | HPD | Astoria DOT Lot (Seniors) | No ZAP ID |  |  |  |  | TBD | Constantinides | [28 empty] | Issue
Pipeline 18 | 18 | Multi | NYCHA | 100% Affordable - 4 sites | No ZAP ID |  |  |  |  | TBD | TBD | [29 empty] | Issue | [7 empty] | Select
Pipeline 19 | 19 | Bx | HPD | Anthony Ave ACS Play Lot | No ZAP ID |  |  |  |  | 50 | Gibson | [11 empty] | Points of Agreement by Q3 of CY2019 | Points of Agreement by Q3 of CY2019 | [16 empty] | Issue | [8 empty] | Select
Pipeline 20 | 20 | Bx | HPD | Morrisania H+H Surface Lot | No ZAP ID |  |  |  |  | 180 | Gibson | [11 empty] | Points of Agreement by Q3 of CY2019 | Points of Agreement by Q3 of CY2019 | [15 empty] | Issue | Issue | [8 empty] | Select
Pipeline 21 | 21 | M | EDC/DM | Bus Depot 126th St-Cultural Operator Only | No ZAP ID |  |  |  |  | 580 | Ayala | [29 empty] | Issue | [8 empty] | Select | Select
Pipeline 22 | 22 | Bk | HPD | Fulton St Sites ( A + B - Seniors) | No ZAP ID |  |  |  |  | 300 | Ampry-Samuel | [30 empty] | 6 6 6 6 6 5 5 5 1: Issue |  |  | Select
Pipeline 23 | 23 | Bk | HPD | 516 Bergen + ENS Lot (Seniors) | No ZAP ID |  |  |  |  | TBD | Cumbo | [11 empty] | Points of Agreement | Points of Agreement | [17 empty] | 6 6 6 6 6 6 6 6 2: Tentative Issue
Pipeline 24 | 24 | Multi | HPD | MWBE RFP | [5 empty] | TBD | Various | [30 empty] | 6 6 6 6 6 6 6 6 2: Issue
Pipeline 25 | 25 | M | NYCHA | Harborview | [5 empty] | 227 | Rosenthal | [11 empty] | Select | Select | [5 empty] | Select
Pipeline 26 | 26 | SI | EDC | Seaview Healthy Community (TBD) | No ZAP ID |  |  |  |  | 400 | Matteo |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | [9 empty] | Select
Pipeline 27 | 27 | M | NYCHA | Baruch Seniors First (TBD) | No ZAP ID |  |  |  | Baruch Senior First | 100 | Rivera |  |  |  | 6: Issue | 1 | 2 | [10 empty] | Select
Pipeline 28 | 28 | Bx | HPD | 351 Powers Avenue | No ZAP ID |  |  |  |  | TBD | Ayala | [11 empty] | Points of Agreement to release in 2019 | Points of Agreement to release in 2019
Pipeline 29 | 29 | Q | HPD | Hunters Point D+E | No ZAP ID |  |  |  |  | 1020 | Van Bramer | [38 empty] | Select
Pipeline 30 | 30 | Bk | HPD | DEP - Myrtle ST | [6 empty] | Cumbo
Pipeline 31 | 31 | BX | HPD | Southern BLVD Acquisition Sites | No ZAP ID |  |  |  |  | TBD | Salamanca
Pipeline 32 | 32 | SI | EDC/DM | Stapleton North (TBD) | No ZAP ID | [5 empty] | Rose
Pipeline 33 | 33 | SI | EDC/DM | Stapleton South (TBD) | No ZAP ID | [5 empty] | Rose | [37 empty] | Select
Note on E4: Cohen, Jon: HPD had approval in May
Note on E50: Sharon Tepper: Selection moved out
Note on E54: Sharon Tepper: reinserted
Note on E56: Sharon Tepper: Selection moved out
Note on E67: Sharon Tepper: I removed the listing in the Project list above and kept here, since we have not yet released the RFP; also moved out schedule
Note on E72: Sharon Tepper: Selection moved out