## BX Housing Pipeline
Boro | CD | Map ID | Source | Project ID | Project Name | Status | Total Units (from planner) | Notes on Total/KS assumed units | KS assumed units | Units remaining (not accounted for in other sources) | Lead Planner | Request for Update | Remaining units likely to be built? | Rationale | Remaining units likely to be built by 2025? (Likely/ Uncertain/ Not likely/ No units remaining) | Remaining units likely to be built by 2035? (Likely/ Uncertain/ Not likely/ No units remaining) | Remaining units likely to be built by 2055? (Likely/ Uncertain/ Not likely/ No units remaining) | Rationale for likely to be built | Phasing (if known) | Notes | MQL View | Suggestion | Must get boro input | Response to MQL View | Portion Built 2025 | Portion Built 2035 | Portion Built 2055 | Outdated Overlapping Project | Non-Residential Project (incl. Group Quarters) | Withdrawn Project | Inactive Project | Other Reason to Omit | Corrected Existing Geometry | Corrected Existing Unit Count | Updated Unit Count | Should be in old ZAP Pull | Should be in new ZAP Pull | Planner Added Project
BX | 205 | 20 | DCP ZAP | 2018X0438 | 2009 Sedgwick Rezoning | Active; Pre-Cert | 65 |  |  | 65 | Christine Camilleri | This project has not materialized in DOB permits despite being certified before mid-2017. What is the likelihood that this project will be built by 2025? By 2035? |  |  | Uncertain | Uncertain | Uncertain | Note: This project has not certified. As the ZAP record indicates, the current status is that the submission of the first draft land use application is pending and environmental review has not begun. |  |  | Potentially conservative | Override with generic build year rules
BX | 201 | 21 | DCP ZAP | 2018X0450 | 261 Walton Avenue | Active; Pre-Cert | 176 |  |  | 176 |  | No | [8 empty] | n/a
BX | 211 | 37 | DCP ZAP | 2019R0164 | Resilient Housing and Open Space ULURP - SI | Active; Pre-Cert | 212 |  |  | 207 |  | No | [8 empty] | n/a
BX | 211 | 122 | DCP ZAP | P2012X0046 | Blondell Commons | Active; Public Review | 228 |  |  | 1 |  | No | [8 empty] | n/a
BX | 208 | 123 | DCP ZAP | P2012X0199 | 5241 Independence Avenue (LAX Residence) | Complete; Completed | 1 |  |  | 1 |  | No | [8 empty] | n/a
BX | 203 | 124 | DCP ZAP | P2012X0204 | Melrose Commons North RFP Site B | Complete; Completed | 277 |  |  | 0 |  | No | [8 empty] | n/a
BX | 209 | 125 | DCP ZAP | P2012X0215 | SOUNDVIEW PARTNERS APARTMENTS | Complete; Completed | 238 |  |  | 0 |  | No | [8 empty] | n/a
BX | 204 | 126 | DCP ZAP | P2012X0218 | 580 Gerard Avenue | Complete; Completed | 124 |  |  | 124 |  | No | [8 empty] | n/a
BX | 201 | 127 | DCP ZAP | P2012X0221 | BROOK AVENUE | Complete; Completed | 66 |  |  | 0 |  | No | [8 empty] | n/a
BX | 201 | 128 | DCP ZAP | P2012X0222 | CROSSROADS PLAZA | Complete; Completed | 428 |  |  | 102 |  | No | [8 empty] | n/a
BX | 205 | 129 | DCP ZAP | P2012X0363 | Creston Ave Residences | Complete; Completed | 66 |  |  | 0 |  | No | [8 empty] | n/a
BX | 201 | 130 | DCP ZAP | P2012X0399 | Triangle Plaza | Complete; Completed | 0 |  |  | 0 |  | No | [8 empty] | n/a
BX | 203 | 131 | DCP ZAP | P2012X0515 | Maple Mesa | Complete; Completed | 25 |  |  | 0 |  | No | [8 empty] | n/a
BX | 208 | 132 | DCP ZAP | P2012X0615 | Edward Cardinal Egan Pavilion - SNAD | Complete; Completed | 46 |  |  | 46 |  | No | [8 empty] | n/a
BX | 204 | 184 | DCP ZAP | P2013X0105 | ArtsBridge Senior Housing | Complete; Completed | 61 |  |  | 0 |  | No | [8 empty] | n/a
BX | 206 | 185 | DCP ZAP | P2013X0120 | Lambert Houses Redevelopment Master Plan | Complete; Completed | 1000 |  |  | 837 |  | No | [8 empty] | n/a
BX | 208 | 186 | DCP ZAP | P2013X0130 | Mann Residence (4450 Livingston Ave) Renewal | Active; Completed | 1 |  |  | 1 |  | No | [8 empty] | n/a
BX | 204 | 187 | DCP ZAP | P2013X0135 | Concourse Village West Rezoning | Complete; Completed | 265 |  |  | 0 |  | No | [8 empty] | n/a
BX | 208 | 188 | DCP ZAP | P2013X0187 | Hebrew Home for the Aged - Expansion | Active; Public Review | 630 |  |  | 630 |  | No | [8 empty] | n/a
BX | 208 | 189 | DCP ZAP | P2013X0348 | 4490 Fieldston Rd Subdivision - SNAD | Complete; Pre-Cert | 3 |  |  | 3 |  | No | [8 empty] | n/a
BX | 201 | 190 | DCP ZAP | P2013X0354 | La Central (Bronxchester RFP) | Complete; Completed | 992 |  |  | 550 |  | No | [8 empty] | n/a
BX | 204 | 191 | DCP ZAP | P2013X0366 | Settlement Housing Fund (1561 Walton Avenue) | Complete; Completed | 60 |  |  | 0 |  | No | [8 empty] | n/a
BX | 208 | 192 | DCP ZAP | P2013X0399 | Sisters of Charity Gate House Expansion - SNAD | Complete; Completed | 3 |  |  | 3 |  | No | [8 empty] | n/a
BX | 208 | 193 | DCP ZAP | P2013X0407 | 6033 Huxley Ave | Complete; Completed | 2 |  |  | 2 |  | No | [8 empty] | n/a
BX | 201 | 296 | DCP ZAP | P2014X0051 | 285 E 138th - Tres Puentes | Complete; Completed | 178 |  |  | 3 |  | No | [8 empty] | n/a
BX | 210 | 297 | DCP ZAP | P2014X0071 | Co-Op City Senior Housing Renewal | Complete; Completed | 183 |  |  |  | Dana Driskell | How many residential units do we expect this project to introduce? | [8 empty] | n/a
BX | 211 | 298 | DCP ZAP | P2014X0121 | 1776 Eastchester Road - Montefiore Staff Housing | Complete; Completed | 182 |  |  | 182 | Michael Kavalar | This project has not materialized in DOB permits despite being certified before mid-2017. What is the likelihood that this project will be built by 2025? By 2035? | Likely |  | Likely | n/a | n/a | Permit has already been issue, but no signs of construction; may be awaiting completion of Bronx Metro-North study |  |  | Project may need to be removed | Check for DOB permit |  | No permit has been issued in the developments data. | 1 | 0 | 0
BX | 201 | 299 | DCP ZAP | P2014X0154 | 861 Eagle Ave Rezoning | On-Hold; Pre-Cert | 78 |  |  | 78 | Michael Kavalar | In mid-year 2018, you had provided feedback that this project was UNCERTAIN to be built by 2025. Is this still the case? If not, what is the likelihood that this project will be built by 2025? By 2035? | Uncertain | On-hold since Jan 2018, applicant resolving financing issues | Not likely | n/a | n/a | Applicant not proceeding with application. |  |  | Potentially conservative | Include in 2055 |  |  | 0 | 0 | 1
BX | 201 | 300 | DCP ZAP | P2014X0401 | Willow Avenue Rezoning | Complete; Completed | 126 |  |  | 126 |  | No | [8 empty] | n/a
BX | 203 | 301 | DCP ZAP | P2014X0459 | New Roads Plaza | Complete; Completed | 94 |  |  | 0 |  | No | [8 empty] | n/a
BX | 206 | 302 | DCP ZAP | P2014X0534 | 1932 Bryant Avenue | Complete; Completed | 327 |  |  | 8 |  | No | [8 empty] | n/a
BX | 209 | 373 | DCP ZAP | P2015X0048 | Seward Avenue Rezoning | Active; Pre-Cert | 714 |  |  | 714 |  | No | [8 empty] | n/a
BX | 212 | 374 | DCP ZAP | P2015X0205 | 241st Street Rezoning | Active; Public Review | 186 |  |  | 186 |  | No | [8 empty] | n/a
BX | 208 | 375 | DCP ZAP | P2015X0217 | 4611 Arlington Ave - Heavey Residence - SNAD Cert | Complete; Completed | 4 |  |  | 4 |  | No | [8 empty] | n/a
BX | 201 | 376 | DCP ZAP | P2015X0275 | 147th Street Rezoning | Complete; Completed | 165 |  |  | 0 |  | No | [8 empty] | n/a
BX | 209 | 377 | DCP ZAP | P2015X0285 | Watson Avenue Rezoning | Complete; Completed | 286 |  |  | 0 |  | No | [8 empty] | n/a
BX | 209 | 378 | DCP ZAP | P2015X0380 | Westchester Mews - Rezoning | Complete; Completed | 206 |  |  | 0 |  | No | [8 empty] | n/a
BX | 210 | 379 | DCP ZAP | P2015X0433 | William Ave Development - City Island | Complete; Completed | 10 |  |  | 10 |  | No | [8 empty] | n/a
BX | 211 | 380 | DCP ZAP | P2015X0460 | 1601 Bronxdale Avenue II | On-Hold; Pre-Cert | 907 |  |  | 907 |  | No |  |  |  | likely |  | Rezoning M1-1 to R7A |  |  | Realistic |  |  |  | 0 | 1 | 0
BX | 211 | 381 | DCP ZAP | P2015X0544 | Williamsbridge Road Rezoning | Active; Public Review | 35 |  |  | 35 |  | No | [8 empty] | n/a
BX | 206 | 442 | DCP ZAP | P2016X0079 | Belmont Cove - Rezoning | Active; Public Review | 158 |  |  | 0 | Tawkiyah Jordan | In mid-year 2018, you had provided feedback that this project was UNCERTAIN to be built by 2025. Is this still the case? If not, what is the likelihood that this project will be built by 2025? By 2035? | Uncertain | On-hold since Oct 2017 | 158 | No units remaining | No units remaining | DCP actions approved/completed in March 2019 |  |  | Realistic |  |  |  | 1 | 0 | 0
BX | 201 | 443 | DCP ZAP | P2016X0084 | 600 E 156th Street - Rezoning | Complete; Completed | 175 |  |  | 0 |  | No | [8 empty] | n/a
BX | 209 | 444 | DCP ZAP | P2016X0085 | 1675 Westchester Avenue - Rezoning | Complete; Completed | 220 |  |  | 0 |  | No | [8 empty] | n/a
BX | 201 | 445 | DCP ZAP | P2016X0102 | 101 Lincoln Avenue | Complete; Completed | 771 |  |  | 0 | Susanna Castiello | In mid-year 2018, you had provided feedback that this project was UNCERTAIN to be built by 2025. Is this still the case? If not, what is the likelihood that this project will be built by 2025? By 2035? | Uncertain | Lot changed hands, no longer controlled by applicant | 0 | 771 | No units remaining | Change of ownership could delay construction |  |  | Realistic |  |  |  | 0 | 1 | 0
BX | 202 | 446 | DCP ZAP | P2016X0167 | Whitlock and 165th Street - Rezoning | Complete; Completed | 474 |  |  | 0 |  | No | [8 empty] | n/a
BX | 208 | 447 | DCP ZAP | P2016X0219 | Delafield - New Site Plan (2016) SNAD | Active; Pre-Cert | 34 |  |  | 34 |  | No | [8 empty] | n/a
BX | 201 | 448 | DCP ZAP | P2016X0258 | 198 East 135th Street - Waterfront Chair Cert | Complete; Completed | 464 |  |  | 37 |  | No | [8 empty] | n/a
BX | 209 | 449 | DCP ZAP | P2016X0337 | 1965 Lafayette Avenue | Complete; Completed | 425 |  |  | 425 | Juton Horstman | This project has not materialized in DOB permits despite being certified before mid-2017. What is the likelihood that this project will be built by 2025? By 2035? | Likely |  | likely - all 425 | n/a | n/a | David Karnovsky told me they were going to start building soon, that was in fall 2018 |  |  | Realistic |  |  |  | 1 | 0 | 0
BX | 204 | 450 | DCP ZAP | P2016X0366 | 1099 Webster Avenue - Rezoning | Active; Pre-Cert | 238 |  |  | 238 |  | No | [8 empty] | n/a
BX | 204 | 451 | DCP ZAP | P2016X0409 | Lower Concourse North Rezoning | Complete; Completed | 1045 |  |  | 0 |  | No | [8 empty] | n/a
BX | 201 | 452 | DCP ZAP | P2016X0435 | 425 Grand Concourse - Former PS 31 | Complete; Completed | 277 |  |  | 0 |  | No | [8 empty] | n/a
BX | 209 | 453 | DCP ZAP | P2016X0450 | 909 Castle Hill Avenue | Active; Pre-Cert | 31 |  |  | 31 |  | No | [8 empty] | n/a
BX | 202 | 508 | DCP ZAP | P2017X0037 | Spofford Campus Redevelopment LSGD | Active; Completed | 740 |  |  | 0 |  | No | [8 empty] | n/a
BX | 209 | 509 | DCP ZAP | P2017X0073 | Stevenson Commons | Active; Pre-Cert | 677 |  |  | 677 | Christine Camilleri | No | [8 empty] | n/a
BX | 208 | 510 | DCP ZAP | P2017X0102 | 4490 Fieldston Rd Lot 1 - SNAD | Complete; Completed | 1 |  |  | 1 |  | No | [8 empty] | n/a
BX | 208 | 511 | DCP ZAP | P2017X0103 | 4490 Fieldston Rd Lot 2 - SNAD | Complete; Completed | 1 |  |  | 1 |  | No | [8 empty] | n/a
BX | 212 | 512 | DCP ZAP | P2017X0149 | Wakefield Village | On-Hold; Pre-Pas | 1300 |  |  | 1300 |  | No | [8 empty] | n/a
BX | 208 | 513 | DCP ZAP | P2017X0222 | 5235 Broadway | On-Hold; Pre-Cert | 142 |  |  | 142 |  | No | [8 empty] | n/a
BX | 212 | 514 | DCP ZAP | P2017X0270 | 695 East Gun Hill Road Rezoning | On-Hold; Pre-Cert | 87 |  |  | 87 | Lauren Harrison | In mid-year 2018, you had provided feedback that this project was UNCERTAIN to be built by 2025. Is this still the case? If not, what is the likelihood that this project will be built by 2025? By 2035? | Uncertain | On-hold since Aug 2017, applicant talking to HPD | Not likely | Uncertain | Uncertain | Applicant was looking to get HPD financing, hasn’t contacted us since mid 2018 |  |  | Potentially conservative | Override with generic build year rules
BX | 203 | 515 | DCP ZAP | P2017X0271 | 1490 Southern Blvd | Complete; Completed | 114 |  |  | 0 |  | No | [8 empty] | n/a
BX | 206 | 516 | DCP ZAP | P2017X0311 | St Josephs - 1949 Bathgate Avenue | Active; Pre-Cert | 296 |  |  | 0 | Lauren Harrison | How many residential units do we expect this project to introduce? |  |  | 296 | No units remaining | No units remaining | Currently reviewing RWCDS |  |  | Realistic |  |  |  | 1 | 0 | 0
BX | 201 | 517 | DCP ZAP | P2017X0312 | Our Lady of Pity - 272 East 151st Street Rezoning | Active; Pre-Cert | 212 |  |  | 212 | Oscar Oliver-Didier | How many residential units do we expect this project to introduce? | [8 empty] | n/a
BX | 207 | 518 | DCP ZAP | P2017X0332 | NYBG Webster Ave FRESH | On-Hold; Pre-Cert | 381 |  |  | 381 |  | No | [8 empty] | n/a
BX | 209 | 519 | DCP ZAP | P2017X0345 | 2069 Bruckner Blvd 2 | Active; Pre-Cert | 342 |  |  | 342 |  | No | [8 empty] | n/a
BX | 206 | 568 | DCP ZAP | P2018X0001 | East Tremont Ave Rezoning | On-Hold; Pre-Cert | 118 |  |  | 118 |  | No | [8 empty] | n/a
BX | 206 | 569 | DCP ZAP | P2018X0084 | 4697 Third Avenue UDAAP | Active; Public Review | 52 |  |  | 0 | Tawkiyah Jordan | In mid-year 2018, you had provided feedback that this project was UNCERTAIN to be built by 2025. Is this still the case? If not, what is the likelihood that this project will be built by 2025? By 2035? | Uncertain | On-hold since Nov 2017 | 52 | No units remaining | No units remaining | DCP actions completed Nov 2018 |  |  | Realistic |  |  |  | 1 | 0 | 0
BX | 201 | 570 | DCP ZAP | P2018X0086 | Melrose NIHOP 1 | On-Hold; Pre-Cert | 28 |  |  | 28 |  | No | [8 empty] | n/a
BX | 203 | 571 | DCP ZAP | P2018X0087 | Melrose NIHOP 2 | On-Hold; Pre-Cert | 43 |  |  | 43 |  | No | [8 empty] | n/a
BX | 201 | 572 | DCP ZAP | P2018X0138 | Betances VI | Active; Public Review | 101 |  |  | 0 |  | No | [8 empty] | n/a
BX | 201 | 573 | DCP ZAP | P2018X0163 | Park Haven FRESH | On-Hold; Pre-Cert | 169 |  |  | 0 |  | No | [8 empty] | n/a
BX | 212 | 574 | DCP ZAP | P2018X0181 | 3900 Webster Avenue | On-Hold; Pre-Pas | 440 |  |  | 440 |  | No | [8 empty] | n/a
BX | 201 | 575 | DCP ZAP | P2018X0203 | 784 Courtlandt Avenue | Active; Pre-Cert | 20 |  |  | 0 |  | No | [8 empty] | n/a
BX | 201 | 576 | DCP ZAP | P2018X0206 | 599 Courtlandt Avenue | Complete; Completed | 8 |  |  | 0 |  | No | [8 empty] | n/a
BX | 201 | 577 | DCP ZAP | P2018X0209 | 431 Concord Avenue | Active; Pre-Cert | 78 |  |  | 78 | Lauren Harrison | In mid-year 2018, you had provided feedback that this project was UNCERTAIN to be built by 2025. Is this still the case? If not, what is the likelihood that this project will be built by 2025? By 2035? | Uncertain | Too early stage in DCP process, applicant has not submitted a Pre-Application Statement | 78 | No units remaining | No units remaining | Currently reviewing RWCDS |  |  | Realistic |  |  |  | 1 | 0 | 0
BX | 201 | 578 | DCP ZAP | P2018X0210 | Brook 156 | Active; Public Review | 55 |  |  | 0 |  | No | [8 empty] | n/a
BX | 208 | 579 | DCP ZAP | P2018X0242 | College of Mt St Vincent - New Building - SNAD | Complete; Completed | 0 |  |  |  | James Rather | How many residential units do we expect this project to introduce? | [8 empty] | n/a
BX | 203 | 580 | DCP ZAP | P2018X0270 | 893 Eagle Avenue Rezoning | Active; Pre-Cert | 88 |  |  | 88 |  | No | [8 empty] | n/a
BX | 206 | 581 | DCP ZAP | P2018X0337 | 425-439 Devoe Avenue | Active; Pre-Cert | 150 |  |  | 150 |  | No | [8 empty] | n/a
BX | 202 | 14200 | EDC | 3 | Spofford Campus Redevelopment LSGD |  | 777 |  |  | 573 |  | No | [8 empty] | n/a
BX | 204 | 14201 | EDC | 4 | Bronx Point |  | 1045 |  |  | 355 |  | No | [8 empty] | n/a
BX | 204 | 14719 | HPD RFP | 103 | Lower Concourse North RFEI - EDC | RFP | [5 empty] | No | [8 empty] | n/a
BX | 205 | 14728 | HPD RFP | 111 | NYCHA Twin Parks | RFP | [5 empty] | No | [8 empty] | n/a
BX | 201 | 14731 | HPD RFP | 114 | NYCHA Betances V and VI | RFP | [5 empty] | No | [8 empty] | n/a
BX | 201 | 14745 | HPD RFP | 127 | MWBE Site D - 359 E. 157th Street | RFP | [5 empty] | No | [8 empty] | n/a
BX | 203 | 14753 | HPD RFP | 134 | NYCHA Morrisania Air Rights | RFP | [5 empty] | No | [8 empty] | n/a
BX | 201 | 14762 | HPD RFP | 18 | MWBE Site D - 359 E. 157th Street | RFP | [5 empty] | No | [8 empty] | n/a
BX | 205 | 14775 | HPD RFP | 3 | NYCHA Twin Parks | RFP | [5 empty] | No | [8 empty] | n/a
BX | 201 | 14779 | HPD RFP | 33 | NYCHA Betances V and VI | RFP | [5 empty] | No | [8 empty] | n/a
BX | 201 | 14802 | HPD RFP | 54 | NYCHA Betances V and VI | RFP | [5 empty] | No | [8 empty] | n/a
BX | 202 | 14804 | HPD RFP | 56 | Spofford RFEI (EDC) | RFP | [5 empty] | No | [8 empty] | n/a
BX | 209 | 14811 | HPD RFP | 62 | NYCHA Senior -Sotomayor | RFP | [5 empty] | No | [8 empty] | n/a
BX | 203 | 14833 | HPD RFP | 82 | MWBE Site E - 1490 Southern Blvd | RFP | [5 empty] | No | [8 empty] | n/a
BX | 205 | 14836 | HPD RFP | 85 | NYCHA Twin Parks | RFP | [5 empty] | No | [8 empty] | n/a
BX | 204 | 14882 | Neighborhood Study | 1337 Jerome Avenue JEROME REZONING COMMITMENT | 1337 Jerome Avenue JEROME REZONING COMMITMENT |  | 0 | [7 empty] | 0 |  |  | City commitment |  |  | Realistic |  |  | Still need input on the size of this project. Otherwise, we must omit it? | 1 | 0 | 0
BX | 204 | 14904 | Neighborhood Study | 1640-1642 Anthony Avenue JEROME REZONING COMMITMENT | 1640-1642 Anthony Avenue JEROME REZONING COMMITMENT |  | 50 | [7 empty] | 50 |  |  | City commitment |  |  | Realistic |  |  |  | 1 | 0 | 0
BX | 205 | 14905 | Neighborhood Study | 1647 Popham Avenue JEROME REZONING COMMITMENT | 1647 Popham Avenue JEROME REZONING COMMITMENT |  | 29 | [7 empty] | 29 |  |  | City commitment |  |  | Realistic |  |  |  | 1 | 0 | 0
BX | 204 | 15177 | Neighborhood Study | 97 West 169th Street JEROME REZONING COMMITMENT | 97 West 169th Street JEROME REZONING COMMITMENT |  | 50 | [7 empty] | 50 |  |  | City commitment |  |  | Realistic |  |  |  | 1 | 0 | 0
BX | 204 | 15340 | Neighborhood Study | Morrisania Diagnostic and Treatment Center Surface Lot JEROME REZONING COMMITMENT | Morrisania Diagnostic and Treatment Center Surface Lot JEROME REZONING COMMITMENT |  | 180 | [7 empty] | 180 |  |  | City commitment |  |  | Realistic |  |  |  | 1 | 0 | 0
BX |  | n/a | City Hall public sites list | Current 33 | East Tremont (NCP) | Current RFP |  | ? |  |  |  | Does BXO have more info on where this HPD RFP is located & total units? If so, please provide BBL & # of units. It's in Salamanca's district. Developer is SUS & Fulcrum. Estimated to be 29 affordable units - total units unknown. | [8 empty] | Project not counted | Ignore bc clusters | [9 empty] | 1
BX |  | n/a | City Hall public sites list | Current 34 | Melrose/Concourse (NCP) | Current RFP |  | ? |  |  |  | Does BXO have more info on where this HPD RFP is located & total units? If so, please provide BBL & # of units. It's in Gibson's district. Developer is SHF & Beechwood. Estimated to be 32 affordable units - total units unknown. | [8 empty] | Project not counted | Ignore bc clusters | [9 empty] | 1
BX |  | n/a | City Hall public sites list | Current 35 | Morrisania/Claremont & Morris Heights/Univ Heights | Current RFP |  | ? |  |  |  | Does BXO have more info on where this HPD RFP is located & total units? If so, please provide BBL & # of units. It's in Gibson, Cabrera, and King's districts. Developer is Neighborhood Infill Partner. Estimated to be 62 affordable units - total units unknown. | [8 empty] | Project may need to be removed | Already in ZAP |  | Agreed. The Public Sites spreadsheet indicates this. | [7 empty] | 1
BX | 204 | n/a | City Hall public sites list | Pipeline 11 | Corporal Fischer/97 W. 169th St. | Pipeline RFP/RFEI | [5 empty] | Does BXO have more info on where this HPD planned RFP/RFEI is located & total units? If so, please provide BBL & # of units. It's in Gibson's district. Estimated to be 65 affordable units - total units unknown.Not sure where the 62 comes from- latest we have is ~50. All will be affordable. This is redundant with 97 WEst 169th (row 99 above) | [8 empty] | Project removed | [10 empty] | 1
BX | 204 | n/a | City Hall public sites list | Pipeline 19 | Anthony Ave ACS Play Lot | Pipeline RFP/RFEI |  |  |  | 0 |  | Does BXO have more info on where this HPD planned RFP/RFEI is located & total units? If so, please provide BBL & # of units. It's in Gibson's district. Estimated to be 50 affordable units - total units unknown. All will be affordable, ~50 total. This is redundant with row 97 above | [5 empty] | redundant project |  |  | Project removed | [10 empty] | 1
BX | 204 | n/a | City Hall public sites list | Pipeline 20 | Morrisania H+H Surface Lot | Pipeline RFP/RFEI |  |  |  | 0 |  | Does BXO have more info on where this HPD planned RFP/RFEI is located & total units? If so, please provide BBL & # of units. It's in Gibson's district. Estimated to be 180 affordable units - total units unknown. All will be affordable. Redundant with row 100 above | [5 empty] | redundant project |  |  | Project removed | [10 empty] | 1
BX | 201 | ? | City Hall public sites list | Pipeline 28 | 351 Powers Avenue | Pipeline RFP/RFEI |  | ? | 203 units (84443 sqft * 2.43 FAR) |  |  | Does BXO have more info on total residential units for this HPD planned RFP/RFEI? I (MIchael P) don't have additional info on these or other potential RFP sites, but happy to work w/ HEIP to engage BX HPD, if helpful | [8 empty] | Uncertain | Project units using PLUTO and count in 2035 |  |  | 0 | 1 | 0
BX |  | n/a | City Hall public sites list | Pipeline 31 | Southern BLVD Acquisition Sites | Pipeline RFP/RFEI |  | ? |  |  |  | Does BXO have more info on where this HPD planned RFP/RFEI is located & total units? If so, please provide BBL & # of units. It's in Salamanca's district These sites would have been accounted for elsewhere- MP to doublecheck with JL | [8 empty] | Project not counted | Treat as normal soft sites | [9 empty] | 1
BX | 211 | 85200 | BXO | 4440-16 & 30 | 2560 Boston Road | Pre-PAS | 330 |  |  |  | James Rather |  |  |  | 330 | ? | ? |  |  |  | Potentially aggressive | Override with generic build year rules |  | This project is in the new ZAP pull. | [12 empty] | 1 | 1
BX | 211 | 85201 | BXO | 4439-20 | 2550 Boston Road | Pre-PAS | 80 |  |  |  | James Rather |  |  |  | 80 | ? | ? |  |  |  | Potentially aggressive | Override with generic build year rules | [15 empty] | 1
BX | 203 | 85202 | BXO | 2965-6,7,8,13 | Southern Blvd Study Pipeline RFP/RFEI | Pipeline RFP/RFEI, awaiting Southern Blvd Study |  | TBD | 80 units (23290 sqft * 3.44 FAR) |  | Justin Lamorella | Part of Southern Blvd Neighborhood Study; owned by HPD |  |  | ? | ? | ? |  |  |  | No inputs given | Include in 2035 |  |  | 0 | 1 | 0 | [10 empty] | 1
BX | 203 | 85203 | BXO | 2758-14 | 1174 LONGFELLOW AVENUE | Awaiting Southern Blvd Study |  | TBD | 82 units (23795 sqft * 3.44 FAR) |  | Justin Lamorella | Part of Southern Blvd Neighborhood Study. project R7 zoning district; owned by EDC |  |  | ? | ? | ? |  |  |  | No inputs given | Include in 2035 |  |  | 0 | 1 | 0 | [10 empty] | 1
BX | 203 | 85204 | BXO | 3006-17,19,21 | 1051 Home Street (and adjacent lots) | Awaiting Southern Blvd Study |  | TBD | 57 units (16705 sqft * 3.44 FAR) |  | Justin Lamorella | Part of Southern Blvd Neighborhood Study. project R7 zoning district; owned by EDC |  |  | ? | ? | ? |  |  |  | No inputs given | Include in 2035 |  |  | 0 | 1 | 0 | [10 empty] | 1
BX | 201 | 85205 | BXO | 2666-56,58,59,60,61,66 | 815 Westchester | PAS filed | 188 |  |  |  | Justin Lamorella |  |  |  | ? | ? | ? |  |  |  | No inputs given | Override with generic build year rules | [15 empty] | 1
BX | 205 |  | BXO | 2861-35 | 1665 Jerome Avenue | Plans filed with DOB years ago. Flagging here because these would have been filed as a community facility and may not be included in DOB permit pulls | 71 |  |  | 71 | Michael Parkinson |  |  | There have been plans in the works for this site going back to 2012, but have never materialized. New plans will filed in 2016, but still no work. | 0 | 71 | 0 | Not confident these units will come on line in the near-term, but given interest in the site, assuming units may come on line by 2035 |  | KS: This is in DOB | Uncertain | Planner input different from KS? | [9 empty] | 1 | [5 empty] | 1
BX | 210 | 85206 | BXO |  | 2500 Westchester Avenue | N/A | 200 | Planner Input: ~200 |  |  |  | This is an as-of-right project that does not require CPC approvals but was discussed at a CD 10 meeting. It is an affordable residential development to be constructed on the open space belonging to St. Peter's Church. The developer was selected through an HPD RFP process. | [8 empty] | Project may need to be removed | Check if overlap with HPD pre-closings or HPD RFPs |  | No overlap. Keep project. | [13 empty] | 1
BX | 207 | 85207 | map |  | 3201 JEROME AVENUE (and adjacent lots) |  | 300 | [8 empty] | likely |  |  |  |  | Uncertain | Any more context? |  |  | 0 | 1 | 0 | [10 empty] | 1
BX | 212 | 85208 | map |  | 1824 ALLERTON AVENUE (half of site) |  |  | assume R7A | 1913 units (478238 sqft * 4 FAR) | [6 empty] | uncertain |  |  |  |  | Uncertain | Any more context? |  |  | 0 | 0.5 | 0.5 | [10 empty] | 1
BX |  | 85209 | map |  | 940 SOUTHERN BOULEVARD |  |  | assume R8A | 367 units (60969 sqft * 6.02 FAR) | [6 empty] | uncertain |  |  |  |  | Uncertain | Any more context? |  |  | 0 | 0.5 | 0.5 | [10 empty] | 1