## BK Housing Pipeline
Boro | CD | Map ID | Source | Project ID | Project Name | Status | Total Units (from planner) | Notes on Total/KS assumed units | KS assumed units | Units remaining (not accounted for in other sources) | Lead Planner | Request for Update | Remaining units likely to be built? | Rationale | Remaining units likely to be built by 2025? (Likely/ Uncertain/ Not likely/ No units remaining) | Remaining units likely to be built by 2035? (Likely/ Uncertain/ Not likely/ No units remaining) | Remaining units likely to be built by 2055? (Likely/ Uncertain/ Not likely/ No units remaining) | Rationale for likely to be built | Phasing (if known) | Notes | MQL View | Suggestion | Must get boro input | Response to MQL View | Portion Built 2025 | Portion Built 2035 | Portion Built 2055 | Outdated Overlapping Project | Non-Residential Project (incl. Group Quarters) | Withdrawn Project | Inactive Project | Other Reason to Omit | Corrected Existing Geometry | Corrected Existing Unit Count | Updated Unit Count | Should be in old ZAP Pull | Should be in new ZAP Pull | Planner Added Project
BK | 301 | 4 | DCP ZAP | 2018K0376 | 77 Commercial Street Special Permit Renewal | Active; Pre-Cert | 720 |  |  | 720 |  | No | [8 empty] | n/a
BK | 301 | 30 | DCP ZAP | 2019K0211 | Bedford Ave Overlay Extension | Active; Pre-Cert | 2 |  |  | 2 |  | No | [8 empty] | n/a
BK | 301 | 45 | DCP ZAP | P2012K0069 | 59 Walton Street | Complete; Completed | 326 |  |  | 151 |  | No | [8 empty] | n/a
BK | 301 | 47 | DCP ZAP | P2012K0087 | 209-231 McGuinness Blvd | Complete; Completed | 141 |  |  | 0 |  | No | [8 empty] | n/a
BK | 301 | 48 | DCP ZAP | P2012K0103 | KEDEM WINERY SPECIAL PERMIT RENEWAL | Complete; Completed | 450 |  |  | 0 |  | No | [8 empty] | n/a
BK | 301 | 49 | DCP ZAP | P2012K0153 | 74 WALLABOUT STREET REZONING | Complete; Completed | 120 |  |  | 21 |  | No | [8 empty] | n/a
BK | 301 | 50 | DCP ZAP | P2012K0231 | GREENPOINT LANDING | Complete; Completed | 707 |  |  | 0 |  | No | [8 empty] | n/a
BK | 301 | 133 | DCP ZAP | P2013K0179 | Domino Sugar | Complete; Completed | 2822 |  |  | 2300 |  | No | [8 empty] | n/a
BK | 301 | 137 | DCP ZAP | P2013K0352 | 75 Greene Street | Complete; Completed | 64 |  |  | 4 |  | No | [8 empty] | n/a
BK | 301 | 139 | DCP ZAP | P2013K0410 | 155 West Street | Complete; Completed | 600 |  |  | 460 |  | No | [8 empty] | n/a
BK | 301 | 140 | DCP ZAP | P2013K0500 | 251 Front Street (2014) | Complete; Completed | 48 |  |  | 6 |  | No | [8 empty] | n/a
BK | 301 | 199 | DCP ZAP | P2014K0153 | LPC Warehouse | Complete; Completed | 55 |  |  | 0 |  | No | [8 empty] | n/a
BK | 301 | 203 | DCP ZAP | P2014K0304 | 695 Grand Street | Complete; Completed | 51 |  |  | 0 |  | No | [8 empty] | n/a
BK | 301 | 204 | DCP ZAP | P2014K0438 | 27-41 West Street | Complete; Completed | 1925 |  |  | 967 | Karensa Wood | This project was certified before 2017, but at least the majority of it has not yet materialized. Do you expect the rest of this project to materialize, and do you expect a change in total unit count or phasing? |  |  | 25% | 100% |  | Construction has not yet started on 27-41 West. By 2025, we may see a quarter of the buildings built, all units built by 2035. |  |  | Realistic |  |  |  | 0.25 | 0.75 | 0
BK | 301 | 210 | DCP ZAP | P2014K0530 | 13-15 Greenpoint Avenue | Complete; Completed | 77 |  |  | 0 | Jonah Rogoff |  | likely | Existing use still in place | likely | [5 empty] | Project not counted | Check for DOB match |  | Matches with 80-unit DOB project. No need to apply rules.
BK | 301 | 459 | DCP ZAP | P2017K0205 | 226 Franklin Street (Chair Cert 15-30) | Complete; Completed | 41 |  |  | 2 |  | No | [8 empty] | n/a
BK | 301 | 460 | DCP ZAP | P2017K0206 | 151 Kent Avenue (chair cert 15-30) | On-Hold; Pre-Cert | 46 |  |  | 0 |  | No | [8 empty] | n/a
BK | 301 | 465 | DCP ZAP | P2017K0283 | Rose Plaza – 470 Kent Avenue | Complete; Completed | 801 |  |  | 801 | Syed Ahmed | In mid-year 2018, you had provided feedback that this project was UNCERTAIN to be built by 2025. Is this still the case? If not, what is the likelihood that this project will be built by 2025? By 2035? | Uncertain | 2nd special permit renewal will expire, will need to come back for approvals again | likely |  |  | ( Lets call this project Rose Plaza – 470 Kent Avenue and remove the 2nd SP Renewal): Considering the site just got sold for approximately $ 185 million, the investors won’t sit too long on that property. I believe once the construction is under way all of it will be done within 24 months. So my view is that all of the units will be on the market by 2025. |  |  | Potentially aggressive | Check if this requires ULURP and what milestone reached by Rose Plaza 470 Kent (currently showing the status for 470 Kent 2nd SP Renewal). If ULURP - apply generic build year rules. If non-ULURP stick to 2025 |  | Non-ULURP. The project status is complete. Will replace the name of the project with the planner's title. | 1 | 0 | 0
BK | 301 | 520 | DCP ZAP | P2018K0031 | 824 Metropolitan Avenue | Active; Pre-Cert | 36 |  |  |  | Syed Ahmed | How many residential units do we expect this project to introduce? | Uncertain | Too early stage in DCP process, applicant has not submitted a Pre-Application Statement | likely |  |  | The projected number of units are 36. The proposed rezoning is in its initial stages. If the rezoning is approved by 2020, then it is likely that the site will be developed by 2025 and all 36 units will be on line. |  |  | Realistic |  |  |  | 1 | 0 | 0
BK | 301 | 14715 | HPD RFP | 10 | Broadway Triangle - Site C | RFP | [5 empty] | No | [8 empty] | n/a
BK | 301 | 14718 | HPD RFP | 102 | Broadway Triangle - Site A | RFP | [5 empty] | No | [8 empty] | n/a
BK | 301 | 14720 | HPD RFP | 104 | Broadway Triangle - Site B | RFP | [5 empty] | No | [8 empty] | n/a
BK | 301 | 14736 | HPD RFP | 119 | Broadway Triangle - Site B | RFP | [5 empty] | No | [8 empty] | n/a
BK | 301 | 14746 | HPD RFP | 128 | Broadway Triangle - Site C | RFP | [5 empty] | No | [8 empty] | n/a
BK | 301 | 14751 | HPD RFP | 132 | Broadway Triangle - Site A | RFP | [5 empty] | No | [8 empty] | n/a
BK | 301 | 14761 | HPD RFP | 17 | Broadway Triangle - Site B | RFP | [5 empty] | No | [8 empty] | n/a
BK | 301 | 14763 | HPD RFP | 19 | Broadway Triangle - Site B | RFP | [5 empty] | No | [8 empty] | n/a
BK | 301 | 14765 | HPD RFP | 20 | Broadway Triangle - Site C | RFP | [5 empty] | No | [8 empty] | n/a
BK | 301 | 14773 | HPD RFP | 28 | Broadway Triangle - Site A | RFP | [5 empty] | No | [8 empty] | n/a
BK | 301 | 14786 | HPD RFP | 4 | Broadway Triangle - Site C | RFP | [5 empty] | No | [8 empty] | n/a
BK | 301 | 14788 | HPD RFP | 41 | Broadway Triangle - Site C | RFP | [5 empty] | No | [8 empty] | n/a
BK | 301 | 14798 | HPD RFP | 50 | Broadway Triangle - Site B | RFP | [5 empty] | No | [8 empty] | n/a
BK | 301 | 14803 | HPD RFP | 55 | Broadway Triangle - Site A | RFP | [5 empty] | No | [8 empty] | n/a
BK | 301 | 14809 | HPD RFP | 60 | Broadway Triangle - Site A | RFP | [5 empty] | No | [8 empty] | n/a
BK | 301 | 14817 | HPD RFP | 68 | Broadway Triangle - Site B | RFP | [5 empty] | No | [8 empty] | n/a
BK | 301 | 14822 | HPD RFP | 72 | Broadway Triangle - Site B | RFP | [5 empty] | No | [8 empty] | n/a
BK | 301 | 14823 | HPD RFP | 73 | Broadway Triangle - Site C | RFP | [5 empty] | No | [8 empty] | n/a
BK | 301 | 14832 | HPD RFP | 81 | Broadway Triangle - Site B | RFP | [5 empty] | No | [8 empty] | n/a
BK | 301 | 14839 | HPD RFP | 88 | Broadway Triangle - Site C | RFP | [5 empty] | No | [8 empty] | n/a
BK | 301 | 14840 | HPD RFP | 89 | Broadway Triangle - Site C | RFP | [5 empty] | No | [8 empty] | n/a
BK | 301 | 14841 | HPD RFP | 9 | Broadway Triangle - Site C | RFP | [5 empty] | No | [8 empty] | n/a
BK | 301 | 14847 | HPD RFP | 95 | Broadway Triangle - Site A | RFP | [5 empty] | No | [8 empty] | n/a
BK | 301 | 14850 | HPD RFP | 98 | Broadway Triangle - Site B | RFP | [5 empty] | No | [8 empty] | n/a
BK | 301 | 85339 | map |  | Greenpoint Landing (inclusive area, to override other polygons) | approved | 5500 | [7 empty] | likely | [5 empty] | Project may need to be removed | Check if fully built out. Otherwise all 2025 |  | Approximately 20% built out. Is another 4,800 units built by 2025 actually realistic? | 1 | 0 | 0 | [10 empty] | 1
BK | 301 | 85340 | map |  | 1 Huron St | draft for waterfront cert | 173 | [7 empty] | likely | [5 empty] | Realistic |  |  |  | 1 | 0 | 0 | [10 empty] | 1
BK | 301 | 85341 | map |  | Greenpoint Terminal Market |  | 2250 | [7 empty] | 500 units | 1500 units | all units | we don’t have a proposed unit count yet, but for planning purposes could assume 2250 units. We don’t have unit counts for each phase of the project yet, but for planning purposes could assume 500 units by 2025, 1500 units by 2035, all by 2055. |  |  | Potentially aggressive | Check which milestone reached and if DCP target cert date is set |  | No DCP target cert date yet. Project is on-hold. Moving all to 2055. Moving 500 units planner suggested in 2025 to 2035. ? | 0 | 0.88889 | 0.11111 | [8 empty] | 1 |  | 1
BK | 301 | 85342 | map |  | MTA/Franklin (7 - 27 Franklin St) |  |  | calculate based on R7 zoning | 413 units (120168 sqft * 3.44 FAR) | [6 empty] | ? |  |  |  |  | Uncertain | Any more context? |  |  | 0 | 0 | 1 | [10 empty] | 1
BK | 301 | 85343 | map |  | 130 - 154 North 7th Street Upzoning | PAS | 30 | [7 empty] | likely | additional units possible post 2025 |  | mixed use upzoning - total unit count unclear but 30 likey by 2025 |  |  | Realistic |  |  |  | 1 | 0 | 0 | [10 empty] | 1
BK | 301 | 85344 | map |  | River Street ConEd Site (87 - 105 River St) |  |  | calculate based on R8 zoning | 823 units (136792 sqft * 6.02 FAR) | [6 empty] | ? |  |  |  |  | Uncertain | Any more context? |  | Undeveloped site with unannounced buyer and community resistance (https://greenpointpost.com/local-group-calls-on-community-board-to-prevent-residential-development-of-con-ed-site) | 0 | 0 | 1 | [10 empty] | 1
BK | 301 | 85345 | map |  | Berry St NYCHA AOR |  | 100 | [13 empty] | Uncertain | Any more context? |  | Omitting because this is an additional NYCHA project | [7 empty] | 1 | [5 empty] | 1
BK | 301 | 85346 | map |  | Williams Plaza NYCHA Rezoning |  | 300 | [10 empty] | rezoning to R7 |  |  | Uncertain | Include 50% in 2035 and 50% in 2055 |  | Shouldn't we omit this because it's an additional NYCHA project? | 0 | 0.5 | 0.5 | [10 empty] | 1
BK | 301 | 85347 | map |  | Independence Towers NYCHA Rezoning |  | 300 | [10 empty] | rezoning to R7 |  |  | Uncertain | Include 50% in 2035 and 50% in 2055 |  | Shouldn't we omit this because it's an additional NYCHA project? | 0 | 0.5 | 0.5 | [10 empty] | 1
BK | 301 | 85354 | map |  | 10 Beadel Street (projected in NBK) |  | 11 | [7 empty] | likely | [5 empty] | Project may need to be removed | Treat as soft site as with all neighborhood study projected and potential sites | [9 empty] | 1 | [5 empty] | 1
BK | 301 | 85355 | map |  | 112 - 114 Kingsland St (projected in NBK) |  | 9 | [7 empty] | likely | [5 empty] | Project may need to be removed | Treat as soft site as with all neighborhood study projected and potential sites | [9 empty] | 1 | [5 empty] | 1
BK | 301 | 85356 | City Hall public sites list | Pipeline 13 | NYCHA - Cooper Park | Pipeline RFP/RFEI | 175 | Planner input: 150-200. Taking average. |  |  |  | Does BKO have more info where this NYCHA RFP/RFEI is located or how many total units? If so, please provide BBL & unit count. In Reynoso's district. Estimated 115 affordable units - total units unknown. |  |  | ? | ? | ? |  |  |  | n/a
BK | 301 | 85357 | City Hall public sites list | Current 44 | Greenpoint Hospital | Current RFP | 600 |  |  |  |  | Does BKO have more info where this HPD RFP is located or how many total units? If so, please provide BBL & unit count. In Reynoso's district. Estimated 300 affordable units - total units unknown. |  |  | ? | ? | ? |  |  |  | n/a
BK | 301 | 85358 | City Hall public sites list |  | 978 - 980 METROPOLITAN AV (projected in NBK) |  | 9 | [13 empty] | Uncertain | Any more context? | Added by boro without sufficient info | These aren't in Public Sites? Omitting these projects. | [7 empty] | 1 | [5 empty] | 1
BK | 301 | 85359 | City Hall public sites list |  | 939 GRAND ST (projected in NBK) |  | 23 | [13 empty] | Uncertain | Any more context? | Added by boro without sufficient info | These aren't in Public Sites? Omitting these projects. | [7 empty] | 1 | [5 empty] | 1
BK | 302 | 8 | DCP ZAP | 2018K0461 | 809 Atlantic Avenue Rezoning | Active; Public Review | 224 |  |  | 204 |  | No | [8 empty] | n/a
BK | 302 | 56 | DCP ZAP | P2012K0488 | BAM South | Complete; Completed | 300 |  |  | 0 |  | No | [8 empty] | n/a
BK | 302 | 57 | DCP ZAP | P2012K0591 | 265 Front Street | Active; Pre-Cert | 9 |  |  | 9 |  | No | [8 empty] | n/a
BK | 302 | 136 | DCP ZAP | P2013K0322 | 1 Clinton Street - BK Heights Library | Complete; Completed | 253 |  |  | 4 |  | No | [8 empty] | n/a
BK | 302 | 141 | DCP ZAP | P2013K0511 | 205 Park Ave Rezoning | Complete; Completed | 70 |  |  | 70 |  | No | [8 empty] | n/a
BK | 302 | 200 | DCP ZAP | P2014K0195 | 141 Willoughby Street | Complete; Completed | 193 |  |  | 193 | Alex Sommer | In mid-year 2018, you had provided feedback that this project was UNCERTAIN to be built by 2025. Is this still the case? If not, what is the likelihood that this project will be built by 2025? By 2035? | Uncertain | Project unlikely to proceed as residential. HPD financing not yet closed | likely | [5 empty] | Potentially aggressive | Check that this did NOT appear in HPD pre-closings list. If that's the case include in 2035 |  | Does not appear in HPD pre-closings list | 0 | 1 | 0
BK | 302 | 202 | DCP ZAP | P2014K0296 | 11-17 Flatbush Ave (One Flatbush) | Complete; Completed | 157 |  |  | 0 |  | No | [8 empty] | n/a
BK | 302 | 305 | DCP ZAP | P2015K0118 | 50 Nevins Street Rezoning | Complete; Completed | 128 |  |  | 0 |  | No | [8 empty] | n/a
BK | 302 | 306 | DCP ZAP | P2015K0145 | 75 greene avenue | Complete; Completed | 22 |  |  | 0 |  | No | [8 empty] | n/a
BK | 302 | 315 | DCP ZAP | P2015K0515 | 1019-1029 Fulton Street UDAAP, SP | Active; Completed | 50 |  |  | 0 |  | No | [8 empty] | n/a
BK | 302 | 391 | DCP ZAP | P2016K0138 | Tillary and Prince Streets Rezoning | Complete; Completed | 262 |  |  | 262 | Anand Amin | This project has not materialized in DOB permits despite being certified before mid-2017. What is the likelihood that this project will be built by 2025? By 2035? | Likely |  | likely | [5 empty] | Realistic |  |  |  | 1 | 0 | 0
BK | 302 | 394 | DCP ZAP | P2016K0180 | 142-150 South Portland | Complete; Completed | 100 |  |  | 0 |  | No | [8 empty] | n/a
BK | 302 | 396 | DCP ZAP | P2016K0250 | 80 Flatbush Avenue Rezoning | Active; Completed | 870 |  |  | 870 |  | No | [8 empty] | n/a
BK | 302 | 454 | DCP ZAP | P2017K0023 | 470 Vanderbilt Special Permit Renewal II | Complete; Completed | 363 |  |  | 363 |  | No | [8 empty] | n/a
BK | 302 | 463 | DCP ZAP | P2017K0254 | 57 Jay Street (Chair Cert 15-30) FT | Complete; Completed | 15 |  |  | 15 |  | No | [8 empty] | n/a
BK | 302 | 469 | DCP ZAP | P2017K0314 | 625 Fulton Street Rezoning | Active; Pre-Cert | 13 |  |  | 13 |  | No | [8 empty] | n/a
BK | 302 | 85331 | map |  | 90 SANDS ST (supportive nursing project) |  | 300 | [7 empty] | likely | [5 empty] | Uncertain | Any more context? |  |  | 1 | 0 | 0 | [10 empty] | 1
BK | 302 | 85332 | map |  | 11 HOYT STREET | DOB permitted but missing in database | 481 | [7 empty] | certain | [5 empty] | Project may need to be removed | Check if DOB permit in full developments DB and bring into DOB count |  | In the DOB development data as job #321197058, need to consider how to add to DOB pipeline. | 1 | 0 | 0 | [10 empty] | 1
BK | 302 | 85333 | map |  | 275 FLATBUSH AVENUE EXT (and adjacent lots) | demolition in progress |  | calculate from exist zoning | 283 units (28280 sqft * 10 FAR) | [5 empty] | likely | [5 empty] | Realistic |  |  |  | 1 | 0 | 0 | [10 empty] | 1
BK | 302 | 85334 | map |  | LIU/BK Hospital | info meeting | 1000 | [8 empty] | likely |  |  |  |  | Realistic |  |  |  | 0 | 1 | 0 | [10 empty] | 1
BK | 302 | 85335 | map |  | 98 3 AVENUE (and adjacent lots) | info meeting |  | calculate based on R7D zoning | 368 units (87557 sqft * 4.2 FAR) | [5 empty] | likely |  |  | applicant proposes R7D zoning with mixed residential/commercial. DCP in support. |  |  | Potentially aggressive | Override with generic build year rules | [15 empty] | 1
BK | 302 | 85336 | map |  | 88 3 AVENUE | info meeting |  | calculate based on R9 zoning | 352 units (46823 sqft * 7.52 FAR) | [6 empty] | uncertain |  | applicant proposes R9 zoning with mixed residential/commercial. DCP NOT in support. |  |  | Realistic |  |  |  | 0 | 0.5 | 0.5 | [10 empty] | 1
BK | 302 | 85337 | map |  | Atlantic Terminal |  | 0 | [9 empty] | not likely | highly unlikely, sitting on a lot of FAR. Year 2050. Recommend not projecting. |  |  | Project removed | [10 empty] | 1 | [5 empty] | 1
BK | 302 | 85338 | map |  | 2 - 58 HALL STREET (and adjacent lots) | info meeting | 400 | [9 empty] | likely | Very early stages - The applicants are interested in rezoning for residential, however we feel that a mix commercial/industrial and a small portion of residential is appropriate in this location. Conservatively ~400 units 2055 |  |  | Realistic |  |  |  | 0 | 0 | 1 | [10 empty] | 1
BK | 302 | 85360 | City Hall public sites list | Pipeline 4 | DUMBO Man Bridge Dev Rights (69 Adams St) | Pipeline RFP/RFEI |  |  | 162 units (17945 sqft * 9 FAR) |  |  | Does BKO have more info where this EDC/DM RFP/RFEI is located or how many total units? If so, please provide BBL & unit count. In Levin's district |  | Last update from EDC was that they were still in the early phases of this. | not likely | likely |  |  |  |  | Uncertain | Waiting on EDC input on build year and units |  | Keeping in 2055 on advice of R. Holbrook (EDC). | 0 | 0 | 1
BK | 303 | 9 | DCP ZAP | 2018K0468 | 776-780 Myrtle Avenue (UDAAP) | Active; Public Review | 50 |  |  | 50 | Collin Lee | No | [8 empty] | n/a
BK | 303 | 14 | DCP ZAP | 2018K0517 | Bed-Stuy Central and North NIHOP Cluster (UDAAP) | On-Hold; Pre-Cert | 45 |  |  | 0 |  | No | [8 empty] | n/a
BK | 303 | 59 | DCP ZAP | P2012K0670 | 27 Albany Avenue | Complete; Completed | 47 |  |  | 0 |  | No | [8 empty] | n/a
BK | 303 | 135 | DCP ZAP | P2013K0309 | Pfizer Sites Rezoning | Complete; Completed | 859 |  |  | 787 |  | No | [8 empty] | n/a
BK | 303 | 201 | DCP ZAP | P2014K0259 | 895 Bedford Avenue Rezoning | Active; Public Review | 36 |  |  | 36 |  | No | [8 empty] | n/a
BK | 303 | 206 | DCP ZAP | P2014K0469 | 376-378 Flushing Ave, 43 Franklin Ave(Rose Castle) | Complete; Completed | 296 |  |  | 154 |  | No | [8 empty] | n/a
BK | 303 | 208 | DCP ZAP | P2014K0492 | 744 Bedford Avenue FRESH | Complete; Completed | 82 |  |  | 82 |  | No | [8 empty] | n/a
BK | 303 | 308 | DCP ZAP | P2015K0203 | 723-733 Myrtle Avenue Rezoning | Complete; Public Review | 75 |  |  | 75 | Anthony Grande | This project has not materialized in DOB permits despite being certified before mid-2017. What is the likelihood that this project will be built by 2025? By 2035? | Likely |  | Uncertain | Likely |  | The property was for sale following the rezoning. Not clear if there is an interested developer; however, this is significantly soft and should be developed by 2035. |  |  | Realistic |  |  |  | 0.5 | 0.5 | 0
BK | 303 | 389 | DCP ZAP | P2016K0100 | 874 Willoughby Avenue FRESH (Cert) | Active; Pre-Cert | 105 |  |  | 105 |  | No | [8 empty] | n/a
BK | 303 | 399 | DCP ZAP | P2016K0311 | 2 Howard Avenue Rezoning | Active; Public Review | 33 |  |  | 33 |  | No | [8 empty] | n/a
BK | 303 | 403 | DCP ZAP | P2016K0373 | 1618 Fulton Street (UDAAP) | Complete; Completed | 85 |  |  | 0 |  | No | [8 empty] | n/a
BK | 303 | 455 | DCP ZAP | P2017K0051 | 410 Tompkins Avenue FRESH (cert) | Complete; Completed | 34 |  |  | 34 |  | No | [8 empty] | n/a
BK | 303 | 462 | DCP ZAP | P2017K0240 | Rochester Suydam ULURP (UDAAP) | Active; Pre-Cert | 69 |  |  | 27 |  | No | [8 empty] | n/a
BK | 303 | 467 | DCP ZAP | P2017K0285 | 948 Myrtle Avenue FRESH (certification) | Complete; Completed | 100 |  |  | 68 |  | No | [8 empty] | n/a
BK | 303 | 471 | DCP ZAP | P2017K0342 | 633 Marcy Avenue FRESH (cert) | Active; Pre-Cert | 64 |  |  | 64 |  | No | [8 empty] | n/a
BK | 303 | 472 | DCP ZAP | P2017K0364 | DeKalb Commons (NCP-NIHOP) (UDAAP) | On-Hold; Pre-Cert | 85 |  |  | 0 |  | No | [8 empty] | n/a
BK | 303 | 475 | DCP ZAP | P2017K0429 | 1921 Atlantic Ave - MWBE Site B | Active; Public Review | 235 |  |  | 235 |  | No | [8 empty] | n/a
BK | 303 | 528 | DCP ZAP | P2018K0273 | 1430 Fulton Street FRESH (cert) | Complete; Completed | 132 |  |  | 132 |  | No | [8 empty] | n/a
BK | 303 | 14714 | HPD RFP | 1 | MWBE Site B - 1921 Atlantic Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 303 | 14750 | HPD RFP | 131 | MWBE Site B - 1921 Atlantic Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 303 | 14764 | HPD RFP | 2 | MWBE Site B - 1921 Atlantic Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 303 | 14771 | HPD RFP | 26 | MWBE Site B - 1921 Atlantic Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 303 | 14774 | HPD RFP | 29 | MWBE Site B - 1921 Atlantic Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 303 | 14790 | HPD RFP | 43 | MWBE Site B - 1921 Atlantic Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 303 | 14797 | HPD RFP | 5 | NYCHA Sumner Houses | RFP | [5 empty] | No | [8 empty] | n/a
BK | 303 | 14805 | HPD RFP | 57 | MWBE Site B - 1921 Atlantic Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 303 | 14813 | HPD RFP | 64 | MWBE Site B - 1921 Atlantic Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 303 | 14821 | HPD RFP | 71 | MWBE Site B - 1921 Atlantic Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 303 | 14824 | HPD RFP | 74 | MWBE Site B - 1921 Atlantic Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 303 | 14827 | HPD RFP | 77 | MWBE Site B - 1921 Atlantic Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 303 | 14837 | HPD RFP | 86 | MWBE Site B - 1921 Atlantic Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 303 | 85348 | HPD RFP |  | 868 KENT AVENUE (and adjacent lots) |  |  | calculate based on FAR of ~4 | 66 units (16543 sqft * 4 FAR) | [5 empty] | uncertain | likely |  |  |  |  | Uncertain | Any more context? |  | This project appears in our ZAP pull. Strangely, it does not appear in our list of RFPs. | 0.5 | 0.5 | 0 | [10 empty] | 1
BK | 303 | 85349 | HPD RFP |  | 688 - 722 Myrtle Ave |  |  | calculate based on R7A zoning | 86 units (21582 sqft * 4 FAR) | [5 empty] | uncertain | likely |  |  |  |  | Uncertain | Any more context? |  |  | 0.5 | 0.5 | 0 | [10 empty] | 1
BK | 303 | 85350 | HPD RFP |  | 784 - 800 Myrtle Ave (HPD) |  | 170 | [7 empty] | likely | [5 empty] | Uncertain | Any more context? |  |  | 1 | 0 | 0 | [10 empty] | 1
BK | 303 | 85351 | HPD RFP |  | 53 UTICA AVENUE |  | 300 | [8 empty] | likely |  |  |  |  | Uncertain | Any more context? |  |  | 0 | 0.5 | 0.5 | [10 empty] | 1
BK | 303 | 85352 | HPD RFP |  | 1754 FULTON STREET (HPD) |  | 150 | [7 empty] | likely | [5 empty] | Uncertain | Any more context? |  |  | 1 | 0 | 0 | [10 empty] | 1
BK | 303 | 85353 | HPD RFP |  | HPD sites along Fulton St and Howard Ave |  | 350 | [7 empty] | likely | [5 empty] | Uncertain | Is this the same as Public Sites Fulton Street sites? |  | Likely, same city council district | 1 | 0 | 0 | [10 empty] | 1
BK | 304 | 29 | DCP ZAP | 2019K0153 | NIHOP Old Stanley - 641 Chauncey | Active; Pre-Cert | 8 |  |  | 8 |  | No | [8 empty] | n/a
BK | 304 | 43 | DCP ZAP | P2012K0041 | RHEINGOLD REZONING | Active; Completed | 977 |  |  | 0 |  | No | [8 empty] | n/a
BK | 304 | 211 | DCP ZAP | P2014K0541 | Suydam Street rezoning | Active; Public Review | 95 |  |  | 8 |  | No | [8 empty] | n/a
BK | 304 | 390 | DCP ZAP | P2016K0120 | 605 Hart Street FRESH (Authorization) | Complete; Completed | 56 |  |  | 56 |  | No | [8 empty] | n/a
BK | 304 | 404 | DCP ZAP | P2016K0433 | 1601 DeKalb Avenue Rezoning | Complete; Completed | 122 |  |  | 122 |  | No | [8 empty] | n/a
BK | 304 | 474 | DCP ZAP | P2017K0417 | 63 Stockholm Street - Bushwick Alliance | Active; Public Review | 20 |  |  | 20 |  | No | [8 empty] | n/a
BK | 304 | 14816 | HPD RFP | 67 | NYCHA Senior -Bushwick II | RFP | [5 empty] | No | [8 empty] | n/a
BK | 305 | 7 | DCP ZAP | 2018K0445 | 50 Pennsylvania Avenue FRESH Food Store | Active; Pre-Cert | 200 |  |  | 0 |  | No | [8 empty] | n/a
BK | 305 | 23 | DCP ZAP | 2019K0038 | East New York Christian Cultural Center | Active; Pre-Cert | 2000 |  |  | 2000 |  | No | [7 empty] | KS Note: Updated geomerty for this site to include full block face. Need to overwrite old shapefile. MS: This is the same geography as already exists on ZAP. | n/a
BK | 305 | 38 | DCP ZAP | 2 [ESD Project] | Fountain Avenue |  | 1169 |  |  | 1104 |  | This is an ESD project. Can you confirm this is still a project, and will be residential? What are the latest phasing plans for this project (break down as much as possible ## of units by a specific year)? |  |  | uncertain | likely |  | https://esd.ny.gov/fountain-avenue-project. Development will be divided in three phases with construction ending in 2027. No more details have been provided by NYS. |  |  | Realistic |  |  |  | 0.5 | 0.5 | 0
BK | 305 | 53 | DCP ZAP | P2012K0249 | Cypress Hills Senior Housing | Complete; Completed | 54 |  |  | 0 |  | No | [8 empty] | n/a
BK | 305 | 54 | DCP ZAP | P2012K0250 | Pitkin-Berriman Rezoning | Complete; Completed | 26 |  |  | 0 |  | No | [8 empty] | n/a
BK | 305 | 392 | DCP ZAP | P2016K0159 | Linden Boulevard rezoning | Complete; Completed | 521 |  |  | 286 |  | No | [8 empty] | n/a
BK | 305 | 400 | DCP ZAP | P2016K0319 | Lincoln and Wortman Avenues Rezoning (PQ,PP,ZM,ZR) | Active; Pre-Cert | 193 |  |  | 193 |  | No | [8 empty] | n/a
BK | 305 | 468 | DCP ZAP | P2017K0286 | 461 Alabama Ave (HA,HU,ZS) | Active; Public Review | 73 |  |  | 6 |  | No | [8 empty] | n/a
BK | 305 | 524 | DCP ZAP | P2018K0116 | ENY North NCP (UDAAP) | On-Hold; Pre-Cert | 42 |  |  | 42 |  | No | [8 empty] | n/a
BK | 305 | 525 | DCP ZAP | P2018K0122 | Fresh Creek URP Phase 5 (HC) | On-Hold; Pre-Cert | 92 |  |  | 92 | Alexandra Paty Diaz | In mid-year 2018, you had provided feedback that this project was UNCERTAIN to be built by 2025. Is this still the case? If not, what is the likelihood that this project will be built by 2025? By 2035? | Uncertain | draft LUA not received yet. Action is to increase 92 units of the overall 500 units total | likely | [5 empty] | Potentially aggressive | Check project description if total development is 592 units, if ULURP needed and which milestone reached |  | Project description shows minor change -- 92 unit increase to 2,477 max DUs. Project is non-ULURP, and still Pre-Cert, no milestones. Don't see reason to push this back past 2025, based on planner input. ? | 1 | 0 | 0
BK | 305 | 529 | DCP ZAP | P2018K0275 | Sutter Avenue Rezoning | On-Hold; Pre-Cert | 24 |  |  | 24 |  | No | [8 empty] | n/a
BK | 305 | 533 | DCP ZAP | P2018K0333 | 515 Blake Avenue (HA,ZM,ZR,ZS) | On-Hold; Pre-Cert | 361 |  |  | 361 |  | No | [8 empty] | n/a
BK | 305 | 14755 | HPD RFP | 136 | Dinsmore-Chestnut | RFP | [5 empty] | No | [8 empty] | n/a
BK | 305 | 14781 | HPD RFP | 35 | Grant Avenue (Modular) | RFP | [5 empty] | No | [8 empty] | n/a
BK | 305 | 14825 | HPD RFP | 75 | MWBE Site A - 461 Alabama Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 305 | 14955 | Neighborhood Study | 247 Vermont Street (NIHOP and NCP Clusters) EAST NEW YORK REZONING COMMITMENT | 247 Vermont Street (NIHOP and NCP Clusters) EAST NEW YORK REZONING COMMITMENT |  |  |  | 6 units (4190 sqft * 1.35 FAR) |  |  | How many residential units do we expect from this commimitment site? |  |  | ? | ? | ? |  |  |  | n/a
BK | 305 | 15107 | Neighborhood Study | 66 EAST NEW YORK REZONING COMMITMENT | 66 EAST NEW YORK REZONING COMMITMENT (3269 ATLANTIC AVENUE) |  | 275 |  |  |  |  | How many residential units do we expect from this commimitment site? |  |  | likely |  |  | permit for 275 units issued in 2018. |  |  | Project may need to be removed | Check for DOB match |  | This is Dinsmore-Chestnut. Overlaps with 275 unit DOB job. | [7 empty] | 1
BK | 305 | 15109 | Neighborhood Study | 67 EAST NEW YORK REZONING COMMITMENT | 67 EAST NEW YORK REZONING COMMITMENT |  | 403 |  |  |  |  | How many residential units do we expect from this commimitment site? |  |  | likely |  |  | permit for 304 units (affordable) issued in 2017. |  |  | Project may need to be removed | Check for DOB match |  | This is Phipps House. Overlaps with 403 unit DOB jobs. | [7 empty] | 1
BK | 305 | 85321 | map |  | Chesnut Commons (HPD site?) |  |  | calculate from exist zoning | 150 units (27838 sqft * 5.4 FAR) | [11 empty] | Uncertain | Any more context? |  | Could this be part of Dinsmore-Chestnut? | 0 | 0 | 1 | [10 empty] | 1
BK | 305 | 85322 | map |  | 2424 LINDEN BOULEVARD | pre info meeting | 200 | [13 empty] | n/a | [16 empty] | 1
BK | 305 | 85323 | map |  | Dumont & Ruby Street - churches talking to HPD |  |  | calculate from exist zoning | 55 units (60770 sqft * 0.9 FAR) | [11 empty] | Uncertain | Any more context? |  |  | 0 | 0 | 1 | [10 empty] | 1
BK | 305 | 85324 | map |  | St. Pauls Baptist Church | pre info meeting | 600 | [13 empty] | n/a | [16 empty] | 1
BK | 305 | 85325 | map |  | 350 SHEFFIELD AVENUE | pre info meeting | 145 | [13 empty] | n/a | [16 empty] | 1
BK | 305 | 85326 | map |  | Grace Baptist Church |  | 100 | [13 empty] | Uncertain | Any more context? |  |  | 0 | 0 | 1 | [10 empty] | 1
BK | 305 | 85327 | map |  | 888 FOUNTAIN AVENUE (NYS site) |  | 4569 | [8 empty] | uncertain | likely | https://esd.ny.gov/sites/default/files/rfp/Brooklyn-Dev-Center-RFP-4262018.pdf |  |  | Project may need to be removed. |  |  | To ignore. Cannot find evidence of this unit count. | [7 empty] | 1 | [5 empty] | 1
BK | 306 | 55 | DCP ZAP | P2012K0364 | 363-365 Bond Street | Complete; Completed | 253 |  |  | 0 |  | No | [8 empty] | n/a
BK | 306 | 58 | DCP ZAP | P2012K0665 | 14-18 Carroll Street Rezoning | Complete; Completed | 10 |  |  | 10 |  | No | [8 empty] | n/a
BK | 306 | 311 | DCP ZAP | P2015K0386 | 41 Summit Street Rezoning | Active; Public Review | 7 |  |  | 7 |  | No | [8 empty] | n/a
BK | 306 | 313 | DCP ZAP | P2015K0440 | 260 Van Brunt Street Rezoning | On-Hold; Pre-Cert | 39 |  |  | 39 |  | No | [8 empty] | n/a
BK | 306 | 386 | DCP ZAP | P2016K0053 | 120 Fifth Avenue | Complete; Public Review | 165 |  |  | 0 |  | No | [8 empty] | n/a
BK | 306 | 393 | DCP ZAP | P2016K0163 | 55-63 Summit Street Rezoning | Complete; Completed | 14 |  |  | 14 |  | No | [8 empty] | n/a
BK | 306 | 405 | DCP ZAP | P2016K0437 | Columbia Street Waterfront UDAAP | On-Hold; Pre-Cert | 13 |  |  | 3 | Catherine Ferrara Iannitto | In mid-year 2018, you had provided feedback that this project was UNCERTAIN to be built by 2025. Is this still the case? If not, what is the likelihood that this project will be built by 2025? By 2035? | Uncertain | This project has been on hold in HPD's hands for several years. Actions will be simplified when Columbia Street Urban Renewal Plan expires in September 2019, so may move forward near that date. | may be best to ask HPD | [5 empty] | n/a
BK | 306 | 470 | DCP ZAP | P2017K0341 | 52 Lorraine Street Rezoning | On-Hold; Pre-Cert | 114 |  |  | 114 | Jonathan Keller | In mid-year 2018, you had provided feedback that this project was LIKELY expected to be built by 2025. However, it has moved from active to on-hold. What is the likelihood that this project will be built by 2025? By 2035? | Likely |  |  | likely |  | small project, little movement, councilmember may pose difficulty |  |  | Realistic |  |  |  | 0 | 1 | 0
BK | 306 | 530 | DCP ZAP | P2018K0295 | NYCHA NextGen Wyckoff | Active; Pre-Cert | 597 |  |  | 597 |  | No | [8 empty] | n/a
BK | 306 | 14819 | HPD RFP | 7 | NYCHA Wyckoff | RFP | [5 empty] | No | [8 empty] | n/a
BK | 306 | 85314 | map |  | 1 PROSPECT PARK WEST |  |  | calculate from exist zoning | 116 units (19324 sqft * 6.02 FAR) | [5 empty] | likely | [5 empty] | Uncertain | Any more context? |  |  | 1 | 0 | 0 | [10 empty] | 1
BK | 306 | 85315 | map |  | Two Trees (properties around 118 2 AVENUE) |  | 0 | [8 empty] | likely |  | No new units; mixed retail and office development. |  |  | Project not counted | [10 empty] | 1 | [5 empty] | 1
BK | 306 | 85316 | map |  | 694 - 712 HICKS STREET | info meeting | 105 | [8 empty] | likely |  | 105 units (preliminary) |  |  | Realistic |  |  |  | 0 | 1 | 0 | [10 empty] | 1
BK | 306 | 85317 | map |  | 46 NELSON STREET | info meeting |  | calculate based on similar dev in area | 40 units (20101 sqft * 2 FAR) | [6 empty] | uncertain |  | An attorney representing the owner reached out to express interest, but we haven’t held an info meeting yet. |  |  | Realistic |  |  |  | 0 | 0.5 | 0.5 | [10 empty] | 1
BK | 306 | 85318 | map |  | 100 IMLAY STREET |  | 70 | [9 empty] | likely | assume 70 based on sister development at 160 IMLAY |  |  | Uncertain | Any more context? |  |  | 0 | 0 | 1 | [10 empty] | 1
BK | 307 | 24 | DCP ZAP | 2019K0075 | 152 23rd Street Authorization | Active; Pre-Cert | 2 |  |  | 2 |  | No | [8 empty] | n/a
BK | 307 | 207 | DCP ZAP | P2014K0483 | Sunset Park Library | Complete; Completed | 49 |  |  | 0 |  | No | [8 empty] | n/a
BK | 307 | 314 | DCP ZAP | P2015K0450 | 57 Caton Place Rezoning | Complete; Completed | 107 |  |  | 107 |  | No | [8 empty] | n/a
BK | 307 | 85313 | map |  | 312 CONEY ISLAND AVENUE | active private app | 300 | [7 empty] | likely | [5 empty] | Potentially aggressive | Check which milestone reached and if DCP target cert date is set |  | No DCP target cert but application is at EAS stage. This project requires ULURP. This is a duplicate of P2018K0303 in the new ZAP pull -- omit. | 0.5 | 0.5 | 0 | [10 empty] | 1
BK | 307 | 85319 | map |  | 737 4 AVENUE | active private app | 142 | [7 empty] | likely | [5 empty] | Potentially aggressive | Check which milestone reached and if DCP target cert date is set |  | No DCP target cert but application is at EAS stage. This project requires ULURP. | 0.5 | 0.5 | 0 | [10 empty] | 1
BK | 307 | 85320 | map |  | 237A 27 STREET | info meeting | 6 | [13 empty] | n/a | [16 empty] | 1
BK | 308 | 1 | DCP ZAP | 1 [ESD Project] | Atlantic Yards -- Phase II (Pacific Park) |  | 6430 |  |  | 3886 | Jonah Rogoff | This is an ESD project. Can you confirm this is still a project, and will be residential? What are the latest phasing plans for this project (break down as much as possible ## of units by a specific year)? |  |  |  | uncertain | likely | There are 6430 total units (~1240 units built and ~1100 under construction). The last article I read indicated 2035 would be when full built out occurs, but possible it will be delayed. |  |  | Realistic |  |  |  | 0 | 0.5 | 0.5
BK | 308 | 12 | DCP ZAP | 2018K0488 | 840 Atlantic Ave | Active; Pre-Cert | 281 |  |  | 281 |  | No | [8 empty] | n/a
BK | 308 | 25 | DCP ZAP | 2019K0093 | 1559-1563 Prospect Place | Active; Pre-Cert | 45 |  |  | 45 |  | No | [8 empty] | n/a
BK | 308 | 142 | DCP ZAP | P2013K0549 | 1050 Pacific Street Rezoning | Active; Public Review | 103 |  |  | 103 |  | No | [8 empty] | n/a
BK | 308 | 196 | DCP ZAP | P2014K0056 | 587 Bergen Street Rezoning | Complete; Completed | 26 |  |  | 26 |  | No | [8 empty] | n/a
BK | 308 | 304 | DCP ZAP | P2015K0063 | 1350 Bedford Avenue Rezoning | Complete; Completed | 94 |  |  | 0 |  | No | [8 empty] | n/a
BK | 308 | 309 | DCP ZAP | P2015K0351 | 1010 Pacific Street Rezoning | Active; Public Review | 154 |  |  | 154 |  | No | [8 empty] | n/a
BK | 308 | 385 | DCP ZAP | P2016K0052 | 1535 Bedford Ave FRESH (Chair Cert) | Complete; Completed | 7 |  |  | 7 |  | No | [8 empty] | n/a
BK | 308 | 456 | DCP ZAP | P2017K0120 | 805 Washington Avenue - FRESH ZA,ZC | Complete; Completed | 37 |  |  | 0 |  | No | [8 empty] | n/a
BK | 308 | 457 | DCP ZAP | P2017K0168 | 35 Underhill Avenue rezoning | Complete; Completed | 39 |  |  | 39 |  | No | [8 empty] | n/a
BK | 308 | 522 | DCP ZAP | P2018K0048 | 1134-1142 Pacific Street Rezoning | On-Hold; Pre-Cert | 139 |  |  | 139 | Anthony Grande | In mid-year 2018, you had provided feedback that this project was LIKELY expected to be built by 2025. However, it has moved from active to on-hold. What is the likelihood that this project will be built by 2025? By 2035? | Likely |  | Not likely |  |  | This project will be closed out soon. |  |  | Potentially conservative | Include in 2055 |  |  | 0 | 0 | 1
BK | 308 | 526 | DCP ZAP | P2018K0143 | Grand Ave and Pacific St Rezoning | Active; Pre-Cert | 64 |  |  | 64 |  | No | [8 empty] | n/a
BK | 308 | 85311 | map |  | 1317 BEDFORD AVENUE | info meeting | 200 | [13 empty] | n/a
BK | 308 | ? | City Hall public sites list | Pipeline 23 | 516 Bergen + ENS Lot (Seniors) | Pipeline RFP/RFEI |  |  | 35 units (17478 sqft * 2.0 FAR) |  |  | Does BKO have more info where this HPD RFP is located or how many total units? If so, please provide BBL & unit count. In Cumbo's district |  |  | ? | ? | ? |  |  |  | n/a
BK | 309 | 3 | DCP ZAP | 2018K0356 | Franklin Avenue Rezoning | Active; Public Review | 518 |  |  | 518 |  | No | [8 empty] | n/a
BK | 309 | 46 | DCP ZAP | P2012K0085 | EMPIRE BOULEVARD REZONING | Complete; Completed | 68 |  |  | 68 |  | No | [8 empty] | n/a
BK | 309 | 197 | DCP ZAP | P2014K0144 | 31 Lincoln Road Apartments | Complete; Completed | 93 |  |  | 93 |  | No | [8 empty] | n/a
BK | 309 | 397 | DCP ZAP | P2016K0272 | Bedford-Union Armory (LSGD) | Complete; Completed | 415 |  |  | 0 |  | No | [8 empty] | n/a
BK | 309 | 523 | DCP ZAP | P2018K0080 | 960 Franklin Avenue Rezoning | Active; Pre-Cert | 1578 |  |  | 1578 |  | No | [8 empty] | n/a
BK | 309 | 527 | DCP ZAP | P2018K0153 | 253-263 Empire Boulevard - FRESH ZC | On-Hold; Pre-Cert | 66 |  |  | 66 | Kevin Kraft | In mid-year 2018, you had provided feedback that this project was LIKELY expected to be built by 2025. However, it has moved from active to on-hold. What is the likelihood that this project will be built by 2025? By 2035? | Likely | applicants have DOB permits and are actively pursuing a FRESH certification. Aiming for a early fall certification | likely | likely |  | applicants have DOB permits and are actively pursuing a FRESH certification |  |  | Project may need to be removed | Check for DOB match |  | Only a 15 unit permit has appeared in the data, which intersects directly with this lot and permit issued in March 2018. The planner modified the units remaining count. | 1 | 0 | 0 |  |  |  |  | 1
BK | 309 | 14190 | EDC | 1 | Bedford-Union Armory |  | 415 |  |  | 0 |  | No | [8 empty] | n/a
BK | 309 | 85304 | map |  | 840 - 846 Empire Bl | info meeting |  |  | 319 units (92764 sqft * 3.44 FAR) | [5 empty] | likely | [5 empty] | Potentially aggressive | Override with generic build year rules | [15 empty] | 1
BK | 309 | 85305 | map |  | 600 - 630 Crown Street | info meeting |  | calculate from exist zoning | 196 units (56874 sqft * 3.44 FAR) | [6 empty] | likely |  |  |  |  | Realistic |  |  |  | 0 | 1 | 0 | [10 empty] | 1
BK | 309 | 85306 | map |  | 456 EASTERN PARKWAY | info meeting |  | calculate from exist zoning | 45 units (18660 sqft * 2.43 FAR) | [11 empty] | n/a | [16 empty] | 1
BK | 309 | 85307 | map |  | 1679 - 1715 BEDFORD AV |  |  | calculate from exist zoning | 135 units (55685 sqft * 2.43 FAR) | [6 empty] | likely |  |  |  |  | Realistic |  |  |  | 0 | 1 | 0 | [10 empty] | 1
BK | 309 | 85308 | map |  | Medgar Evars Parking Lot |  |  | calculate from exist zoning | 123 units (50533 sqft * 2.43 FAR) | [7 empty] | likely |  |  |  | Uncertain | Any more context? |  |  | 0 | 0 | 1 | [10 empty] | 1
BK | 309 | 85309 | map |  | 1039 FRANKLIN AVENUE | info meeting |  | calculate from exist zoning | 253 units (73614 sqft * 3.44 FAR) | [5 empty] | likely | [5 empty] | Potentially aggressive | Override with generic build year rules | [15 empty] | 1
BK | 309 | 85310 | map |  | 469 FLATBUSH AVENUE | info meeting |  |  | 92 units (26630 sqft * 3.44 FAR) | [6 empty] | ? |  |  |  |  | n/a | [16 empty] | 1
BK | 309 | 85312 | map |  | Kings Co Hospital/ SUNY Downstate | info meeting | 1250 | Planner input: 1000-1500. Taking average. | I would assume the midpoint of 1250 | [6 empty] | likely |  | Identified as part of Gov Cuomo's Vital Brookyn Initiative |  |  | Realistic |  |  |  | 0 | 1 | 0 | [10 empty] | 1
BK | 310 | 13 | DCP ZAP | 2018K0500 | 9114 5th Avenue Rezoning | Active; Pre-Cert | 50 |  |  |  | Sanmati Naik | How many residential units do we expect this project to introduce? | [8 empty] | n/a
BK | 310 | 303 | DCP ZAP | P2015K0024 | 2nd Special Permit Renewal 6200 Eighth Avenue | Complete; Completed | 216 |  |  | 216 | Richard Jacobs | No | Uncertain | 2nd special permit renewal will expire, will need to come back for approvals again | ? | ? | ? |  |  |  | Potentially aggressive | Include in 2035 |  |  | 0 | 1 | 0
BK | 310 | 317 | DCP ZAP | P2015K0537 | 6208 8th Avenue (SP 74-681) | Active; Pre-Cert | 250 |  |  | 250 |  | No | [8 empty] | n/a
BK | 310 | 458 | DCP ZAP | P2017K0173 | 6418 8th Avenue | Active; Pre-Cert | 48 |  |  | 48 | Sanmati Naik | ZAP currently only includes information on units associated with MIH and voluntary affordable housing for this project. How many total residential units do we expect this project to introduce? | Likely | [7 empty] | n/a
BK | 311 | 44 | DCP ZAP | P2012K0047 | MAPLE LANE VIEWS | Complete; Completed | 112 |  |  | 0 |  | No | [8 empty] | n/a
BK | 311 | 138 | DCP ZAP | P2013K0364 | 273 Avenue U Rezoning | Active; Pre-Cert | 9 |  |  | 9 |  | No | [8 empty] | n/a
BK | 311 | 402 | DCP ZAP | P2016K0351 | 1881-1883 McDonald Avenue Rezoning | Complete; Completed | 36 |  |  | 36 |  | No | [8 empty] | n/a
BK | 311 | 464 | DCP ZAP | P2017K0266 | 2080 McDonald Avenue Rezoning | On-Hold; Pre-Cert | 96 |  |  | 96 | Richard Jacobs | In mid-year 2018, you had provided feedback that this project was LIKELY expected to be built by 2025. However, it has moved from active to on-hold. What is the likelihood that this project will be built by 2025? By 2035? | Likely |  | ? | ? | ? |  |  |  | n/a
BK | 312 | 5 | DCP ZAP | 2018K0395 | 1880 Coney Island Ave Rezoning | Active; Pre-Cert | 195 |  |  | 195 |  | No | [8 empty] | n/a
BK | 312 | 6 | DCP ZAP | 2018K0415 | 1776 48th Street Rezoning | Active; Pre-Cert | 5 |  |  | 3 | Collin Lee | How many residential units do we expect this project to introduce? | Uncertain | Too early stage in DCP process, applicant has not submitted a Pre-Application Statement | [6 empty] | n/a
BK | 312 | 10 | DCP ZAP | 2018K0479 | 5914 Bay Parkway Rezoning | Active; Pre-Cert | 41 |  |  | 35 |  | No | [8 empty] | n/a
BK | 312 | 26 | DCP ZAP | 2019K0111 | 1251-1271 60th Street Rezoning | Active; Pre-Cert | 100 |  |  | 100 |  | No | [8 empty] | n/a
BK | 312 | 384 | DCP ZAP | P2016K0021 | 1501-1555 60th Street Rezoning | Active; Pre-Cert | 109 |  |  | 109 |  | No | [8 empty] | n/a
BK | 312 | 387 | DCP ZAP | P2016K0080 | 3901 9th Avenue Rezoning | Active; Public Review | 44 |  |  | 44 |  | No | [8 empty] | n/a
BK | 312 | 401 | DCP ZAP | P2016K0347 | 4217 New Utrecht Avenue Rezoning | On-Hold; Pre-Cert | 139 |  |  | 139 |  | No | [8 empty] | n/a
BK | 312 | 85303 | map |  | Brooklyn Yards |  | 270 | [8 empty] | ? |  |  |  |  | Uncertain | Any more context? |  |  | 0 | 0 | 1 | [10 empty] | 1
BK | 313 | 22 | DCP ZAP | 2019K0036 | 1002 Brighton Beach Avenue | Active; Pre-Cert | 150 |  |  | 150 |  | No | [8 empty] | n/a
BK | 313 | 27 | DCP ZAP | 2019K0125 | Resilient Housing and Open Space ULURP - Brooklyn | Active; Pre-Cert | 52 |  |  | 52 |  | No | [8 empty] | n/a
BK | 313 | 52 | DCP ZAP | P2012K0245 | OCEANVIEW MANOR | Complete; Completed | 24 |  |  | 24 |  | No | [8 empty] | n/a
BK | 313 | 194 | DCP ZAP | P2014K0042 | Sea Park North Rezoning | Complete; Completed | 153 |  |  | 153 |  | No | [8 empty] | n/a
BK | 313 | 209 | DCP ZAP | P2014K0494 | W 22nd - W 23rd St Coney Island Rezoning | Active; Public Review | 78 |  |  | 78 |  | No | [8 empty] | n/a
BK | 313 | 318 | DCP ZAP | P2015K0539 | West Shore Rezoning LSGD | Active; Pre-Cert | 1690 |  |  | 1690 | Amritha Mahesh | This project has not materialized in DOB permits despite being certified before mid-2017. What is the likelihood that this project will be built by 2025? By 2035? | Uncertain | Yet to be seen whether project will certify (highly contentious due to resiliency and transportation concerns) | Not likely | Maybe | Maybe | Yet to be seen whether project will certify (highly contentious due to resiliency and transportation concerns |  |  | Realistic |  |  |  | 0 | 0.5 | 0.5
BK | 313 | 382 | DCP ZAP | P2016K0006 | 2957 Shell Road Rezoning | On-Hold; Pre-Cert | 189 |  |  | 189 | Collin Lee | In mid-year 2018, you had provided feedback that this project was UNCERTAIN to be built by 2025. Is this still the case? If not, what is the likelihood that this project will be built by 2025? By 2035? | Uncertain | Cautious that this project will certify within 5 years. Issues with police shed adjacent to site that must be addressed first. | Probably not. | Maybe | Yes | Issues with Police Shed on property will delay the build date. |  |  | Realistic |  |  |  | 0 | 0.5 | 0.5
BK | 313 | 521 | DCP ZAP | P2018K0039 | 271 Sea Breeze Avenue ZM | Active; Pre-Cert | 114 |  |  | 114 |  | No | [8 empty] | n/a
BK | 313 | 14191 | EDC | 10 | Coney West (Parcel C1) |  | 135 |  |  | 0 |  | No | [8 empty] | n/a
BK | 313 | 14192 | EDC | 11 | Coney West (Parcel C2) |  | 220 |  |  | 12 |  | No | [8 empty] | n/a
BK | 313 | 14193 | EDC | 12 | Coney West (Parcel C3) |  | 145 |  |  | 145 |  | No | [8 empty] | n/a
BK | 313 | 14194 | EDC | 13 | Coney West (Parcel C4) |  | 160 |  |  | 160 |  | No | [8 empty] | n/a
BK | 313 | 14195 | EDC | 14 | Coney West (Parcel D) |  | 400 |  |  | 400 |  | No | [8 empty] | n/a
BK | 313 | 14196 | EDC | 15 | Coney North (Parcel N1) |  | 446 |  |  | 0 |  | No | [8 empty] | n/a
BK | 313 | 14197 | EDC | 16 | Coney North (Parcel N2) |  | 373 |  |  | 373 |  | No | [8 empty] | n/a
BK | 313 | 14198 | EDC | 17 | Coney North (Parcel N3) |  | 259 |  |  | 259 |  | No | [8 empty] | n/a
BK | 313 | 14205 | EDC | 8 | Coney West (Parcel A) |  | 508 |  |  | 508 |  | No | [8 empty] | n/a
BK | 313 | 14206 | EDC | 9 | Coney West (Parcels E & F) |  | 1353 |  |  | 1353 |  | No | [8 empty] | n/a
BK | 314 | 11 | DCP ZAP | 2018K0481 | 56 Marlborough Road Zoning Authorization | Active; Public Review | 2 |  |  | 2 |  | No | [8 empty] | n/a
BK | 314 | 51 | DCP ZAP | P2012K0242 | Brooklyn College Nostrand Avenue Development | Complete; Completed | 83 |  |  | 83 |  | No | [8 empty] | n/a
BK | 314 | 307 | DCP ZAP | P2015K0157 | Caton Flats (Flatbush Caton Market) | Complete; Completed | 251 |  |  | 0 |  | No | [8 empty] | n/a
BK | 314 | 383 | DCP ZAP | P2016K0008 | 1640 Flatbush Avenue | Active; Public Review | 115 |  |  | 115 |  | No | [8 empty] | n/a
BK | 314 | 395 | DCP ZAP | P2016K0236 | 1620 Cortelyou Road Rezoning | On-Hold; Public Review | 88 |  |  | 88 | Amy Jin | In mid-year 2018, you had provided feedback that this project was LIKELY expected to be built by 2025. However, it has moved from active to on-hold. What is the likelihood that this project will be built by 2025? By 2035? | Likely |  | likely |  |  | currently updating eas |  |  | Realistic |  |  |  | 1 | 0 | 0
BK | 314 | 85300 | map |  | Sears parking lot (possible project in C4-2) |  |  | calculate from zoning | 272 units (111788 sqft * 2.43 FAR) | [6 empty] | likely |  |  |  | KS: The Sear's lot was incorrectly drawn on the boro planner map, so I found the actual lot 3 blocks away and regeocoded. | Uncertain | Any more context? |  |  | 0 | 1 | 0 | [10 empty] | 1
BK | 314 | 85301 | map |  | 2580 - 2644 Nostrand Ave (R7A/C2-4 proposed) |  | 250 | [8 empty] | ? |  |  |  |  | Uncertain | Any more context? |  |  | 0 | 0 | 1 | [10 empty] | 1
BK | 314 | 85302 | map |  | 1214 - 1238 E. 14 St (M1-1 to R7A proposed) |  | 150 | [8 empty] | ? |  |  |  |  | Uncertain | Any more context? |  |  | 0 | 0 | 1 | [10 empty] | 1
BK | 315 | 2 | DCP ZAP | 2018K0354 | 2510 Coney Island Avenue Rezoning | Active; Pre-Cert | 60 |  |  | 60 |  | No | [8 empty] | n/a
BK | 315 | 28 | DCP ZAP | 2019K0147 | 2959 Avenue Y Rezoning | Active; Pre-Cert | 38 |  |  | 38 |  | No | [8 empty] | n/a
BK | 315 | 531 | DCP ZAP | P2018K0300 | 2840 Knapp Street Rezoning | Active; Pre-Cert | 0 |  |  |  | Anthony Grande | How many residential units do we expect this project to introduce? |  |  | No residential |  |  | This is a nursing home project. |  |  | Project not counted | [7 empty] | 1
BK | 315 | 532 | DCP ZAP | P2018K0320 | 2892 Nostrand Avenue Rezoning | Active; Pre-Cert | 59 |  |  | 59 |  | No | [8 empty] | n/a
BK | 316 | 134 | DCP ZAP | P2013K0263 | Livonia Avenue Rezoning | Complete; Completed | 278 |  |  | 0 |  | No | [8 empty] | n/a
BK | 316 | 195 | DCP ZAP | P2014K0044 | Bergen-Saratoga | Complete; Completed | 80 |  |  | 0 |  | No | [8 empty] | n/a
BK | 316 | 198 | DCP ZAP | P2014K0145 | Henry Apartments | Complete; Completed | 79 |  |  | 0 |  | No | [8 empty] | n/a
BK | 316 | 205 | DCP ZAP | P2014K0454 | Van Sinderen Plaza | Complete; Pre-Cert | 130 |  |  | 0 |  | No | [8 empty] | n/a
BK | 316 | 310 | DCP ZAP | P2015K0353 | 1860 Eastern Parkway | Complete; Completed | 67 |  |  | 0 |  | No | [8 empty] | n/a
BK | 316 | 312 | DCP ZAP | P2015K0393 | Marcus Garvey Apartments LSGD | Active; Completed | 724 |  |  | 724 |  | No | [8 empty] | n/a
BK | 316 | 316 | DCP ZAP | P2015K0526 | Ebenezer Plaza Rezoning | Complete; Completed | 531 |  |  | 0 |  | No | [8 empty] | n/a
BK | 316 | 388 | DCP ZAP | P2016K0082 | Edwin's Place | Complete; Completed | 126 |  |  | 0 |  | No | [8 empty] | n/a
BK | 316 | 398 | DCP ZAP | P2016K0273 | 210-214 Hegeman Avenue | Complete; Completed | 71 |  |  | 0 |  | No | [8 empty] | n/a
BK | 316 | 461 | DCP ZAP | P2017K0230 | 803 Rockaway Avenue Rezoning | On-Hold; Pre-Cert | 153 |  |  | 153 | Anthony Grande | In mid-year 2018, you had provided feedback that this project was LIKELY expected to be built by 2025. However, it has moved from active to on-hold. What is the likelihood that this project will be built by 2025? By 2035? | Likely |  | Likely |  |  | The hold up is to resolve MX zoning issues with DEP, but the developer is very aggressively pursuing this project and they have HPD support. |  |  | Realistic |  |  |  | 1 | 0 | 0
BK | 316 | 466 | DCP ZAP | P2017K0284 | 1510 Broadway | Active; Pre-Cert | 60 |  |  | 60 | Anthony Grande | In mid-year 2018, you had provided feedback that this project was UNCERTAIN to be built by 2025. Is this still the case? If not, what is the likelihood that this project will be built by 2025? By 2035? | Uncertain | Too early stage in DCP process, applicant has not submitted a Pre-Application Statement | Likely |  |  | They have submitted a draft application, and this is moving forward |  |  | Realistic |  |  |  | 1 | 0 | 0
BK | 316 | 473 | DCP ZAP | P2017K0368 | Brownsville North - Ocean Hill NCP Cluster | Active; Public Review | 32 |  |  | 32 |  | No | [8 empty] | n/a
BK | 316 | 14716 | HPD RFP | 100 | Brownsville Site A - Rockaway Avenue/Chester Street | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14717 | HPD RFP | 101 | Brownsville Site B - Christopher/Glenmore Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14721 | HPD RFP | 105 | MWBE Site C - 1510-1524 Broadway | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14722 | HPD RFP | 106 | Brownsville Site A - Rockaway Avenue/Chester Street | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14724 | HPD RFP | 108 | Brownsville Site A - Rockaway Avenue/Chester Street | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14725 | HPD RFP | 109 | Brownsville Site C - Livonia Sites | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14726 | HPD RFP | 11 | Brownsville Site C - Livonia Sites | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14727 | HPD RFP | 110 | Brownsville Site B - Christopher/Glenmore Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14729 | HPD RFP | 112 | Brownsville Site A - Rockaway Avenue/Chester Street | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14730 | HPD RFP | 113 | MWBE Site C - 1510-1524 Broadway | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14733 | HPD RFP | 116 | Brownsville Site C - Livonia Sites | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14734 | HPD RFP | 117 | Brownsville Site A - Rockaway Avenue/Chester Street | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14735 | HPD RFP | 118 | Brownsville Site A - Rockaway Avenue/Chester Street | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14737 | HPD RFP | 12 | Brownsville Site C - Livonia Sites | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14738 | HPD RFP | 120 | Brownsville Site B - Christopher/Glenmore Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14739 | HPD RFP | 121 | MWBE Site C - 1510-1524 Broadway | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14741 | HPD RFP | 123 | Brownsville Site A - Rockaway Avenue/Chester Street | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14743 | HPD RFP | 125 | Brownsville Site C - Livonia Sites | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14744 | HPD RFP | 126 | Brownsville Site A - Rockaway Avenue/Chester Street | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14749 | HPD RFP | 130 | Brownsville Site C - Livonia Sites | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14752 | HPD RFP | 133 | Brownsville Site A - Rockaway Avenue/Chester Street | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14758 | HPD RFP | 14 | Brownsville Site A - Rockaway Avenue/Chester Street | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14760 | HPD RFP | 16 | Brownsville Site C - Livonia Sites | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14766 | HPD RFP | 21 | Brownsville Site C - Livonia Sites | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14768 | HPD RFP | 23 | Brownsville Site B - Christopher/Glenmore Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14769 | HPD RFP | 24 | Brownsville Site C - Livonia Sites | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14770 | HPD RFP | 25 | Brownsville Site B - Christopher/Glenmore Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14772 | HPD RFP | 27 | Brownsville Site B - Christopher/Glenmore Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14776 | HPD RFP | 30 | Brownsville Site B - Christopher/Glenmore Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14777 | HPD RFP | 31 | Brownsville Site A - Rockaway Avenue/Chester Street | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14778 | HPD RFP | 32 | Brownsville Site A - Rockaway Avenue/Chester Street | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14780 | HPD RFP | 34 | Brownsville Site B - Christopher/Glenmore Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14782 | HPD RFP | 36 | Brownsville Site B - Christopher/Glenmore Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14783 | HPD RFP | 37 | Brownsville Site B - Christopher/Glenmore Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14784 | HPD RFP | 38 | Brownsville Site C - Livonia Sites | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14785 | HPD RFP | 39 | Brownsville Site A - Rockaway Avenue/Chester Street | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14791 | HPD RFP | 44 | Brownsville Site A - Rockaway Avenue/Chester Street | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14792 | HPD RFP | 45 | MWBE Site C - 1510-1524 Broadway | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14793 | HPD RFP | 46 | MWBE Site C - 1510-1524 Broadway | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14794 | HPD RFP | 47 | Brownsville Site C - Livonia Sites | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14796 | HPD RFP | 49 | MWBE Site C - 1510-1524 Broadway | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14800 | HPD RFP | 52 | Brownsville Site A - Rockaway Avenue/Chester Street | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14801 | HPD RFP | 53 | Brownsville Site C - Livonia Sites | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14806 | HPD RFP | 58 | Brownsville Site A - Rockaway Avenue/Chester Street | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14807 | HPD RFP | 59 | Brownsville Site C - Livonia Sites | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14808 | HPD RFP | 6 | Brownsville Site B - Christopher/Glenmore Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14810 | HPD RFP | 61 | MWBE Site C - 1510-1524 Broadway | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14812 | HPD RFP | 63 | Brownsville Site A - Rockaway Avenue/Chester Street | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14814 | HPD RFP | 65 | Brownsville Site B - Christopher/Glenmore Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14815 | HPD RFP | 66 | Brownsville Site B - Christopher/Glenmore Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14820 | HPD RFP | 70 | Brownsville Site C - Livonia Sites | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14826 | HPD RFP | 76 | Brownsville Site C - Livonia Sites | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14828 | HPD RFP | 78 | MWBE Site C - 1510-1524 Broadway | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14829 | HPD RFP | 79 | Brownsville Site B - Christopher/Glenmore Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14834 | HPD RFP | 83 | Brownsville Site B - Christopher/Glenmore Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14835 | HPD RFP | 84 | Brownsville Site A - Rockaway Avenue/Chester Street | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14843 | HPD RFP | 91 | Brownsville Site B - Christopher/Glenmore Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14844 | HPD RFP | 92 | Brownsville Site C - Livonia Sites | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14848 | HPD RFP | 96 | Brownsville Site B - Christopher/Glenmore Ave | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14851 | HPD RFP | 99 | MWBE Site C - 1510-1524 Broadway | RFP | [5 empty] | No | [8 empty] | n/a
BK | 316 | 14917 | Neighborhood Study | 1801 Pitkin Avenue (NIHOP and NCP Clusters) EAST NEW YORK REZONING COMMITMENT | 1801 Pitkin Avenue (NIHOP and NCP Clusters) EAST NEW YORK REZONING COMMITMENT |  |  |  | 12 units (4844 sqft * 2.43 FAR) |  |  | How many residential units do we expect from this commimitment site? |  |  | ? | ? | ? |  |  |  | n/a
BK | 316 | 15298 | Neighborhood Study | Christopher-Glenmore EAST NEW YORK REZONING COMMITMENT | Christopher-Glenmore EAST NEW YORK REZONING COMMITMENT |  |  | duplicate with HPD Brownsville Site B - Christopher/Glenmore Ave | 0 |  |  | How many residential units do we expect from this commimitment site? |  |  | likely | [5 empty] | Project may need to be removed |  |  |  | 1 | 0 | 0 |  |  |  |  | 1
BK | 316 | 15323 | Neighborhood Study | Hector's Court Men's Shelter Closure (NIHOP and NCP Clusters) EAST NEW YORK REZONING COMMITMENT | Hector's Court Men's Shelter Closure (NIHOP and NCP Clusters) EAST NEW YORK REZONING COMMITMENT |  |  |  | 50 units (11795 sqft * 4.2 FAR) |  |  | How many residential units do we expect from this commimitment site? |  |  | ? | ? | ? |  |  |  | n/a
BK | 316 | 85329 | map |  | 150 OSBORN STREET and nearby | info meeting |  | calculate from exist zoning | 106 units (43470 sqft * 2.43 FAR) | [6 empty] | somewhat likely |  |  |  |  | Realistic |  |  |  | 0 | 0.5 | 0.5 | [10 empty] | 1
BK | 316 | 85330 | map |  | 670 THOMAS S BOYLAND ST | info meeting |  | calculate from exist zoning | 53 units (21700 sqft * 2.43 FAR) | [6 empty] | somewhat likely |  |  |  |  | Realistic |  |  |  | 0 | 0.5 | 0.5 | [10 empty] | 1
BK | 317 | 85328 | map |  | 16 ERASMUS STREET (100% affordable) | PAS |  | calculate from exist zoning | 26 units (10898 sqft * 2.43 FAR) | [11 empty] | n/a | [16 empty] | 1
BK |  |  | City Hall public sites list | Current 10 | East New York North | Current RFP |  | ? |  |  |  | Does BKO have more info where this HPD RFP is located or how many total units? If so, please provide BBL & unit count. In Espinal's district. Developer is EBC. Estimated 41 affordable units - total units unknown. |  |  | ? | ? | ? |  |  |  | n/a
BK |  |  | City Hall public sites list | Current 37 | Bed Stuy East & Weeksville | Current RFP |  | ? |  |  |  | Does BKO have more info where this HPD RFP is located or how many total units? If so, please provide BBL & unit count. In Ampry-Samuel's district. Developer is Habitat. Estimated 69 affordable units - total units unknown. |  |  | ? | ? | ? |  |  |  | n/a
BK |  |  | City Hall public sites list | Current 40 | East New York South & East (NIHOP & NCP) | Current RFP |  | ? |  |  |  | Does BKO have more info where this HPD RFP is located or how many total units? If so, please provide BBL & unit count. In Barron & Espinal's district. Developer is MHANY & CHLDC. Estimated 69 affordable units - total units unknown. |  |  | ? | ? | ? |  |  |  | n/a
BK |  |  | City Hall public sites list | Current 41 | East New York South & West (NIHOP & NCP) | Current RFP |  | ? |  |  |  | Does BKO have more info where this HPD RFP is located or how many total units? If so, please provide BBL & unit count. In Barron's district. Developer is Rajoy & PM Architecture. Estimated 71 affordable units - total units unknown. |  |  | ? | ? | ? |  |  |  | n/a
BK |  |  | City Hall public sites list | Pipeline 22 | Fulton St Sites ( A + B - Seniors) | Pipeline RFP/RFEI |  | ? |  |  |  | Does BKO have more info where this HPD RFP is located or how many total units? If so, please provide BBL & unit count. In Ampry-Samuel's district. Estimated 300 affordable units - total units unknown. |  |  | ? | ? | ? |  |  |  | n/a
BK |  |  | City Hall public sites list | Pipeline 30 | DEP - Myrtle ST | Pipeline RFP/RFEI |  | ? |  |  |  | Does BKO have more info where this HPD RFP is located or how many total units? If so, please provide BBL & unit count. In Cumbo's district |  |  | ? | ? | ? |  |  |  | n/a