## MN Housing Pipeline
Boro | CD | Map ID | Source | Project ID | Project Name | Status | Total Units (from planner) | Notes on Total/KS assumed units | KS assumed units | Units remaining (not accounted for in other sources) | Lead Planner | Request for Update | Remaining units likely to be built? | Rationale | Remaining units likely to be built by 2025? (Likely/ Uncertain/ Not likely/ No units remaining) | Remaining units likely to be built by 2035? (Likely/ Uncertain/ Not likely/ No units remaining) | Remaining units likely to be built by 2055? (Likely/ Uncertain/ Not likely/ No units remaining) | Rationale for likely to be built / Other comments | Phasing (if known) | MQL View | Suggestion | Must get boro input | Response to MQL View | Portion Built 2025 | Portion Built 2035 | Portion Built 2055 | Outdated Overlapping Project | Non-Residential Project (incl. Group Quarters) | Withdrawn Project | Inactive Project | Other Reason to Omit | Corrected Existing Geometry | Corrected Existing Unit Count | Updated Unit Count | Should be in old ZAP Pull | Should be in new ZAP Pull | Planner Added Project
MN | 101 | 40 | DCP | P2007M0206 | 50 LISPENARD ST | Complete; Pre-Cert | 5 |  |  |  | Grace Han | How many residential units do we expect this project to introduce? | [7 empty] | n/a
MN | 101 | 41 | DCP | P2009M0216 | 11 HUBERT ST | Complete; Pre-Cert | 1 |  |  |  | Alison Brown | How many residential units do we expect this project to introduce? | [7 empty] | n/a
MN | 101 | 60 | DCP | P2012M0081 | 83 WALKER ST | Complete; Completed | 9 |  |  | 0 |  | No | [7 empty] | n/a
MN | 101 | 61 | DCP | P2012M0178 | 47-50 WEST STREET | Complete; Completed | 300 |  |  | 300 |  | No | [7 empty] | n/a
MN | 101 | 63 | DCP | P2012M0261 | 84 WHITE STREET | Complete; Completed | 33 |  |  | 33 |  | No | [7 empty] | n/a
MN | 101 | 64 | DCP | P2012M0264 | Text Amendment to Special TMU | Complete; Completed | 33 |  |  | 0 |  | No | [7 empty] | n/a
MN | 101 | 76 | DCP | P2012M0307 | 415 GREENWICH STREET | Complete; Completed | 90 |  |  | 90 |  | No | [7 empty] | n/a
MN | 101 | 83 | DCP | P2012M0512 | 70 PINE ST ROOFTOP RECREATION | Complete | 600 |  |  | 0 |  | No | [7 empty] | n/a
MN | 101 | 230 | DCP | P2014M0488 | 70 Vestry St - Parking Facility | Complete; Completed | 47 |  |  | 47 | [9 empty] | n/a
MN | 101 | 340 | DCP | P2015M0542 | 140 West Street Rooftop Rec Waiver | Complete; Pre-Cert | 158 |  |  | 158 |  | No | [7 empty] | n/a
MN | 101 | 85114 | map |  | 456 Greenwich Street | Waiting DOB approval | 0 |  |  |  | Alison Brown | [6 empty] | 8 story hotel proposed, not yet DOB approved |  | Project not counted | [7 empty] | 1 | [8 empty] | 1
MN | 101 | 85115 | map |  | Independence Plaza/ 310 Greenwich Street |  | 120 | Planner input: 80-160. Taking average. |  |  | Alison Brown |  |  |  |  | uncertain |  | possibility of adding 4th, 39 story tower. residential tower. ~80 - 160 units (assuming 2-4 units per floor?) |  | Potentially aggressive | Include in 2055 unless in ZAP |  |  | 0 | 0 | 1 | [10 empty] | 1
MN | 101 | 85116 | map |  | 124/125 White Street |  | 0 |  |  |  | Alison Brown | [6 empty] | BBJ Proposal - increase of ~500 "beds" from current MDC site |  | Project not counted | Only res from Rikers is in Bronx | [6 empty] | 1 | [8 empty] | 1
MN | 101 | 85117 | map |  | 72 Nassau Street |  | 60 |  |  |  | Alison Brown |  |  |  | uncertain |  |  | BBJ Proposal - increase of ~500 "beds" from current MDC site |  | Potentially aggressive | Include in 2055 unless in ZAP |  |  | 0 | 0 | 1 | [10 empty] | 1
MN | 102 | 71 | DCP | P2012M0293 | 62 Wooster Street | Complete; Completed | 11 |  |  | 11 |  | No | [7 empty] | n/a
MN | 102 | 73 | DCP | P2012M0303 | 111 Mercer Street | Complete; Completed | 4 |  |  | 4 |  | No | [7 empty] | n/a
MN | 102 | 74 | DCP | P2012M0304 | IN GOD'S LOVE WE DELIVER | Complete; Completed | 79 |  |  | 79 |  | No | [7 empty] | n/a | [7 empty] | 0
MN | 102 | 80 | DCP | P2012M0485 | 325 West Broadway Renewal | Complete; Completed | 53 |  |  | 31 |  | No | [7 empty] | Project may need to be removed | Is this a dupe? |  | No overlaps in ZAP. It does not seem to be a duplicate.
MN | 102 | 86 | DCP | P2012M0582 | 688 Broadway | Complete; Completed | 16 |  |  | 0 |  | No | [7 empty] | n/a
MN | 102 | 87 | DCP | P2012M0586 | 36 Bleecker Street | Complete; Completed | 20 |  |  | 1 |  | No | [7 empty] | n/a
MN | 102 | 88 | DCP | P2012M0587 | 498 Broome Street | Complete; Completed | 4 |  |  | 4 |  | No | [7 empty] | n/a
MN | 102 | 143 | DCP | P2013M0024 | 37 Great Jones Street | Active; Completed | 3 |  |  |  |  | No | [7 empty] | n/a
MN | 102 | 146 | DCP | P2013M0188 | 150 Charles Street | Complete; Completed | 97 |  |  | 97 |  | No | [7 empty] | n/a
MN | 102 | 151 | DCP | P2013M0451 | 102 Greene Street | Active; Completed | 0 |  |  |  |  | No | [5 empty] | Marked for deletion by planner |  | Project removed | [10 empty] | 1
MN | 102 | 153 | DCP | P2013M0520 | 42 Crosby Street | Complete; Completed | 10 |  |  | 0 |  | No | [7 empty] | n/a
MN | 102 | 215 | DCP | P2014M0166 | 41 Great Jones Street | Complete; Completed | 3 |  |  | 2 |  | No | [7 empty] | n/a
MN | 102 | 221 | DCP | P2014M0257 | 550 Washington St- Special Hudson River Park Distr | Complete; Completed | 593 |  |  |  |  | No | [7 empty] | n/a
MN | 102 | 231 | DCP | P2014M0522 | 40 Wooster Street - 74-711 | Complete | 4 |  |  | 0 |  | No | [7 empty] | n/a
MN | 102 | 232 | DCP | P2014M0524 | 57-63 Greene Street (New SP for Additional Units) | Active; Pre-Cert | 15 |  |  | 6 |  | No | [7 empty] | n/a
MN | 102 | 320 | DCP | P2015M0010 | 601 Washington Street Parking Garage | On-Hold; Pre-Cert | 8 |  |  | 0 |  | No | [7 empty] | n/a
MN | 102 | 329 | DCP | P2015M0238 | SoHo Tower - FA Preservation Cert | Complete; Completed | 0 |  |  |  |  | No | [5 empty] | Marked as double counted by planner |  | Project removed | [10 empty] | 1
MN | 102 | 339 | DCP | P2015M0502 | 10 Greene Street | Complete; Completed | 4 |  |  | 0 |  | No | [7 empty] | n/a
MN | 102 | 420 | DCP | P2016M0421 | 21 E 12th Street Parking Garage | Complete; Completed | 53 |  |  | 53 |  | No | [7 empty] | n/a
MN | 102 | 476 | DCP | P2017M0001 | SoHo Tower Parking Garage | Complete; Completed | 115 |  |  | 115 |  | No | [7 empty] | n/a
MN | 102 | 545 | DCP | P2018M0251 | HPD Haven Green Senior Housing | Active; Public Review | 0 |  |  |  |  | No | [5 empty] | Marked for deletion by planner |  | Project removed | [10 empty] | 1
MN | 102 | 546 | DCP | P2018M0291 | 52 Elizabeth Street - parking | Active; Pre-Cert | 38 |  |  | 38 |  | No | [7 empty] | n/a
MN | 102 | 14830 | HPD RFP | 8 | Mott-Elizabeth Streets | RFP | 123 |  |  |  |  | No | [7 empty] | n/a
MN | 102 | 85107 | map |  | 388 HUDSON STREET |  | 172 | [9 empty] | likely | 172 units estimated from HPD |  | Potentially aggressive | Include in 2055 unless in ZAP |  |  | 0 | 0 | 1 | [10 empty] | 1
MN | 102 | 85108 | map |  | Union Square South (rezoning?) |  | 1650 | [7 empty] | uncertain |  |  |  |  | Potentially aggressive | Include in 2055 unless in ZAP |  |  | 0 | 0 | 1 | [10 empty] | 1
MN | 102 | 85132 | map |  | NYU Core |  |  |  | 588.2353 | [8 empty] | 1.5 mil sqft for student housing and .5 mil sqft for faculty housing |  | No inputs given | Include in 2055 |  |  | 0 | 0 | 1 | [10 empty] | 1
MN | 102 |  | City Hall public sites list | Pipeline 1 | 131 Sixth Ave |  | 155 | Planner input: 130-170. Taking average. |  |  | Sylvia Li | How many total residential units? What is the phasing (# of units by X year)? |  |  | uncertain |  |  | ECF just sent me there RFEI. There’re four potential options for future developments, two of which contemplate residential development with IH business. Based on standard assumptions (20% loss factor and 850 sf unit size), unit count would range between 130 – 170 |  | Potentially aggressive | Include in 2035 |  |  | 0 | 1 | 0 | [6 empty] | 1 | 150
MN | 103 | 33 | DCP | 2019M0197 | Seward Park Extension Minor Modification | Active; Pre-Cert | 0 |  |  |  |  | No | [5 empty] | Doesn't generate units |  | Project not counted | [7 empty] | 1
MN | 103 | 69 | DCP | P2012M0291 | East Houston Street Rezoning | Active; Completed | 88 |  |  |  |  | No | [7 empty] | n/a
MN | 103 | 70 | DCP | P2012M0292 | SEWARD PARK MIXED-USE DEVELOPMENT PROJECT | Complete; Completed | 1000 |  |  |  |  | No | [7 empty] | n/a
MN | 103 | 79 | DCP | P2012M0479 | Two Bridges (HealthCare Chaplaincy) | Complete; Completed | 120 |  |  | 120 |  | No | [5 empty] | Wrong location - not going forward |  | Project removed | [8 empty] | 1
MN | 103 | 149 | DCP | P2013M0405 | 333 Broome Street | On-Hold; Pre-Cert | 0 |  |  |  | Edwin Marshall | How many residential units do we expect this project to introduce? | [5 empty] | Likely to be terminated |  | Project removed | [10 empty] | 1
MN | 103 | 212 | DCP | P2014M0022 | Two Bridges LSRD -- Site 4A (ParkIt Mgmt) | On-Hold; Pre-Cert | 0 |  |  |  |  | No | [5 empty] | Marked for deletion by planner - project terminated |  | Project removed | [8 empty] | 1
MN | 103 | 323 | DCP | P2015M0120 | 66 Allen Street | Complete; Completed | 8 |  |  |  |  | No | [7 empty] | n/a
MN | 103 | 326 | DCP | P2015M0228 | Go Broome Street Development (50 Norfolk St) | Active; Pre-Cert | 488 |  |  | 488 |  | No | [7 empty] | n/a
MN | 103 | 343 | DCP | P2015M0599 | Two Bridges - LSRD Mod - 260 South St (5) | Active; Public Review | 1350 |  |  | 1350 |  | No | [5 empty] | Technically complete but in litigation |  | No inputs given | Include 50% in 2035 and 50% in 2055 |  |  | 0 | 0.5 | 0.5
MN | 103 | 416 | DCP | P2016M0321 | Two Bridges - LSRD Mod - 247 Cherry St (4A-4B) | Active; Public Review | 660 |  |  | 660 |  | No | [5 empty] | Technically complete but in litigation |  | No inputs given | Include 50% in 2035 and 50% in 2055 |  |  | 0 | 0.5 | 0.5
MN | 103 | 417 | DCP | P2016M0334 | Two Bridges - LSRD Mod - 259 Clinton St (6A) | Active; Public Review | 765 |  |  | 765 |  | No | [5 empty] | Technically complete but in litigation |  | No inputs given | Include 50% in 2035 and 50% in 2055 |  |  | 0 | 0.5 | 0.5
MN | 103 | 482 | DCP | P2017M0370 | 302 East 2nd Street and 276 East 3rd Street | No ULURP needed | 55 |  |  | 55 | Matthew Pietrus | In mid-year 2018, you had provided feedback that this project was UNCERTAIN to be built by 2025. Is this still the case? If not, what is the likelihood that this project will be built by 2025? By 2035? | Uncertain | HPD financing uncertain | uncertain |  |  |  |  | Potentially aggressive | Include in 2035 if not appearing on HPD pre-closings list |  | Appears in Pre-Closings | 1 | 0 | 0
MN | 103 | 538 | DCP | P2018M0127 | Lower East Side Minor Modification(Grand St Guild) | Active; Pre-Cert | 652 |  |  | 652 |  | No | [7 empty] | n/a
MN | 103 | 540 | DCP | P2018M0155 | East Village Housing (204 Ave A and 535 E 12th St) | Complete | 21 |  |  | 21 |  | No | [7 empty] | n/a
MN | 103 | 14831 | HPD RFP | 80 | NYCHA LaGuardia | RFP | [5 empty] | No | [7 empty] | n/a
MN | 103 | 14849 | HPD RFP | 97 | NYCHA Senior - Baruch | RFP | [5 empty] | No | [7 empty] | n/a
MN | 103 | 85109 | map |  | Potential rezoning C6-2A -> C6-3X (north of Cooper Square) |  | 170 | [8 empty] | uncertain |  |  |  | Potentially aggressive | Include in 2055 unless in ZAP |  |  | 0 | 0 | 1 | [10 empty] | 1
MN | 103 | 85110 | map | 2019M0319 | Campos Plaza II (Build to Preserve) | Active; Pre-Cert | 173 | [7 empty] | uncertain |  |  |  |  | Realistic | Same as other NYCHA - 50% in 2025 |  | I believe that this is part of Public Sites -- would make sense to add to that unit count. | 0.5 | 0.5 | 0 | [10 empty] | 1
MN | 103 | 85111 | map |  | Meltzer Apts (Build to Preserve) |  | 146 | [8 empty] | uncertain |  |  |  | Potentially aggressive | Include in 2055 unless in ZAP |  |  | 0 | 0 | 1 | [10 empty] | 1
MN | 103 | 85112 | map |  | Seward Park Extension A (Build to Preserve) |  | 136 | [8 empty] | uncertain |  |  |  | Potentially aggressive | Include in 2055 unless in ZAP |  |  | 0 | 0 | 1 | [10 empty] | 1
MN | 103 | 85113 | map |  | Seward Park Extension B (Build to Preserve) |  | 108 | [8 empty] | uncertain |  |  |  | Potentially aggressive | Include in 2055 unless in ZAP |  |  | 0 | 0 | 1 | [10 empty] | 1
MN | 104 | 42 | DCP | P2009M0294 | WESTERN RAIL YARDS | Complete; Completed | 5193 | Planner input: 5193 in map |  |  | Basha Gerhards | This is a large project, what are the latest phasing plans for this project (break down as much as possible ## of units by a specific year)? | [7 empty] | n/a | [12 empty] | 1 | 5193
MN | 104 | 62 | DCP | P2012M0258 | DURST W57 | Complete; Completed | 863 |  |  | 863 |  | No | [7 empty] | n/a
MN | 104 | 75 | DCP | P2012M0305 | CURA Site 7 | Complete; Completed | 530 |  |  | 14 |  | No | [7 empty] | n/a
MN | 104 | 78 | DCP | P2012M0387 | 605 West 42nd Street (HY parking cert) | Complete; Completed | 1168 |  |  | 0 |  | No | [7 empty] | n/a
MN | 104 | 84 | DCP | P2012M0564 | 505-513 West 43rd Street | Complete; Completed | 190 |  |  | 59 |  | No | [7 empty] | n/a
MN | 104 | 85 | DCP | P2012M0566 | Fulton Houses | Complete; Completed | 158 |  |  | 0 |  | No | [7 empty] | n/a
MN | 104 | 89 | DCP | P2012M0635 | 606 West 57th Street (TF Cornerstone) | Complete; Completed | 1189 |  |  | 78 |  | No | [7 empty] | n/a
MN | 104 | 216 | DCP | P2014M0169 | 537-545 W. 37th St. (ERYTDR & Res. Cert.) | Complete; Completed | 131 |  |  |  | Annie White | How many residential units do we expect this project to introduce? | [7 empty] | n/a
MN | 104 | 218 | DCP | P2014M0186 | 520 West 28th Street (parking special permit) | Complete; Completed | 41 |  |  | 41 |  | No | [7 empty] | n/a
MN | 104 | 223 | DCP | P2014M0298 | 530 West 28 Street (parking special permit) | Complete; Completed | 36 |  |  | 36 |  | No | [7 empty] | n/a
MN | 104 | 226 | DCP | P2014M0333 | Covenant House | On-Hold; Pre-Pas | 988 |  |  | 988 |  | No |  |  | not likely | not likely | uncertain |  |  | Potentially conservative | Override with generic build year rules |  | Planner said this project is "dead". Placing in 2055? | 0 | 0 | 1
MN | 104 | 227 | DCP | P2014M0430 | 551 Tenth Ave. (HY DIB application) | Complete; Completed | 598 |  |  | 598 |  | No | [7 empty] | n/a
MN | 104 | 229 | DCP | P2014M0470 | The Windermere | Active; Pre-Cert | 20 |  |  | 20 | Joseph Huennekens | ZAP currently only includes information on units associated with MIH and voluntary affordable housing for this project. How many total residential units do we expect this project to introduce? | [7 empty] | n/a
MN | 104 | 319 | DCP | P2015M0004 | 537-545 W. 37th Street (DIB application) | Complete; Completed | 131 |  |  | 131 |  | No | [7 empty] | n/a
MN | 104 | 325 | DCP | P2015M0209 | 509 W. 38th Street (DIB with IH) | Complete; Public Review | 179 |  |  | 179 |  | No | [7 empty] | n/a
MN | 104 | 330 | DCP | P2015M0247 | 3 Hudson Blvd (DIB, ERYTDR, office & res certs) | On-Hold; Pre-Cert | 0 |  |  | 0 | Annie White | In mid-year 2018, you had provided feedback that this project was LIKELY expected to be built by 2025. However, it has moved from active to on-hold. What is the likelihood that this project will be built by 2025? By 2035? | Likely |  |  |  |  | This project dropped their residential program. Revised Certs to drop Residential Cert. |  | Project not counted | [7 empty] | 1
MN | 104 | 337 | DCP | P2015M0487 | 532 West 20th St (parking special permits) | Complete; Completed | 9 |  |  | 0 |  | No | [7 empty] | n/a
MN | 104 | 410 | DCP | P2016M0148 | 520 West 41st Street (DIB, ERY, 93-122) | Active; Pre-Cert | 1400 |  |  | 901 |  | No | [7 empty] | n/a
MN | 104 | 412 | DCP | P2016M0240 | Section 93-122 Text Amendment | Complete; Completed | 400 |  |  | 400 |  | No | [7 empty] | n/a
MN | 104 | 414 | DCP | P2016M0289 | 601 West 29th Street (Block 675 - Douglaston) | Active; Completed | 990 |  |  | 59 |  | No | [7 empty] | n/a
MN | 104 | 477 | DCP | P2017M0157 | 606 West 30th Street (Block 675 - Lalezarian) | Active; Completed | 252 |  |  | 252 |  | No | [7 empty] | n/a
MN | 104 | 481 | DCP | P2017M0358 | Slaughterhouse -HY Subdistrict (495 11th Ave) | Active; Pre-Cert | 250 |  |  | 250 |  | No | [7 empty] | n/a
MN | 104 | 547 | DCP | P2018M0308 | 201-207 7th Avenue Dispo | Active; Pre-Cert | 26 |  |  | 26 |  | No | [7 empty] | n/a
MN | 104 | 14759 | HPD RFP | 15 | NYCHA Harborview Terrace | RFP | [5 empty] | No | [7 empty] | n/a
MN | 104 | 14787 | HPD RFP | 40 | Clinton Hell's Kitchen - MTA Site at 54th St and 9th Ave | RFP | [5 empty] | No | [7 empty] | n/a
MN | 104 | 14818 | HPD RFP | 69 | Slaughterhouse - EDC | RFP | [5 empty] | No | [7 empty] | n/a
MN | 104 | 14838 | HPD RFP | 87 | Clinton/Hell's Kitchen - DEP/Amtrak Site | RFP | [5 empty] | No | [7 empty] | n/a
MN | 104 | 14846 | HPD RFP | 94 | NYCHA Harborview Terrace | RFP | [5 empty] | No | [7 empty] | n/a
MN | 104 | 85101 | map |  | 260 12 AVENUE (Georgetown) |  | 1200 | [8 empty] | likely |  |  |  | Potentially aggressive | Include in 2055 unless in ZAP |  |  | 0 | 0 | 1 | [10 empty] | 1
MN | 104 | 85102 | map |  | Fulton Houses - Build to Preserve |  |  | ? | [11 empty] | n/a | [16 empty] | 1
MN | 104 | 85103 | MNO |  | 629 West 54th St (rezoning + Hudson River Park Transfers) | Pre-PAS | 660 |  |  |  | Annie White |  |  |  |  | uncertain |  | We have heard interest in rezoning properties in West Clinton to support residential development through rezoning + Hudson River Park Transfers. The two properties in pre-PAS phase currently are 801 11th Ave (550 units) and 629 West 54th St (660 units). Both of these unit numbers are aggressive estimates. There could be opportunity for more properties to follow this model in West Clinton, but nothing yet is on the table. |  | Realistic |  |  |  | 0 | 0.5 | 0.5 | [10 empty] | 1
MN | 104 | 85104 | MNO |  | 801 11th Ave (rezoning + Hudson River Park Transfers) | Pre-PAS | 550 |  |  |  | Annie White |  |  |  |  | uncertain |  | We have heard interest in rezoning properties in West Clinton to support residential development through rezoning + Hudson River Park Transfers. The two properties in pre-PAS phase currently are 801 11th Ave (550 units) and 629 West 54th St (660 units). Both of these unit numbers are aggressive estimates. There could be opportunity for more properties to follow this model in West Clinton, but nothing yet is on the table. |  | Realistic |  |  |  |  | 0.5 | 0.5 | [10 empty] | 1
MN | 104 | 85105 | map |  | 314 WEST 43 STREET |  | 370 | [12 empty] | n/a | [16 empty] | 1
MN | 104 | 85106 | map |  | 536 WEST 23 STREET (U-haul) |  | 140 | [12 empty] | n/a | [16 empty] | 1
MN | 105 | 39 | DCP | P2005M0053 | HUDSON YARDS | Complete; Completed | 13508 |  |  | 8197 | Kenny Ramnarine | This is a large project, what are the latest phasing plans for this project (break down as much as possible ## of units by a specific year)? | [7 empty] | n/a
MN | 105 | 65 | DCP | P2012M0276 | 5 EAST 20TH STREET | Complete; Pre-Cert | 1 |  |  |  | Adam Wolff | How many residential units do we expect this project to introduce? | [7 empty] | n/a
MN | 105 | 81 | DCP | P2012M0490 | 872 Broadway | Complete; Completed | 3 |  |  |  | Frank Ruchala | How many residential units do we expect this project to introduce? | [7 empty] | n/a
MN | 105 | 144 | DCP | P2013M0126 | 230 W. 36th Street (Verizon) | On-Hold; Pre-Pas | 109 |  |  | 109 |  | No |  |  | not likely | uncertain | uncertain |  |  | Potentially conservative | Override with generic build year rules
MN | 105 | 145 | DCP | P2013M0127 | 39-41 W. 23rd Street | Complete; Completed | 42 |  |  | 0 |  | No | [7 empty] | n/a
MN | 105 | 152 | DCP | P2013M0466 | 7 W 21st Street Garage | Complete; Completed | 300 |  |  | 11 |  | No | [7 empty] | n/a
MN | 105 | 214 | DCP | P2014M0161 | 43 East 20th Street - Res Conversion | Active; Pre-Cert | 2 |  |  | 2 |  | No | [7 empty] | n/a
MN | 105 | 217 | DCP | P2014M0179 | W. 29th Street Parking and Text | Complete; Completed | 95 |  |  | 95 |  | No | [7 empty] | n/a
MN | 105 | 322 | DCP | P2015M0077 | 150 Wooster Street - 2014 | Complete; Completed | 28 |  |  | 28 |  | No | [7 empty] | n/a
MN | 105 | 331 | DCP | P2015M0294 | 7 E. 19th Street - Res Conversion | Complete; Completed | 4 |  |  | 4 |  | No | [7 empty] | n/a
MN | 105 | 342 | DCP | P2015M0563 | 129-131 Fifth Ave - Residential Conversion | Complete; Completed | 1 |  |  |  | Bob Tuttle | How many residential units do we expect this project to introduce? | [7 empty] | n/a
MN | 105 | 406 | DCP | P2016M0032 | 21-37 W. 25th Street Rezoning | On-Hold; Pre-Cert | 339 |  |  | 339 |  | No | [7 empty] | n/a
MN | 105 | 407 | DCP | P2016M0101 | 110 E 16th St - 74-711 | Active; Public Review | 55 |  |  | 55 |  | No | [7 empty] | n/a
MN | 105 | 419 | DCP | P2016M0356 | 213-227 West 28th Street parking special permits | Active; Pre-Cert | 200 |  |  | 200 |  | No | [7 empty] | n/a
MN | 105 | 484 | DCP | P2017M0443 | 262 Fifth Ave parking special permit | Active; Pre-Cert | 41 |  |  | 0 |  | No | [7 empty] | n/a
MN | 105 | 537 | DCP | P2018M0124 | 25 E. 21st Street - Gramercy Condominium | Active; Pre-Cert | 10 |  |  |  | Ezra Moser | How many residential units do we expect this project to introduce? | [7 empty] | n/a
MN | 106 | 72 | DCP | P2012M0298 | Rivergate | Complete; Completed | 34 |  |  | 0 |  | No | [7 empty] | n/a
MN | 106 | 77 | DCP | P2012M0309 | Cornell NYC Tech Campus | Complete; Completed | 1094 |  |  | 742 |  | No | [6 empty] | The phasing plan upon approval in 2013 was for the completion of 271 units of faculty housing and 171 units of student housing by 2018, and 798 units of faculty housing and 296 units of student housing by 2038 (note that the latter numbers are total units and include the first phase units). | n/a |  |  | View is realistic. | 0 | 0 | 1 | [6 empty] | 1 | 798
MN | 106 | 147 | DCP | P2013M0316 | adAPT | Complete; Completed | 55 |  |  | 0 |  | No | [7 empty] | n/a
MN | 106 | 148 | DCP | P2013M0347 | Brookdale Campus - LSGD | On-Hold; Pre-Cert | 764 |  |  | 764 | Bob Tuttle | In mid-year 2018, you had provided feedback that this project was LIKELY expected to be built by 2025. However, it has moved from active to on-hold. What is the likelihood that this project will be built by 2025? By 2035? - There is a necessity for the project but momentum is dependent on Council member support, which currently does not exist. | Likely |  |  | likely |  |  |  | Realistic |  |  |  | 0 | 1 | 0
MN | 106 | 219 | DCP | P2014M0188 | 237 E. 34th Street (transit land use application) | Complete; Completed | 79 |  |  | 0 |  | No | [7 empty] | n/a
MN | 106 | 220 | DCP | P2014M0226 | 252 East 57th Street | Complete; Completed | 270 |  |  | 270 |  | No | [7 empty] | n/a
MN | 106 | 408 | DCP | P2016M0127 | East River Fifties_Sutton Place - Text Amendment | Complete; Completed | 0 |  |  | 0 |  | No | [5 empty] | withdrawn |  | Project removed | [8 empty] | 1
MN | 106 | 409 | DCP | P2016M0133 | East 33rd St Rezoning | Complete; Completed | 115 |  |  | 115 |  | No | [7 empty] | n/a
MN | 106 | 536 | DCP | P2018M0060 | East River Fifties - Text Amendment | Complete; Completed | 0 |  |  | 0 |  | No | [5 empty] | Areawide, not associated wth any specific development sites. |  | Project removed | [10 empty] | 1
MN | 106 | 85133 | MNO | Block 970, Lot 1 | East River Realty Co | Complete; Vested | 2275 | [7 empty] | Likely |  |  | Special permit already vested and portions of the larger project are being completed now at 685 First Ave and 626 First Ave |  | Realistic | Need to get remaining units after de-duping with DOB |  |  | 1 | 0 | 0 | [10 empty] | 1
MN | 106 | 85134 | MNO | Block 934, Lot 1 | Kips Bay Court | Active; Pre-Cert | 260 |  |  |  | Scott Williamson |  |  |  | Likely |  |  | Projected build year 2023. |  | Realistic |  |  |  | 1 | 0 | 0 | [10 empty] | 1
MN | 107 | 15 | DCP | 2018M0467 | 266 West 96th Street | Active; Pre-Cert | 170 |  |  | 170 |  | No | [7 empty] | n/a
MN | 107 | 68 | DCP | P2012M0285 | West 106th street rezoning | Complete; Completed | 597 |  |  | 597 | Calvin Brown | This project has not materialized in DOB permits despite being certified before mid-2017. What is the likelihood that this project will be built by 2025? By 2035? | Likely |  |  | likely |  | I would say 2035. The nursing home was supposed to move to a 96th Street site to facilitate the development of the 106th Street site once vacated. However, there has been some legal challenges that have delayed construction. |  | Realistic |  |  |  | 0 | 1 | 0
MN | 107 | 338 | DCP | P2015M0488 | West 108th St WSFSSH | Complete; Completed | 281 |  |  | 49 |  | No | [7 empty] | n/a
MN | 107 | 85124 | map |  | NYCHA BTP (865 AMSTERDAM AVENUE, no upzone needed) |  | 875 | [8 empty] | uncertain |  |  |  | Project may need to be removed | Do not count any more NYCHA projects beyond what's in existing spreadsheets | [9 empty] | 1
MN | 107 | 85125 | map |  | NYCHA BTP (865 AMSTERDAM AVENUE, upzone to R8) |  | 1000 | [8 empty] | uncertain |  |  |  | Project may need to be removed | Do not count any more NYCHA projects beyond what's in existing spreadsheets | [9 empty] | 1
MN | 107 | 85126 | map |  | Silverstein (WEST END AVENUE & W 65 St) |  |  | calculate from exist zoning | 476 units (47606 sqft * 10 FAR) | [5 empty] | uncertain | likely |  |  |  | Potentially aggressive | Include in 2055 unless in ZAP |  |  | 0 | 0 | 1 | [6 empty] | 1 | 476
MN | 108 | 31 | DCP | 2019M0056 | East 94th Street Rezoning | Active; Pre-Cert | 560 |  |  | 560 |  | No | [7 empty] | n/a
MN | 108 | 82 | DCP | P2012M0498 | 203-205 EAST 92ND STREET POPS | Complete; Pre-Cert | 231 |  |  | 0 |  | No | [7 empty] | n/a
MN | 108 | 224 | DCP | P2014M0299 | 20 East 71st Street | Complete; Completed | 1 |  |  | 0 |  | No | [7 empty] | n/a
MN | 108 | 321 | DCP | P2015M0067 | 302 East 96th Street (transit easement) | Complete; Completed | 55 |  |  | 7 |  | No | [7 empty] | n/a
MN | 108 | 334 | DCP | P2015M0374 | 660 Madison Text Amendment | On-Hold; Pre-Cert | 24 |  |  | 0 |  | No | [7 empty] | n/a
MN | 108 | 341 | DCP | P2015M0547 | 19 East 70th Street | Complete; Completed | 1 |  |  | 1 |  | No | [7 empty] | n/a
MN | 108 | 415 | DCP | P2016M0303 | 172-174 East 73rd Street (74-711 special permit) | Complete; Completed | 2 |  |  | 2 |  | No | [7 empty] | n/a
MN | 108 | 14795 | HPD RFP | 48 | NYCHA Holmes | RFP | [5 empty] | No | [7 empty] | n/a
MN | 108 | 85127 | MNO | Block 1411, Lot 1 and 113 | Lenox Hill Hospital | Active; Pre-Cert | 200 |  |  |  | Scott Williamson |  |  |  | Likely |  |  | Units likely to be completed first to pay for the hospital. |  | Realistic |  |  |  | 1 | 0 | 0 | [10 empty] | 1
MN | 109 | 479 | DCP | P2017M0265 | 135th Street -12th Avenue Rezoning | Active; Pre-Cert | 60 |  |  | 60 |  | No | [7 empty] | n/a
MN | 109 | 85118 | map |  | W 142 Street Rezoning (R6A -> R9A/MIH) | Proposed | 89 | [7 empty] | ? |  |  |  |  | Potentially aggressive | Include in 2055 unless in ZAP |  |  | 0 | 0 | 1 | [10 empty] | 1
MN | 109 | 85119 | map |  | Columbia/Manhattanville campus |  | 0 | [10 empty] | 6.8 mil sqdt floor area. No residential. ~350,000 to 1.3 mil sqft student housing. |  | Project not counted | [7 empty] | 1 | [8 empty] | 1
MN | 109 | 85120 | map |  | 614 WEST 125 STREET (Trustees of Columbia) |  | 220 | [8 empty] | uncertain |  | 220 units possible if upzoned to R10 |  | Potentially aggressive | Include in 2055 unless in ZAP |  |  | 0 | 0 | 1 | [10 empty] | 1
MN | 109 | 85121 | map |  | Union Theological Seminary AOR Tower (3041 BROADWAY) |  | 175 | [7 empty] | ? |  |  |  |  | Potentially aggressive | Include in 2055 unless in ZAP |  |  | 0 | 0 | 1 | [10 empty] | 1
MN | 109 | 85122 | map |  | Riverside Church air rights |  | 175 | [8 empty] | uncertain |  | Riverside church has air rights looking to sell - may add housing/tower on their campus. |  | Potentially aggressive | Include in 2055 unless in ZAP |  |  | 0 | 0 | 1 | [10 empty] | 1
MN | 109 | 85123 | map |  | 2861 BROADWAY (possible upzone to R10) |  | 200 | [7 empty] | ? |  |  |  |  | Potentially aggressive | Include in 2055 unless in ZAP |  |  | 0 | 0 | 1 | [10 empty] | 1
MN | 110 | 32 | DCP | 2019M0176 | 114th-115th Street Rezoning | Active; Pre-Pas | 500 |  |  | 500 |  | No | [7 empty] | n/a
MN | 110 | 66 | DCP | P2012M0277 | HARLEM DOWLING | Complete; Completed | 58 |  |  | 0 |  | No | [7 empty] | n/a
MN | 110 | 67 | DCP | P2012M0278 | Lenox Terrace | Active; Pre-Cert | 1642 |  |  |  |  | No | [7 empty] | n/a
MN | 110 | 90 | DCP | P2012M0680 | West 117th Street Rezoning | Complete; Completed | 220 |  |  | 115 | Calvin Brown | In mid-year 2018, you had provided feedback that this project was UNCERTAIN to be built by 2025. Is this still the case? If not, what is the likelihood that this project will be built by 2025? By 2035? | Uncertain | Existing uses still in place | likely |  |  | Under construction |  | Project may need to be removed | Check if DOB |  | Multiple developments included this ZAP project. The remaining 115 units should be included. | 1 | 0 | 0
MN | 110 | 150 | DCP | P2013M0432 | 492 Saint Nicholas Avenue | Complete; Completed | 10 |  |  | 0 |  | No | [7 empty] | n/a
MN | 110 | 154 | DCP | P2013M0523 | Greater Harlem Nursing Home and Rehab | Complete; Completed |  | Planner input: 30 beds |  |  | Calvin Brown | How many residential units do we expect this project to introduce? | [7 empty] | n/a |  |  | This is group quarters. |  |  |  |  | 1
MN | 110 | 213 | DCP | P2014M0068 | 260-264 West 153rd Street | Complete; Completed | 51 |  |  | 0 |  | No | [7 empty] | n/a
MN | 110 | 225 | DCP | P2014M0332 | Strivers Plaza FRESH | Complete; Completed | 54 |  |  | 0 |  | No | [7 empty] | n/a
MN | 110 | 327 | DCP | P2015M0236 | The Robeson 407 Lenox Avenue | Active; Completed | 79 |  |  | 0 |  | No | [7 empty] | n/a
MN | 110 | 328 | DCP | P2015M0237 | The Leroy 225 West 140th Street | Complete; Completed | 20 |  |  | 0 |  | No | [7 empty] | n/a
MN | 110 | 332 | DCP | P2015M0320 | CUCS West 127th Supportive Hsing | Complete; Completed | 116 |  |  | 116 |  | No | [7 empty] | n/a
MN | 110 | 333 | DCP | P2015M0359 | Harlem Renaissance 2012 NBT Way Project | Complete; Completed | 240 |  |  | 240 | Edwin Marshall | This project has not materialized in DOB permits despite being certified before mid-2017. What is the likelihood that this project will be built by 2025? By 2035? | Likely |  | likely |  |  |  |  | Realistic |  |  |  | 1 | 0 | 0
MN | 110 | 335 | DCP | P2015M0428 | 2395 Frederick Douglass Boulevard | Active; Completed | 74 |  |  | 0 |  | No | [7 empty] | n/a
MN | 110 | 411 | DCP | P2016M0199 | Ennis Francis Houses LSRD | Active; Pre-Cert | 271 |  |  | 22 |  | No | [7 empty] | n/a
MN | 110 | 480 | DCP | P2017M0295 | Balton Commons | Completed | 36 |  |  | 36 | Joseph Huennekens | ZAP currently only includes information on units associated with MIH and voluntary affordable housing for this project. How many total residential units do we expect this project to introduce? | [7 empty] | n/a
MN | 110 | 483 | DCP | P2017M0377 | NMEIII West 140th and West 150th | On-Hold; Pre-Cert | 61 |  |  | 61 |  | No | [7 empty] | n/a
MN | 110 | 534 | DCP | P2018M0055 | W. 132nd Street Rezoning | On-Hold; Pre-Cert | 0 |  |  |  |  | No | [5 empty] | Site waas landmarked, unlikely |  | Project removed | [10 empty] | 1
MN | 110 | 539 | DCP | P2018M0144 | 116 Edgecombe Avenue | Active; Pre-Cert | 75 |  |  |  |  | No | [7 empty] | n/a
MN | 110 | 541 | DCP | P2018M0158 | NIHOP and NCP Cluster I (Northern Cluster) | Active; Pre-Cert | 30 |  |  | 30 | Joseph Huennekens | In mid-year 2018, you had provided feedback that this project was UNCERTAIN to be built by 2025. Is this still the case? If not, what is the likelihood that this project will be built by 2025? By 2035? | Uncertain | Too early stage in DCP process, applicant has not submitted a Pre-Application Statement | likely |  |  | I would say by 2025 only because these sites are being developed as-of-right just requires HPD discretionary actions and these are mostly small sites |  | Realistic |  |  |  | 1 | 0 | 0
MN | 110 | 542 | DCP | P2018M0159 | NIHOP and NCP Cluster II (Middle Cluster) | Active; Pre-Cert | 40 |  |  | 40 | Joseph Huennekens | In mid-year 2018, you had provided feedback that this project was UNCERTAIN to be built by 2025. Is this still the case? If not, what is the likelihood that this project will be built by 2025? By 2035? | Uncertain | Too early stage in DCP process, applicant has not submitted a Pre-Application Statement | likely |  |  | I would say by 2025 only because these sites are being developed as-of-right just requires HPD discretionary actions and these are mostly small sites |  | Realistic |  |  |  | 1 | 0 | 0
MN | 110 | 543 | DCP | P2018M0161 | NIHOP and NCP Cluster III (Southern Cluster) | Active; Pre-Cert | 26 |  |  | 26 | Joseph Huennekens | In mid-year 2018, you had provided feedback that this project was UNCERTAIN to be built by 2025. Is this still the case? If not, what is the likelihood that this project will be built by 2025? By 2035? | Uncertain | Too early stage in DCP process, applicant has not submitted a Pre-Application Statement | JH: likely. Other planner: unlikely |  |  | I would say by 2025 only because these sites are being developed as-of-right just requires HPD discretionary actions and these are mostly small sites. |  | Realistic |  |  |  | 1 | 0 | 0
MN | 110 | 548 | DCP | P2018M0332 | NIHOP and NCP Cluster V (Western Site) | Active; Pre-Cert | 6 |  |  |  | Joseph Huennekens | How many residential units do we expect this project to introduce? | Uncertain | Too early stage in DCP process, applicant has not submitted a Pre-Application Statement | [5 empty] | n/a
MN | 110 | 549 | DCP | P2018M0335 | La Hermosa | Active; Pre-Cert | 204 |  |  | 204 | Joseph Huennekens | ZAP currently only includes information on units associated with MIH and voluntary affordable housing for this project. How many total residential units do we expect this project to introduce? | Likely | [6 empty] | n/a
MN | 110 | 14748 | HPD RFP | 13 | MWBE Site F - 263-267 West 126th Street | RFP | [5 empty] | No | [7 empty] | n/a
MN | 110 | 14767 | HPD RFP | 22 | MWBE Site F - 263-267 West 126th Street | RFP | [5 empty] | No | [7 empty] | n/a
MN | 110 | 14799 | HPD RFP | 51 | MWBE Site F - 263-267 West 126th Street | RFP | [5 empty] | No | [7 empty] | n/a
MN | 110 |  | City Hall public sites list | Current 32 | Central Harlem I & II |  |  | ? |  |  | Joseph Huennekens | Does MNO know where this HPD RFP is located & total units? If so, please provide BBL & # of units. In Perkin's district. Joe Huennekens: Developer is Lemor & IRIS. Estimated to be 100 affordable units - total units unknown. Lemor Realty was the developer/coapplicant with HPD on Balton Commons (P2019M0295), which is a proposed 36-unit building at 263W. 126th Street…perhaps this is connected? That’s been my only interaction with them. Would you like me to reach out to HPD and ask them if they have more information? |  |  | ? | ? | ? |  |  | Project may need to be removed | Corresponding ZAP projects found |  | Agreed. | [7 empty] | 1
MN | 111 | 34 | DCP | 2019M0237 | Las Raices | Active; Initiation | 88 |  |  | 88 |  | No | [7 empty] | n/a
MN | 111 | 228 | DCP | P2014M0466 | East River Plaza | On-Hold; Pre-Cert | 1100 |  |  | 700 |  | No | [7 empty] | n/a
MN | 111 | 233 | DCP | P2014M0548 | Lexington Gardens II | Complete; Completed | 400 |  |  | 0 |  | No | [7 empty] | n/a
MN | 111 | 234 | DCP | P2014M0556 | 2262-2280 Third Avenue; and 2246-2258 Third Avenue | On-Hold; Pre-Cert | 157 |  |  | 157 |  | No | [7 empty] | n/a
MN | 111 | 413 | DCP | P2016M0259 | 1700 Park Avenue | On-Hold; Pre-Cert | 289 |  |  | 289 | Beverly Jimenez-Talavera | In mid-year 2018, you had provided feedback that this project was UNCERTAIN to be built by 2025. Is this still the case? If not, what is the likelihood that this project will be built by 2025? By 2035? | Uncertain | This site was rezoned as part of the EH Rezoning. The developer may still develop the site but will have to go through HPD to modify controls on the site. |  | likely |  | By the latter year is more likely. As a result of the rezoning they can build as of right but they still need discretionary actions from HPD in order to develop. |  | Realistic |  |  |  | 0 | 1 | 0
MN | 111 | 418 | DCP | P2016M0355 | ECF East 96th Street | Active; Completed | 1200 |  |  | 1200 | Calvin Brown | This project has not materialized in DOB permits despite being certified before mid-2017. What is the likelihood that this project will be built by 2025? By 2035? | Likely |  |  | likely |  | By the latter year is more likely because the project is currently being legally challenged. |  | Potentially aggressive | Include 50% in 2035 and 50% in 2055 similar to Two Bridges |  |  | 0 | 0.5 | 0.5
MN | 111 | 421 | DCP | P2016M0429 | East 126th Street Bus Depot Memorial Project | Complete; Completed | 730 |  |  | 0 |  | No | [7 empty] | n/a
MN | 111 | 478 | DCP | P2017M0259 | Sendero Verde East 111th Street | Active; Completed | 710 |  |  |  |  | No | [7 empty] | n/a
MN | 111 | 535 | DCP | P2018M0058 | Terence Cardinal Cooke Rezoning | Active; Pre-Cert | 529 |  |  | 529 |  | No | [7 empty] | n/a
MN | 111 | 544 | DCP | P2018M0162 | NIHOP and NCP Cluster IV (CB11 Site) | Active; Pre-Cert | 8 |  |  | 8 | Joseph Huennekens | In mid-year 2018, you had provided feedback that this project was UNCERTAIN to be built by 2025. Is this still the case? If not, what is the likelihood that this project will be built by 2025? By 2035? | Uncertain | Too early stage in DCP process, applicant has not submitted a Pre-Application Statement | ? | ? | ? |  |  | No inputs given | Include in 2025 given small sites |  |  | 1 | 0 | 0
MN | 111 | 14199 | EDC | 2 | 126 St Bus Depot |  | 730 |  |  | 730 |  | No | [7 empty] | n/a
MN | 111 | 14757 | HPD RFP | 138 | SustaiNYC (E. 111th Street) | RFP | [5 empty] | No | [7 empty] | n/a
MN | 111 | 14872 | Neighborhood Study | 125th St MEC Center EAST HARLEM REZONING COMMITMENT |  |  | 700 |  |  |  |  | How many residential units do we expect from this commitment site? | [7 empty] | Project may need to be removed | Curbed says this has filed a permit app EOY 2017 |  | In permit data for ~400 units -- let's omit this planner input as it's incorrect, and we could instead have this flow through the Neighborhood Study projects.
MN | 111 | 14873 | Neighborhood Study | 126th St Bus Depot EAST HARLEM REZONING COMMITMENT |  |  | 730 |  |  |  |  | How many residential units do we expect from this commitment site? | [7 empty] | Project may need to be removed | This is also an EDC pipeline project |  | Project is zeroed out because it intersects with EDC
MN | 111 | 15287 | Neighborhood Study | Acacia Gardens EAST HARLEM REZONING COMMITMENT |  |  | 179 |  |  |  |  | How many residential units do we expect from this commitment site? |  |  | likely |  |  | under construction |  | Project may need to be removed | Check if DOB permit |  | No DOB permit but this appears in the pre-closings data | 1 | 0 | 0
MN | 111 | 15336 | Neighborhood Study | Lexington Gardens EAST HARLEM REZONING COMMITMENT |  |  | 400 |  |  |  |  | How many residential units do we expect from this commitment site? |  |  | likely |  |  | under construction |  | Project may need to be removed | Check if DOB permit |  | Matches with permit | 1 | 0 | 0
MN | 111 | 15348 | Neighborhood Study | (Projected RFP) HRA East Harlem Multi‐Service Center (Site 1) EAST HARLEM REZONING COMMITMENT |  |  | 200 |  |  |  |  | How many residential units do we expect from this commitment site? | [5 empty] | estimated 175 -211 (depending on the zoning; this may be a rezoning) |  | No inputs given | Override with generic build year rules
MN | 111 | 15349 | Neighborhood Study | (Projected RFP) NYPD 25th Precinct Parking Lot (Site 2) EAST HARLEM REZONING COMMITMENT |  |  | 240 |  |  |  |  | How many residential units do we expect from this commitment site? | [7 empty] | No inputs given | Override with generic build year rules
MN | 111 | 15350 | Neighborhood Study | (Projected RFP) Urban Assembly School (Site 4) EAST HARLEM REZONING COMMITMENT |  |  |  |  | 75 units (81169 sqft * 0.93 Remaining FAR on site) |  |  | How many residential units do we expect from this commitment site? |  |  |  | not likely |  | SCA/DOE have not committed to developing this site. It was explored as part of the process but we don’t expect any residential units on this site by 2035 |  | No inputs given | Include in 2055 |  |  | 0 | 0 | 1
MN | 111 | 15359 | Neighborhood Study | Sendero Verde EAST HARLEM REZONING COMMITMENT |  |  | 711 |  |  |  |  | How many residential units do we expect from this commitment site? | [7 empty] | No inputs given | Check Sendero Verde CEQR docs or ZAP for estimated build year |  | No need -- project is zeroed out after matches to HPD and DOB pipeline
MN | 111 | 85135 | MNO | List BBLs here | P2019M0031 - 201 East 125th Street | ? | 953 |  |  |  | Calvin Brown |  |  |  | 404 units | 549 units |  | the project will be developed in three phases with 404 residential units being built first by 2025; the remainder of the site should be developed by 2035 with a total (including the 404 units) of approximately 953 residential units. |  | Realistic |  |  |  | 0.42392 | 0.57608 | 0 | [10 empty] | 1
MN | 111 | 85128 | map |  | NYCHA BTP Washington Houses |  | 1050 | Planner input: 600-1500. Taking average. | [9 empty] | additional units dependent on remaining at R7-2 or pursuing R8 |  | Project may need to be removed | Do not count any more NYCHA projects beyond what's in existing spreadsheets |  | Not in Public Sites | [7 empty] | 1 | [5 empty] | 1
MN | 111 | 85129 | map |  | NYCHA BTP Washington Houses |  | 1150 | Planner input: 600-1700. Taking average. | [9 empty] | additional units dependent on remaining at R7-2 or pursuing R7X |  | Project may need to be removed | Do not count any more NYCHA projects beyond what's in existing spreadsheets |  | Not in Public Sites | [7 empty] | 1 | [5 empty] | 1
MN | 111 | 85130 | map |  | MEC HPD project |  | 700 | [10 empty] | was at DCP in 2008. |  | Project may need to be removed | This looks like it's same as the East Harlem 125th commitment site |  | Agreed -- same project. | [7 empty] | 1 | [5 empty] | 1
MN | 111 | 85131 | map |  | Savoy Park II Houses infill |  | 1200 | [8 empty] | uncertain |  | very preliminary plan for infill (akin to Lenox Terrace) |  | Potentially aggressive | Include in 2055 unless in ZAP |  |  | 0 | 0 | 1 | [10 empty] | 1
MN | 112 | 222 | DCP | P2014M0274 | Broadway-Sherman Avenue Rezoning (Sherman Plaza) -> Now AOR at 4650 Broadway | Complete; Completed | 272 |  |  |  |  | No |  |  | uncertain | likely |  | This project was disapproved at the City Council level so it did not move forward. An article posted in Fall of 2018 shows an as-of-right proposal expected to consist of 272 residential units at the site: https://newyorkyimby.com/2018/11/hello-living-acquires-4650-broadway-for-55-million-releases-new-renderings.html. There are no filings at DOB for a development at this time, however, there seems to be demo permit for the existing garage: http://a810-bisweb.nyc.gov/bisweb/JobsQueryByLocationServlet?requestid=1&allbin=1064218&allstrt=BROADWAY&allnumbhous=4650 |  | Realistic | Agree with 50% in 2025 |  |  | 0.5 | 0.5 | 0
MN | 112 | 324 | DCP | P2015M0208 | Seaman Avenue Rezoning | Complete; Completed | 29 |  |  | 29 |  | No | [7 empty] | n/a
MN | 112 | 336 | DCP | P2015M0454 | 207th Street Rezoning North Cove at Sherman Creek | On-Hold; Pre-Cert | 832 |  |  | 218 |  | No | [7 empty] | n/a
MN | 112 | 14742 | HPD RFP | 124 | Inwood Library | RFP | [5 empty] | No | [7 empty] | n/a
MN | 112 | 14965 | Neighborhood Study | 25 INWOOD REZONING COMMITMENT | [7 empty] | No | [7 empty] | n/a
MN | 112 | 15062 | Neighborhood Study | 4 INWOOD REZONING COMMITMENT | [7 empty] | No | [7 empty] | n/a
MN | 112 | 15304 | Neighborhood Study | DOT Bridge Repair Facility INWOOD REZONING COMMITMENT | [7 empty] | No | [7 empty] | n/a
MN | 112 | 15306 | Neighborhood Study | Dyckman Houses INWOOD REZONING COMMITMENT | [7 empty] | No | [7 empty] | n/a
|  |  | Neighborhood Study | 4095 Ninth Avenue INWOOD REZONING COMMITMENT | 4095 Ninth Avenue INWOOD REZONING COMMITMENT |  |  |  | 367 units (60995 sqft * 6.02 FAR)