## QN Housing Pipeline
Boro | CD | Map ID | Source | Project ID | Project Name | Status | Total Units | Notes on Total/KS assumed units | Units KS | Units remaining (not accounted for in other sources) | Lead Planner | Request for Update | Remaining units likely to be built? | Rationale | Remaining units likely to be built by 2025? (Likely/ Uncertain/ Not likely/ No units remaining) | Remaining units likely to be built by 2035? (Likely/ Uncertain/ Not likely/ No units remaining) | Remaining units likely to be built by 2055? (Likely/ Uncertain/ Not likely/ No units remaining) | Rationale for likely to be built | Phasing (if known) | Commercial SF | Note | MQL View | Suggestion | Must get boro input | Response to MQL View | Portion Built 2025 | Portion Built 2035 | Portion Built 2055 | Outdated Overlapping Project | Non-Residential Project (incl. Group Quarters) | Withdrawn Project | Inactive Project | Other Reason to Omit | Corrected Existing Geometry | Corrected Existing Unit Count | Updated Unit Count | Should be in old ZAP Pull | Should be in new ZAP Pull | Planner Added Project
QN | 401 | 93 | DCP ZAP | P2012Q0022 | 38th St- 35th Ave Rezoning | Active; Public Review | 118 |  |  | 118 | Joy Chen | No | Likely |  | likely | [6 empty] | Realistic |  |  |  | 1 | 0 | 0
QN | 401 | 95 | DCP ZAP | P2012Q0062 | HALLETTS POINT | Complete; Completed | 2644 |  |  | 2172 | Rafael Berges Jr. | In mid-year 2018, you had provided feedback that this project was UNCERTAIN to be built by 2025. Is this still the case? If not, what is the likelihood that this project will be built by 2025? By 2035? | Likely | Construction is currently stalled, but applicant is currently engaged with DCP in conversations about new waterfront certification. Project is also eligible for federal Opportunity Zone funds. | Not likely | 1/2 remaining units likely | All remaining untis likely |  |  |  |  | Realistic |  |  |  | 0 | 0.5 | 0.5
QN | 401 | 96 | DCP ZAP | P2012Q0102 | VERNON BLVD- BROADWAY REZONING | Active; Pre-Cert | 261 |  |  | 261 | Joy Chen | No | Likely |  |  | Likely | [5 empty] | Realistic |  |  | ZAP Build Year is 2016 -- not a useful data point | 0 | 1 | 0
QN | 401 | 99 | DCP ZAP | P2012Q0127 | 23RD AVENUE REZONING | Complete; Completed | 2 |  |  | 2 |  | No | [9 empty] | Realistic
QN | 401 | 100 | DCP ZAP | P2012Q0311 | ASTORIA COVE DEVELOPMENT | Complete; Completed | 1723 |  |  | 1723 | Rafael Berges Jr. | This project has not materialized in DOB permits despite being certified before mid-2017. What is the likelihood that this project will be built by 2025? By 2035? | Likely | Project is currently stalled and owner has not provided signal that they are moving forward with development in the near future. Long-term build-out likely due to market potential. | Not likely | 1/3 total units likely | All remaining untis likely |  |  |  |  | Realistic |  |  |  | 0 | 0.33333 | 0.66667
QN | 401 | 236 | DCP ZAP | P2014Q0200 | 38th St - 35 th st Ave. Rezoning | Complete; Completed | 26 |  |  | 0 |  | No | [9 empty] | n/a
QN | 401 | 237 | DCP ZAP | P2014Q0210 | 14-41 Broadway Rezoning | Complete; Completed | 28 |  |  | 13 |  | No | [9 empty] | n/a
QN | 401 | 344 | DCP ZAP | P2015Q0070 | 12th Street & 31st Avenue Rezoning | On-Hold; Pre-Cert | 61 |  |  | 61 |  | No | [9 empty] | n/a
QN | 401 | 351 | DCP ZAP | P2015Q0578 | 11-14 35th AVENUE Ravenswood Rezoning | Active; Public Review | 84 |  |  | 84 |  | No | [9 empty] | n/a
QN | 401 | 423 | DCP ZAP | P2016Q0060 | 35-10 Astoria Boulevard South Rezoning | Complete; Public Review | 35 |  |  | 35 |  | No | [9 empty] | n/a
QN | 401 | 425 | DCP ZAP | P2016Q0278 | Variety Boys and Girls Club Rezoning | Active; Public Review | 112 |  |  | 112 |  | No | [9 empty] | n/a
QN | 401 | 430 | DCP ZAP | P2016Q0381 | 44-01 Northern Boulevard Rezoning | Active; Pre-Cert | 310 |  |  | 310 | Blake Montieth | No | Likely |  | Likely | [6 empty] | Realistic |  |  |  | 1 | 0 | 0
QN | 401 | 489 | DCP ZAP | P2017Q0152 | 20th Avenue Elimination - Queens | Active; Pre-Cert | 51 |  |  |  | Phillip Montgomery | How many residential units do we expect this project to introduce? |  |  | likely | [6 empty] | Realistic |  |  |  | 1 | 0 | 0
QN | 401 | 493 | DCP ZAP | P2017Q0380 | 26th Road Rezoning | On-Hold; Pre-Cert | 40 |  |  | 40 | Blake Montieth | In mid-year 2018, you had provided feedback that this project was LIKELY expected to be built by 2025. However, it has moved from active to on-hold. What is the likelihood that this project will be built by 2025? By 2035? | Not likely | DCP will close application due to inactivity | Not likely | Not likely | Not likely |  |  |  |  | Potentially conservative | Include in 2055 |  |  | 0 | 0 | 1
QN | 401 | 552 | DCP ZAP | P2018Q0042 | 47-15 34th Avenue Rezoning | Active; Public Review | 201 |  |  | 201 | Blake Montieth | No | Likely |  | Likely | [6 empty] | Realistic |  |  |  | 1 | 0 | 0
QN | 401 | 553 | DCP ZAP | P2018Q0046 | LICIC - 44th Drive Waterfront Rezoning | On-Hold; Pre-Cert | 1146 |  |  | 1146 | Alexis Wheeler | This is a large project that may be affected by the Amazon departure. What updated information can you share regarding project likelihood and latest phasing plans (break down as much as possible ## of units by a specific year)? | Likely |  | ? | ? | ? |  |  |  |  | Project removed | [10 empty] | 1
QN | 401 | 556 | DCP ZAP | P2018Q0101 | 22-60 46th Street (MEGA) Rezoning | Active; Pre-Cert | 53 |  |  | 53 | Blake Montieth | No | Likely |  | Likely | [6 empty] | Realistic |  |  |  | 1 | 0 | 0
QN | 401 | 557 | DCP ZAP | P2018Q0120 | 30-11 12th Street Rezoning | Active; Pre-Cert | 0 |  |  | 0 | Blake Montieth | No | Likely |  | Likely | [6 empty] | Potentially aggressive | Override with generic build year rules
QN | 401 | 559 | DCP ZAP | P2018Q0146 | 23-83 31st St Rezoning | On-Hold; Pre-Cert | 50 |  |  | 50 | Blake Montieth | In mid-year 2018, you had provided feedback that this project was LIKELY expected to be built by 2025. However, it has moved from active to on-hold. What is the likelihood that this project will be built by 2025? By 2035? | Not likely | DCP will close application due to inactivity | Not likely | Not likely | Not likely |  |  |  |  | Potentially conservative | Include in 2055 |  |  | 0 | 0 | 1
QN | 401 | 562 | DCP ZAP | P2018Q0324 | 42-01 28th Avenue Rezoning | Active; Pre-Cert | 66 |  |  | 66 | Blake Montieth | ZAP currently only includes information on units associated with MIH and voluntary affordable housing for this project. How many total residential units do we expect this project to introduce? | Likely |  | Likely | [6 empty] | Realistic |  |  |  | 1 | 0 | 0
QN | 401 | 563 | DCP ZAP | P2018Q0325 | 43-19 35th Avenue Rezoning | Active; Pre-Pas | 230 |  |  | 230 | Blake Montieth | ZAP currently only includes information on units associated with MIH and voluntary affordable housing for this project. How many total residential units do we expect this project to introduce? | Likely |  | Not likely | Likely | [5 empty] | Realistic |  |  |  | 0 | 1 | 0
QN | 401 | 85416 | Map |  | West Cove |  | 1375 |  |  |  | Rafael Berges Jr. |  |  |  |  | likely | [5 empty] | Realistic |  |  | In ZAP (w/o important information) as project 2018Q0491 | 0 | 1 | 0 | [10 empty] | 1
QN | 401 | 85417 | City Hall public sites list | Pipeline 17 | Astoria DOT Lot (Seniors) | Pipeline RFP/RFEI | 150 |  |  | 150 | Blake Montieth | Does QNO know where this planned HPD RFP/RFEI is located and how many total units? If so, please provide BBL and # of units. In Constantinides' district. KS: geocoded from map comment. | Likely |  | Likely | [6 empty] | Realistic |  |  |  | 1 | 0 | 0
QN | 401 | 85418 | QNO | List BBLs here | Garage One Site - 34-28 21 St (Sanitation Garage) |  |  |  | 146 units (59971 sqft * 2.43 FAR) | [6 empty] | likely | [5 empty] | Uncertain | Any more context? |  |  | 0 | 1 | 0 | [10 empty] | 1
QN | 401 | 85420 | Map |  | LIC Waterfront |  | 7300 |  |  |  | Alexis Wheeler |  |  |  | 2433.3333 | 4866.6667 | [5 empty] | Realistic |  |  |  | 0.33333 | 0.66667 | 0 | [10 empty] | 1
QN | 401 | 85421 | QNO | List BBLs here | NY Blood Center - 10-01 45 Rd |  |  |  | 325 units (81291 sqft * 4 FAR) |  | ? |  |  |  | ? | ? | ? |  |  |  |  | No input given | Include in 2055 |  | This project (P2017M0300) has no residential data and has been listed in initation for 400+ days | 0 | 0 | 1 |  |  |  | 1 | [6 empty] | 1
QN | 401 | 85430 | Map |  | Kaufman Arts District |  | 3000 |  |  |  | Blake Montieth |  |  |  |  | 1500 | 1500 |  |  | 450000 | This development would include about 3,000 housing units with about 450,000 square feet of commercial floor area. The zoning districts would potentially be C4-2F, C6-3, and C4-5D. I anticipate that half of the development would be complete by 2035 and the remaining half would be complete by 2055 | Realistic |  |  | Project in ZAP as 2018Q0489 -- no residential data | 0 | 0.5 | 0.5 | [6 empty] | 1 | 1500 | 1 |  | 1
QN | 402 | 101 | DCP ZAP | P2012Q0313 | 22-44 Jackson Avenue (formerly known as Wolkoff) | Complete; Completed | 372 |  |  | 0 |  | No | [9 empty] | Realistic
QN | 402 | 157 | DCP ZAP | P2013Q0443 | 11-55 49th Avenue Rezoning | Complete; Completed | 140 |  |  | 0 |  | No | [9 empty] | Realistic
QN | 402 | 235 | DCP ZAP | P2014Q0025 | Silvercup West Special Permit Renewals | Complete; Completed | 1000 |  |  | 1000 | Penny Lee | In mid-year 2018, you had provided feedback that this project was UNCERTAIN to be built by 2025. Is this still the case? If not, what is the likelihood that this project will be built by 2025? By 2035? | Uncertain | Site cleanup complete in Jan. 2018.However, permits expired in 7/2016; approved plan not buildable without follow up actions |  | likely |  | Same Comment as 2018, unlikely it will be built by 2025, 2035 more likely. |  |  |  | Realistic |  |  |  | 0 | 1 | 0
QN | 402 | 239 | DCP ZAP | P2014Q0465 | Barnett Avenue Rezoning | Active; Completed | 209 |  |  | 209 | Scott Solomon | No |  |  | See project ID 2017Q0346 below regarding same site. The original project was withdrawn from ULURP. | [5 empty] | Withdrawn in 2016; 50-25 Barnett Ave Rezoning is new iteration with 164 units only | Project removed | [6 empty] | 1
QN | 402 | 424 | DCP ZAP | P2016Q0098 | 52nd Street Rezoning | Active; Pre-Cert | 60 |  |  | 60 |  | No |  |  | 60 | 0 | 0 | Certification before end of 2019 with ULURP approval likely |  |  |  | Realistic |  |  |  | 1 | 0 | 0
QN | 402 | 432 | DCP ZAP | P2016Q0413 | 69-02 Queens Boulevard Rezoning & LSGD | Active; Public Review | 561 |  |  | 561 |  | No |  |  | 481 | [5 empty] | 2019Q0331 Minor Modifications post ULURP. 481 dwelling units proposed as per PAS. | Realistic |  |  |  | 1 | 0 | 0 | [6 empty] | 1 | 481
QN | 402 | 433 | DCP ZAP | P2016Q0436 | 62-04 Roosevelt Ave Rezoning | Active; Pre-Cert | 213 |  |  | 213 |  | No | [9 empty] | Realistic
QN | 402 | 486 | DCP ZAP | P2017Q0067 | Anable Basin Special District | On-Hold; Pre-Cert | 4995 |  |  | 4995 | Alexis Wheeler | This is a large project that may be affected by the Amazon departure. What updated information can you share regarding project likelihood and latest phasing plans (break down as much as possible ## of units by a specific year)? | Likely |  | Unlikely | [5 empty] | Private applicants & EDC still assessing options. Refer to AW & JY for updated information. | Project removed | [10 empty] | 1
QN | 402 | 492 | DCP ZAP | P2017Q0346 | 50-25 Barnett Avenue Rezoning | Active; Pre-Cert | 164 |  |  | 164 |  | No |  |  | 164 | 0 | 0 | Certification before end of 2020 with ULURP approval likely |  |  |  | Realistic |  |  |  | 1 | 0 | 0
QN | 402 | 494 | DCP ZAP | P2017Q0385 | 27-01 Jackson Ave. Disposition of Dev. Rights | Complete; Completed | 120 |  |  |  | Blake Montieth | No | Likely |  | Likely | [6 empty] | Realistic |  |  |  | 1 | 0 | 0
QN | 402 | 495 | DCP ZAP | P2017Q0386 | 26-32 Jackson Ave. Disposition of Dev. Rights | Complete; Completed | 361 |  |  |  | Blake Montieth | No | Likely |  | Likely | [6 empty] | Realistic |  |  |  | 1 | 0 | 0
QN | 402 | 497 | DCP ZAP | P2017Q0427 | Court Square Block 3 Text Amendment | Active; Public Review | 272 |  |  | 272 | Blake Montieth | No | Likely |  | Likely | [6 empty] | Realistic |  |  |  | 1 | 0 | 0
QN | 402 | 551 | DCP ZAP | P2018Q0040 | Queens Blvd MIH Text Amendment | Active; Pre-Cert | 323 |  |  | 201 |  | No |  |  | 323 | 0 | 0 | Certification before end of 2020; non-ULURP text amendment, approval reasonable |  |  |  | Realistic |  |  |  | 1 | 0 | 0
QN | 402 | 14723 | HPD RFP | 107 | LIC Waterfront Mixed-Use Development | RFP | [5 empty] | No | [9 empty] | n/a
QN | 402 | 14732 | HPD RFP | 115 | 11-24 Jackson Ave (EDC) | RFP | [5 empty] | No | [9 empty] | n/a
QN | 402 | 14747 | HPD RFP | 129 | 11-24 Jackson Ave (EDC) | RFP | [5 empty] | No | [9 empty] | n/a
QN | 402 | 14754 | HPD RFP | 135 | Hunters Point F + G | RFP | [5 empty] | No | [9 empty] | n/a
QN | 402 | 14756 | HPD RFP | 137 | Hunters Point F + G | RFP | [5 empty] | No | [9 empty] | n/a
QN | 402 | 14842 | HPD RFP | 90 | LIC Waterfront Mixed-Use Development | RFP | [5 empty] | No | [9 empty] | n/a
QN | 402 | 14845 | HPD RFP | 93 | LIC Waterfront Mixed-Use Development | RFP | [5 empty] | No | [9 empty] | n/a
QN | 402 | 85422 | map |  | Arch Street Yard |  | 4500 |  |  |  | Coralie Ayres |  |  |  |  | 1000 | remainder | 2,000 units by 2035 at a 50% confidence and the remaining balance at 100% by 2055 |  |  |  | Uncertain | Any more context? |  | Overriding planner input. We are treating EDC projects which R. Holbrook did not provide to us as 2055, so we should do the same here. ? | 0 | 0 | 1 | [10 empty] | 1
QN | 402 | 85423 | City Hall public sites list | Pipeline 29 | Hunters Point D+E | Pipeline RFP/RFEI | 1704 |  |  |  | Coralie Ayres | How many total residential units? What is the phasing (# of units by X year)? Estimated 1020 affordable units - total units unknown. |  |  | likely |  |  | HPD have confirmed the dwelling unit number is the same as I provided earlier for the Hunter’s Point Parcels D + E. However, they are more optimistic regarding the anticipated completion year- being 2025 |  |  |  | Realistic |  |  |  | 1 | 0 | 0
QN | 402 | 85424 | map |  | Hunters Point Subdistrict B |  | 1550 | Planner input: 1500-1600. Taking average. |  |  | Coralie Ayres |  |  |  |  | likely | [5 empty] | Realistic |  |  |  | 0 | 1 | 0 | [10 empty] | 1
QN | 402 | 85425 | QNO | 2019Q0089 | 21-31 46th Avenue Rezoning | Active; Pre-Cert | 108 |  |  | 108 | Coralie Ayres |  |  |  | 108 | 0 | 0 | Early stage, subject to change (scale of development & neighborhood trend) |  | 7124 |  | Realistic |  |  |  | 1 | 0 | 0 | [9 empty] | 1
QN | 402 | 85426 | QNO | 2019Q0284 | 44-61 11th Street Rezoning | Active; Pre-PAS | 64 |  |  | 64 | Coralie Ayres |  |  |  | 64 | 0 | 0 | Early stage, subject to change (scale of development & neighborhood trend) |  |  |  | Potentially aggressive | Override with generic build year rules | [14 empty] | 1
QN | 402 |  | QNO | 2019Q0118 | RiverLInc (BBL 4004890001) | Active; Pre-Cert | 1537 | Planner input: 1537 (Max res scenario) Market = 1,153 Affordable = 384 |  | 1537 | Coralie Ayres |  |  |  | 1537 (originally one phase- subject to change with revised scheme) | 0 | 0 | Development site is currently vacant, remediated and unimproved. It is estimated that construction would last for approximately 48 to 54 months. |  | 1035661 | KS: Project subsumed by LIC waterfront total count. | Potentially conservative | Include in 2055 |  | This project is struckthrough because it is included in Alexis Wheeler's LIC Waterfront estimates. | [7 empty] | 1 | [5 empty] | 1
QN | 403 | 555 | DCP ZAP | P2018Q0090 | 34-20 Junction Blvd. Rezoning | On-Hold; Pre-Cert | 281 |  |  | 281 | Kathi Ko | In mid-year 2018, you had provided feedback that this project was LIKELY expected to be built by 2025. However, it has moved from active to on-hold. What is the likelihood that this project will be built by 2025? By 2035? | Likely |  | Not Likely | Maybe likely | [5 empty] | Realistic |  |  |  | 0 | 0.5 | 0.5
QN | 403 | 85419 | Map |  | Koeppel Nissan Rezoning | close to submitting PAS | 212 |  |  |  | Kathi Ko |  |  |  | ? | ? | ? | Approximately 212 DUs. They haven’t submitted a PAS yet, but seem ready to do so soon, so maybe 2025 if they can act quickly? |  |  |  | Potentially aggressive | Override with generic build year rules | [15 empty] | 1
QN | 404 | 102 | DCP ZAP | P2012Q0315 | 88-08 Justice Avenue Restrictive Dec Termination | Active; Public Review | 184 |  |  | 184 |  | No | [9 empty] | Project may need to be removed | Check if built since this is a RD termination |  | Not yet built. Still in construction (https://www.cityrealty.com/nyc/east-elmhurst/88-08-justice-avenue/171772), Cyclomedia shows in construction as of September 2018.
QN | 404 | 238 | DCP ZAP | P2014Q0364 | Corona Senior Residence | Complete; Completed | 66 |  |  | 0 |  | No | [9 empty] | n/a
QN | 404 | 485 | DCP ZAP | P2017Q0039 | 74-21 Queens Blvd. Rezoning | Active; Pre-Cert | 115 |  |  | 115 |  | No | [9 empty] | n/a
QN | 404 | 487 | DCP ZAP | P2017Q0099 | 40-31 82nd Street Rezoning | Complete; Public Review | 88 |  |  | 88 |  | No | [8 empty] | This project was withdrawn by the applicant; no residential units proposed. | n/a | [8 empty] | 1
QN | 404 | 496 | DCP ZAP | P2017Q0405 | 110-40 Saultell Avenue Rezoning | Active; Pre-Cert | 45 |  |  | 45 |  | No | [9 empty] | n/a
QN | 405 | 97 | DCP ZAP | P2012Q0110 | 60TH PLACE DEMAPPING | On-Hold; Pre-Cert |  | ? |  |  | Phillip Montgomery | How many residential units do we expect this project to introduce? | [9 empty] | Project may need to be removed | Read project description - is this just a street demapping? |  | Street demapping and zoning to residential. Not site-specific | [7 empty] | 1
QN | 405 | 103 | DCP ZAP | P2012Q0316 | WOODWARD AVENUE REZONING | Complete; Completed | 96 |  |  | 0 | Thomas Smith | In mid-year 2018, you had provided feedback that this project was UNCERTAIN to be built by 2025. Is this still the case? If not, what is the likelihood that this project will be built by 2025? By 2035? | Uncertain | Unclear on developer's future plans. March 21, 2016 Yimby reported new ownership and described proposed 5 story, 130-unit building. | no units remaining |  |  | From Joy: from what I know the plans were to build 88 units by 2016 but from google maps street view in 2018 it looks like construction has just gotten underway on the site. |  |  |  | n/a
QN | 406 | 16 | DCP ZAP | 2018Q0519 | 112-06 71st Road Rezoning | Active; Pre-Cert | 4 |  |  | 0 | Nolan Gray | No |  |  | 0 | 0 | 0 |  |  |  |  | n/a | [7 empty] | 1
QN | 406 | 104 | DCP ZAP | P2012Q0317 | Lost Battalion Hall Park-Rego Center III Rezoning | On-Hold; Pre-Cert | 872 |  |  | 872 | Kathi Ko | In mid-year 2018, you had provided feedback that this project was UNCERTAIN to be built by 2025. Is this still the case? If not, what is the likelihood that this project will be built by 2025? By 2035? | Uncertain | Flagged as a Major Initiative, likely to come back to DCP shortly |  | likely |  | project is on hold and is more likely expected at 2035 |  |  |  | Realistic |  |  |  | 0 | 1 | 0
QN | 406 | 426 | DCP ZAP | P2016Q0293 | Former Parkway Hospital Site Rezoning | Active; Public Review | 351 |  |  | 351 |  | No |  |  | 351 | 0 | 0 | Pursuing SARA financing |  | 0 |  | Realistic |  |  |  | 1 | 0 | 0
QN | 406 | 85427 | QNO | 2019Q0065 | 98-81 Queens Boulevard | Active; Pre-Cert | 170 |  |  | 170 | Nolan Gray |  |  |  | 0 | 170 | 0 | Developed has indicated that ULURP and development will likely push back completion to post-2025. |  |  |  | Potentially conservative | Check which milestone reached and if DCP target cert date is set |  | DCP Target cert date is set to 2/8/2020. Agreed that the planner estimate is conservative and moving half portion built to 2025. | 0.5 | 0.5 | 0 | [9 empty] | 1
QN | 406 | 85428 | QNO | 3086-7; 3086-29; 3086-34 | 98-04 Queens Boulevard | Active; Pre-Cert | 317 |  |  | 317 | Nolan Gray |  |  |  | 0 | 317 | 0 | Early stages of a potential rezoning. Assume remainder is built out like existing building to maximum residential FAR. |  |  |  | Potentially conservative | Check which milestone reached and if DCP target cert date is set |  | This project is not yet in ZAP. We should trust it as other planner inputs -- unlikely that a project not yet in ZAP will materialize by 2025. ? | 0 | 1 | 0 | [10 empty] | 1
QN | 406 | 85429 | QNO | P2019Q0259 | 91-32 63rd Drive Rezoning | Active; Pre-Cert | 70 |  |  | 70 | Nolan Gray |  |  |  | 70 | 0 | 0 | Vacant Site |  | 12113 |  | Uncertain | Any more context? |  |  | 1 | 0 | 0 | [9 empty] | 1
QN | 407 | 91 | DCP ZAP | P2012Q0008 | XU HOTEL AND RESIDENCES | Complete; Completed | 43 |  |  | 32 |  | No | [9 empty] | Project may need to be removed | Check how many units are hotel vs. res |  | 43 residential units (https://www1.nyc.gov/assets/planning/download/pdf/applicants/env-review/eas/13dcp106q_eas.pdf)
QN | 407 | 94 | DCP ZAP | P2012Q0031 | FLUSHING MEADOWS EAST REZONING | Complete; Completed | 376 |  |  | 266 |  | No | [9 empty] | Project may need to be removed | Check if DCP is applicant |  | Private applicant
QN | 407 | 155 | DCP ZAP | P2013Q0005 | Waterpointe - Special Permit Renewal | Complete; Completed | 52 |  |  | 39 | Hye-Kyung Yang | In mid-year 2018, you had provided feedback that this project was UNCERTAIN to be built by 2025. Is this still the case? If not, what is the likelihood that this project will be built by 2025? By 2035? | Likely | Remediation of the site is not 100% complete. Build Year not clear. | Likely | [5 empty] | Remediation is almost complete but its my understanding that the property is being sold again. | Realistic |  |  |  | 1 | 0 | 0
QN | 407 | 156 | DCP ZAP | P2013Q0393 | Union Street Rezoning | Active; Pre-Cert | 34 |  |  | 34 | Hye-Kyung Yang | This project has not materialized in DOB permits despite being certified before mid-2017. What is the likelihood that this project will be built by 2025? By 2035? | Likely | This project will be certified in the later part of this year. | Likely | [6 empty] | Realistic |  |  |  | 1 | 0 | 0
QN | 407 | 345 | DCP ZAP | P2015Q0168 | 135-01 35th Av Rezoning | Complete; Completed | 93 |  |  | 93 | Hye-Kyung Yang | In mid-year 2018, you had provided feedback that this project was UNCERTAIN to be built by 2025. Is this still the case? If not, what is the likelihood that this project will be built by 2025? By 2035? | Likely | Land owner could sell property to flip. Existing use still the same as today's condition. |  | Likely | [5 empty] | Potentially conservative | Override with generic build year rules
QN | 407 | 422 | DCP ZAP | P2016Q0024 | One Flushing | Complete; Completed | 231 |  |  | 0 |  | No | [9 empty] | n/a
QN | 407 | 428 | DCP ZAP | P2016Q0360 | Flushing Point Plaza | Active; Pre-Cert | 326 |  |  | 326 |  | No | [9 empty] | n/a
QN | 407 | 431 | DCP ZAP | P2016Q0402 | Whitestone Lanes Rezoning | Active; Pre-Cert | 300 |  |  | 300 |  | No | [9 empty] | n/a
QN | 407 | 491 | DCP ZAP | P2017Q0242 | Kissena Center Rezoning | Active; Pre-Cert | 183 |  |  | 183 |  | No | [9 empty] | n/a | [12 empty] | 1 | 160
QN | 407 | 554 | DCP ZAP | P2018Q0079 | 20-04 119th Street College Point Rezoning | Active; Pre-Cert | 40 |  |  | 40 |  | No | [9 empty] | n/a
QN | 407 | 85410 | QNO |  | Flushing Commons | Phase 1 complete | 150 |  |  | 450 | Hye-Kyung Yang |  |  |  | Likely |  |  |  |  | 461,000 gsf | This is the former Muni Lot 1 project led by EDC, approved in 2013. Phase 1 is comprised of approximately 219,000 square feet of office and retail space, 150 units of housing, and a 982 space parking lot. Phase 1 was completed in 2017. Phase 2 will include approximately 242,000 square feet of office and retail space, 450 residential units, 618 additional parking spaces, a state-of-the-art YMCA recreational facility, and a 1.5 acre public plaza, The Green at Flushing Commons. Phase 2 is expected to be completed by 2021. The location of this development is Block 4978 Lot 25 and 7502. | Uncertain | Is the 450 units for Phase 2? |  | Yes (http://flushingcommons.com/) | 1 | 0 | 0 | [7 empty] | 600 |  |  | 1
QN | 407 | 85411 | QNO |  | Sky View Parc | Complete | 376 |  |  |  | Hye-Kyung Yang |  |  |  | likely |  |  | Completed 2018 with 1198 units. 822 units were counted in the 2010 census and the remaining 376 need to be added. |  |  | This development was listed as NYC's 5 Best selling residential projects in 2018. First three towers opened in 2011 with 448 units. Second three towers, called the Grand, completed in 2018 with 750 units. Average per sq. ft were sold for $1,000- $1,200 psf. Location of is Block 5066 Lots 7503, 7507. | Project may need to be removed | [10 empty] | 1 | [5 empty] | 1
QN | 407 | 85412 | QNO | P2017Q0052 | Special Flushing Waterfront District | Active; Pre-Cert | 1607 |  |  |  | Hye-Kyung Yang |  | Likely | Site 2 is anticipated to have shovel in ground by end of 2020. | Likely |  |  |  |  | 1.3M gsf | This is a private application currently in the pre-cert process. It is anticipating certification on August 12, 2019. This project stems directly from the work done by Queens DCP on the Brownfield Opportunity Area (BOA) Nomination Report, completed in Fall 2017. The as-of-right scenario would essentially accomplish similar unit and commerical square footage numbers. The private application of this Special District is essentially molding the envelope of these waterfront blocks and replacing the waterfront access plan. The proposal would approx. 1,607 units; 1.3M gsf commerical; 15,000 gsf community facility space; and 1,500 parking spaces. The location of this District is Block 4963, Lots 1, 7, 8, 9, 65, 75, 85, 200, 210, 212 and 249 and Block 5066 Lot 7501. Please note that Block 5066 Lot 7501 is Sky View Parc. They are included in the Project Area because we want to include them in the revised WAP but the Development Site itself is all other other listed Blocks. | Potentially aggressive | All 1,607 units from site? |  | Residential units comprised of 5 sites (EAS). No context on phasing. Placing portions evenly across 2025 and 2035. | 0.5 | 0.5 | 0 | [8 empty] | 1
QN | 407 | 85413 | QNO |  | Willets Point Phase I |  | 1100 |  |  |  | Hye-Kyung Yang |  |  |  |  | Likely |  |  |  | 20,000 gfs | Willets Point Phase A is a 6-acre of the originial 23-acre Willets Point Development Phase 1 Site. Phase A is expected to be built with ~1,100, 100% affordable housing; 20,000gssf retail; 6,000 gsf community facility space; a K-8, 450 seat school; 1.2acres of open space; and 300 parking spaces. Remediation, for which the developer is responsible, to be completed by the end of 2020. FIrst building for Phase A is to be completed by 2022 and deliver 500 units of the 1,100 DUs. This is a project lead by EDC. Location of Phase A is Block 1833 Lots 117, 111, 103, 120,141,143,151, 158 and p/o 155. | Realistic |  |  |  | 0 | 1 | 0 | [10 empty] | 1
QN | 407 | 85414 | QNO |  | Charles B Wang Health Center |  | 0 |  |  |  | Hye-Kyung Yang | [8 empty] | 12,000 sq ft | They are going through the BSA process. It will be a 6 story, 12,000 sq ft of ambulatory diagnostic treatment healthcare facility. | Project not counted | [7 empty] | 1 | [8 empty] | 1
QN | 408 | 98 | DCP ZAP | P2012Q0112 | SILVERCREST NURSING HOME SR HOUSING | Complete; Completed | 0 |  |  |  | Nolan Gray | How many residential units do we expect this project to introduce? | [8 empty] | Group quarters, no residential units. | Project not counted |  |  | Looks like we did not receive a response from the planner on this one. It's already materialized in DOB permits (81 units), so no need to refer back. ? |  |  |  |  | 1
QN | 408 | 105 | DCP ZAP | P2012Q0320 | UNION TURNPIKE REZONING | Complete; Completed | 39 |  |  | 0 |  | No | [9 empty] | n/a
QN | 408 | 349 | DCP ZAP | P2015Q0480 | 193-02 Horace Harding Expy Special Permit Mod | Complete; Completed | 1 |  |  | 0 |  | No | [9 empty] | n/a
QN | 408 | 550 | DCP ZAP | P2018Q0025 | Kew Gardens Hills Rezoning | Active; Pre-Cert | 0 |  |  | 0 | Scott Solomon | How many residential units do we expect this project to introduce? Zero. Single family to single family rezoning |  |  | 0 | 0 | 0 | No density increase; one-family to one-family rezoning |  |  |  | Project not counted | [10 empty] | 1
QN | 408 | 85406 | QNO | 7075-1; 7117-130; 7117-4 | Fresh Meadows Place | Active; Pre-Cert | 695 |  |  | 695 | Nolan Gray |  |  |  | 139 | 278 | 278 | Large development with likely a long timeframe |  | 294789 |  | Potentially conservative | Pull up portion in 2055 to 2035 instead |  |  | 0.2 | 0.8 | 0 | [10 empty] | 1
QN | 408 | 85407 | QNO | 6803-2; 6807-2; 6808-25 | Kissena Blvd LSGD | Active; Pre-PAS | 675 |  |  | 675 | Nolan Gray |  |  |  | 225 | 450 | 0 | Applicant has plan for temporary location of residents |  | 39999 |  | Realistic |  |  |  | 0.33333 | 0.66667 | 0 | [10 empty] | 1
QN | 408 | 85408 | QNO | 1810875 | T-Building | Pre-RFP | 202 |  |  | 202 | HPD |  |  |  | 0 | 202 | 0 | Early stages, no RFP as of yet |  |  | This is an upcoming HPD project that wasn't listed. | Realistic |  |  |  | 0 | 1 | 0 | [10 empty] | 1
QN | 408 | 85409 | QNO | P2019Q0174 | 185-17 Hillside Ave Rezoning | Active; Pre-Cert | 45 |  |  | 45 | Nolan Gray |  |  |  | 45 | 0 | 0 | Disused Site |  |  |  | Realistic |  |  |  | 1 | 0 | 0 | [9 empty] | 1
QN | 408 | 85415 | QNO |  | Former Holliswood Hosp Subdivision |  | 20 |  |  |  | Nolan Gray |  |  |  | likely | [6 empty] | Realistic |  |  |  | 1 | 0 | 0 | [10 empty] | 1
QN | 410 | 35 | DCP ZAP | 2019Q0126 | Resilient Housing and Open Space ULURP - Queens | Active; Pre-Cert | 240 |  |  | 240 |  | No | [9 empty] | n/a
QN | 411 | 92 | DCP ZAP | P2012Q0014 | Douglaston Parkway Rezoning | Active; Public Review | 83 |  |  | 83 |  | No |  |  | 83 |  |  | App approved in March 2019; construction imminent |  |  |  | Realistic |  |  |  | 1 | 0 | 0
QN | 411 | 350 | DCP ZAP | P2015Q0501 | 255-23 58th Avenue Authorization | Complete; Completed | 2 |  |  | 0 |  | No |  |  | 2 | 0 | 0 | CO issued |  |  |  | n/a
QN | 412 | 434 | DCP ZAP | P2016Q0479 | Northeastern Towers Annex Rezoning | Complete; Completed | 147 |  |  | 0 |  | No | [9 empty] | n/a
QN | 412 | 558 | DCP ZAP | P2018Q0126 | 192nd Street Rezoning | On-Hold; Pre-Pas | 69 |  |  | 67 |  | No | [9 empty] | n/a
QN | 412 | 85405 | Map |  | GJDC RFP |  | 525 |  |  |  | Stephen Everett |  |  |  | likely | [5 empty] | The GJDC RFP only covers the block to the west of 168th St (both east and west blocks are circled on the map). I confirmed with them that the RFP called for “at least” 350 units, but the winning team is proposing 525. The expected completion date is an aggressive December 2021, but even if it slips, it will be complete before 2025. | Realistic |  |  |  | 1 | 0 | 0
QN | 413 | 429 | DCP ZAP | P2016Q0377 | Cross Island Plaza Rezoning | On-Hold; Pre-Pas | 500 |  |  | 500 |  | No |  |  | 0 | 0 | 0 |  |  |  | Project closed | Uncertain | Any more context? | Planner crossed off project without providing rationale | Record recently closed | [7 empty] | 1
QN | 413 | 561 | DCP ZAP | P2018Q0199 | 146-93 Guy Brewer Blvd Rezoning | Active; Pre-Cert | 42 |  |  | 42 |  | No |  |  | 42 | 0 | 0 | Certification before end of 2020 expected with ULURP approval likely |  |  |  | Realistic |  |  |  | 1 | 0 | 0
QN | 414 | 240 | DCP ZAP | P2014Q0506 | Seagirt Boulevard Rezoning | Complete; Completed | 27 |  |  | 27 | Scott Solomon | In mid-year 2018, you had provided feedback that this project was UNCERTAIN to be built by 2025. Is this still the case? If not, what is the likelihood that this project will be built by 2025? By 2035? Rezoning was speculative and lots remain vacant; 2025 is still reasonable for resi dev | Uncertain | Application for rezoning was in anticipation of speculative development. The owners are not developers and have not yet sold their properties to developers nor have they initiated any building permits with DOB | 27 | 0 | 0 |  |  |  |  | Realistic |  |  |  | 1 | 0 | 0
QN | 414 | 346 | DCP ZAP | P2015Q0306 | Beach 62nd Street Rezoning | On-Hold; Pre-Cert | 504 |  |  | 504 | Hallah Saleh | In mid-year 2018, you had provided feedback that this project was LIKELY expected to be built by 2025. However, it has moved from active to on-hold. What is the likelihood that this project will be built by 2025? By 2035? | Likely |  | 0 | 504 | 0 | Project has been on hold for some time however corresspondence with the applicant has started and will likely continue through ULURP |  |  |  | Realistic |  |  |  | 0 | 1 | 0
QN | 414 | 347 | DCP ZAP | P2015Q0365 | 125-02 Ocean Promenade Rezoning | On-Hold; Pre-Cert | 105 |  |  | 105 | Brendan Pillar | How many residential units do we expect this project to introduce? | [9 empty] | n/a
QN | 414 | 348 | DCP ZAP | P2015Q0366 | Rockaway Beach Boulevard Hotel Rezoning | Complete; Completed | 59 |  |  | 59 |  | No | [9 empty] | n/a
QN | 414 | 427 | DCP ZAP | P2016Q0306 | Peninsula Hospital Redevelopment Plan | Active; Pre-Cert | 2200 |  |  | 2200 |  | No | [9 empty] | n/a
QN | 414 | 488 | DCP ZAP | P2017Q0127 | 618 Seagirt Boulevard Rezoning | On-Hold; Pre-Cert | 386 |  |  | 386 |  | No | [9 empty] | n/a
QN | 414 | 490 | DCP ZAP | P2017Q0212 | Beach 67th Street Rezoning | Active; Pre-Cert | 88 |  |  | 88 |  | No | [9 empty] | n/a
QN | 414 | 560 | DCP ZAP | P2018Q0197 | 22-79 Mott Avenue Rezoning | Active; Pre-Cert | 43 |  |  | 43 | Hallah Saleh | In mid-year 2018, you had provided feedback that this project was UNCERTAIN to be built by 2025. Is this still the case? If not, what is the likelihood that this project will be built by 2025? By 2035? | Uncertain | Too early stage in DCP process, applicant has not submitted a Pre-Application Statement | Uncertain | Uncertain | Uncertain | Adverse impact identified in environmental review, applicant may ultimately withdraw application to avoid EIS |  |  |  | Potentially conservative | Include in 2055 |  |  | 0 | 0 | 1
QN | 414 | 14740 | HPD RFP | 122 | Beach 21st Street - EDC | RFP | [5 empty] | No | [9 empty] | n/a
QN | 414 | 14789 | HPD RFP | 42 | Beach 21st Street - EDC | RFP | [5 empty] | No | [9 empty] | n/a
QN | 414 | 15305 | Neighborhood Study | DOT/MTA Disposition Site DOWNTOWN FAR ROCKAWAY REZONING COMMITMENT | DOT/MTA Disposition Site DOWNTOWN FAR ROCKAWAY REZONING COMMITMENT | [6 empty] | No |  |  | ? | ? | ? |  |  |  |  | n/a
QN | 414 | 85401 | Map |  | Arverne by the Sea - The Dunes |  |  |  | 600 |  | Hallah |  |  |  |  | likely |  | Infrastructure needs to be built and has slowed abiltiy to move forward. |  |  |  | Uncertain | Any more context? | KS: spoke to Barry and Brendan, seems realistic |  | 0 | 1 | 0 | [10 empty] | 1
QN | 414 | 85402 | Map |  | Shorefront Parkway infill |  | 800 |  |  |  | John Young |  |  |  |  | likely |  | let’s assume that 800 units are added to the site by 2035. Plans for this site are quite preliminary and they show up to 1,200 new units at this site. However I can’t see the QO supporting that kind of density here so I reduced it by 25% |  |  |  | Uncertain | Any more context? | KS: more info provided by Brendadn. not sure if this is aggressive or realistic | Going with planner input -- no other information available. ? | 0 | 0.5 | 0.5 | [10 empty] | 1
QN | 414 | 85403 | Map |  | Marcal Rezoning |  |  |  | 500 units (124979 sqft * 4 FAR) |  | John Young |  |  |  |  | likely | [5 empty] | Uncertain | Any more context? | KS: spoke to Barry, seems realistic |  | 0 | 1 | 0 | [10 empty] | 1
QN | 414 | 85404 | Map |  | Arverne (eastern sites) |  | 1200 |  |  |  | Brendan Pilar |  |  |  |  | likely |  | For Arverne East, let’s assume that 1,200 unit get built out by 2035 |  |  |  | Uncertain | Any more context? | KS: more info provided by Brendadn. not sure if this is aggressive or realistic | Going with planner input -- no other information available. ? | 0 | 1 | 0 | [10 empty] | 1
QN |  |  | City Hall public sites list | Current 42 | South Jamaica (NCP) | Current RFP | [5 empty] | Does QNO know where this HPD RFP is located and how many total units? If so, please provide BBL and # of units. In Adam's district. Developer is Infinite Horizons & FG-PH. Estimated 40 affordable units - total units unknown. |  |  | ? | ? | ? |  |  |  |  | n/a
QN |  |  | City Hall public sites list | Current 43 | South Jamaica (NIHOP) | Current RFP | [5 empty] | Does QNO know where this HPD RFP is located and how many total units? If so, please provide BBL and # of units. In Ulrich's district. Developer is Briarwood & Fulcrum. Estimated 23 affordable units - total units unknown. |  |  | ? | ? | ? |  |  |  |  | n/a